## Summ_Module
Summary by Status
No | Issue Type | Request
1 | Pharmacy Inventory | 6
2 | Patient Management | 0
3 | Order Management - Web | 5
4 | Order Management - Mobile | 0
5 | Special Drug Request | 1
6 | Outpatient Pharmacy | 4
7 | Inpatient Pharmacy | 0
8 | MAR - Web | 0
9 | MAR - Mobile | 0
10 | MTAC | 7
11 | Ward Pharmacy | 2
12 | Ward Pharmacy - Mobile | 0
13 | Medication Counseling | 0
14 | Medication Counseling - Mobile | 0
15 | Adverse Drug Reaction (ADR) | 2
16 | Clinical Pharmacokinetic Services (CPS) & TDM | 2
17 | Drug Information & Consumer Education | 0
18 | PhIS Portal | 0
19 | Manufacturing - CDR | 10
20 | Manufacturing - Extemporaneous | 2
21 | Manufacturing - Galenical | 0
22 | Manufacturing - IV | 0
23 | Manufacturing - PN | 0
24 | Manufacturing - Radiopharmaceutical | 0
25 | Data Mining - PhARM | 5
26 | Report/Enquiry | 12
27 | IWP | 1
28 | General Module | 4
29 | BCP | 0
| Total | 63

## Summ_State
No | Issue Type | Request
1 | BPF | 3
2 | Johor | 0
3 | Kedah | 3
4 | Kelantan | 14
5 | Melaka | 2
6 | Pahang | 4
7 | Perak | 4
8 | Pulau Pinang | 7
9 | Sabah | 3
10 | Sarawak | 7
11 | Selangor | 9
12 | Terengganu | 1
13 | W. Persekutuan | 1
14 | Negeri Sembilan | 2
15 | Perlis | 0
16 | HKL | 3
17 | W. Labuan | 0
18 | Institut | 0
| Total | 63

## Total
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks | State
1 | 19628653C | I-PhIS050153219S | 2019-02-18 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | PF Report - To exclude Methadone dispensing in PF report | Methadone dispensing record should be excluded from PF reports (PF5.1, PF 5.4, PF 6.3 and others) that have dispensing records. Current practice also ( manually) , for methadone dispensing activities the reporting is done in specific PF 5.7 a-c report only. | [5 empty] | BPF
2 | 19632177C | I-PhIS050417319S | 2019-02-28 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | BI TOOLS-Request to provide report Drug Allergy Card Registry in BI Tools | Receive email from Ms Norazimah : Dear Helpdesk, Kindly please provide report Drug Allergy Card Registry in PhIS to made available in BI Tools. | [5 empty] | BPF
3 | 19624340C | I-PhIS049809319S | 2019-02-01 | Bahagian Perkhidmatan Farmasi (BPF) | Special Drug Request | request to add filtering Submission date at both screen Special Drug Request and report Permohonan | received email from user : I would like to request to add filtering Submission date at both screen Special Drug Request and report Permohonan KPK. When can i have it? kindly refer file upload | [5 empty] | BPF
4 | 19625818C | I-PhIS049939319S | 2019-02-08 | Hospital Kuala Lumpur | General Module | Permohonan CR: User Profile & User Role - khas untuk Pentadbir Jururawat & Pegawai Perubatan | Receive email from user : Untuk makluman, pihak kami menghadapi kesukaran dalam menyelenggara akaun pengguna terutamanya bagi Jururawat dan Pegawai Perubatan setelah tiga (3) tahun PhIS dijalankan di HKL. Seperti yang diketahui, proses penyelenggaraan akaun pengguna (maintenance of user account/profile) ini penting bagi memastikan hanya pengguna yang aktif sahaja wujud supaya tidak berlaku isu data integrity (contoh: nama prescriber yang tidak lagi wujud digunakan semasa Record Prescription). Tambahan pula, ekoran daripada peluasan PhIS di wad-wad HKL (bagi pelaksaaan imprest stock) memerlukan penyelenggaraan akaun Jururawat yang lebih komprehensif. Oleh sebab pergerakan anggota di HKL adalah sangat kerap dan bilangan anggota yang terlalu ramai, pihak kami memerlukan Pentadbir khusus daripada pihak Jururawat/Pegawai Perubatan. Namun demikian, didapati Role â€œFacility Admin Generalâ€ bagi menyelenggara User Profile dan User Role adalah terikat dengan Role-Group lain seperti Calendar, Mobile_Security, Inventory Notification, Hospital Information yang didapati agak sensitif/boleh membahayakan tetapan sistem di fasiliti menyebabkan ianya tidak sesuai untuk diâ€™enableâ€™kan kepada Pentadbir (Jururawat/Pegawai Perubatan). Oleh yang demikian, pihak kami ingin memohon Change Request bagi mewujudkan Role khusus untuk pentadbir pihak luar daripada Farmasi (pihak Jururawat/Pegawai Perubatan/Pentadbir) untuk membolehkan mereka menyelenggara akaun bagi anggota di bawah jagaan masing-masing. Dilampirkan beberapa screenshot untuk rujukan pihak tuan/puan. Besarlah harapan kami sekiranya permohonan ini dapat dipertimbangkan. | [5 empty] | HKL
5 | 19627685C | I-PhIS050082319S | 2019-02-14 | Hospital Kuala Lumpur | Pharmacy Inventory | request - system to allow indent same drug.non drug code for different item code | user request system to allow indent same drug/non drug code for different item code. For example item: GLN0200022(Bismuth, Iodoform, Liquid Paraffin (BIPP) Paste, Gauze) got 3 different item code, and user need to order 2 different item code , system will prompt alert message item already in list | [5 empty] | HKL
6 | 19631058C | I-PhIS050325119S | 2019-02-25 | Hospital Kuala Lumpur | MTAC | MTAC reporting - Request enhancement | Tuan/puan, Dengan segala hormatnya saya merujuk kepada perkara di atas. Pihak kami ingin membuat Change Request untuk menambah collapsible box Specific Details ke dalam modul MTAC Reporting bagi Cardiac Rehab Program (CRP) (seperti dalam screenshots) yang dilampirkan. Antara fields yang akan dimasukkan di bawah Specific Details adalah seperti berikut (Rujuk lampiran): 1- Thrombolysis - Checkbox (Yes/No) - If yes, Thrombolytic agents; Checkbox: Streptokinase or Tenecteplase or Others (Please specify: Open short text field) - Date given; Calendar field 2- ECHO - At discharge: Numeric field (suffix %) - Date ECHO done: Calendar field - After 6 months: Numeric field (suffix %) - Date ECHO done: Calendar field 3- Stress Test Results - Date Test done: Calendar field - Checkbox: Positive or Negative 4- Percutaneous Coronary Intervention (PCI) Status - Checkbox (Yes/No) - If yes, Types; Checkbox: Drug-eluting Stent (DES) or Bare-metal Stent (BMS) or Drug-eluting Balloon or Bioresorbable Vascular Scaffold (BVS) or Others (Please specity: Open short text field) Memandangkan kami merupakan antara perintis program MTAC CRP, kami amat mengharapkan agar Change Request ini dapat dilaksanakan bagi memudahkan aktiviti PhIS MTAC Reporting dijalankan. Justeru menjadikan PhIS sebagai platform utama untuk rujukan bagi menjalankan aktiviti MTAC CRP di masa akan datang. Besarlah harapan kami sekiranya permohonan ini dapat dipertimbangkan. | [5 empty] | HKL
7 | 19628894C | I-PhIS050177719S | 2019-02-19 | Klinik Kesihatan Sungai Lalang | Report/Enquiry | Issue Report - Request to filter report for Offline Issue | Encik Amir request to filter report for Offline Issue Reason User want to check back issue offline to facility not using PhIS, easier for user to check thru online. | [5 empty] | Kedah
8 | 19624653C | I-PhIS049843219S | 2019-02-03 | Hospital Sik | Report/Enquiry | Item Movement - Request to add count sheet transaction & created by column | User request to add count sheet transaction and created by column in item movement. User claimed she has perform count sheet but no record appear in item movement. User informed flow of MOF is should appear verification report in item movement even user did not perform any adjustment. User also want to add column created by column for each transaction. | [5 empty] | Kedah
9 | 19631210C | I-PhIS050339419S | 2019-02-26 | Klinik Kesihatan Bandar Baharu | Report/Enquiry | Request to cater issue for data not generated if server down during monthly scheduler process | Based on report 19628257C, user want to proceed request to cater issue for data not generated if server down at facility during monthly scheduler process as per suggested at activity A12. | [5 empty] | Kedah
10 | 19626257C | I-PhIS049969219S | 2019-02-11 | Hospital Gua Musang | Adverse Drug Reaction (ADR) | ADR Reporting - No notification pop up inform order already sent to NPRA | User Ms Hafiza reported after she proceed sent to NPRA no notification pop up.User inquiry order already sent to NPRA or not. | [5 empty] | Kelantan
11 | 19624975C | I-PhIS049871019S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Permintaan untuk Cycle/kitaran kemoterapi | Email from user : Cycle/kitaran kemoterapi tidak dinyatakan pada kertas kerja phis Untuk pemantauan kitaran kemoterapi pesakit. Setiap regimen kemoterapi mempunyai kitaran hari yang berbeza. Data di isi ketika proses | [5 empty] | Kelantan
12 | 19624955C | I-PhIS049870119S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Regimen kemoterapi tidak dinayatakan pada kertas kerja phis | Isu: Regimen kemoterapi tidak dinayatakan pada kertas kerja phis Justifikasi: Untuk pemantauan jenis regimen kemoterapi yang diberikan pesakit Catatan: Bagi memastikan pesakit menerima regimen yang sepatutnya. Data di isi ketika proses transcribing. | [5 empty] | Kelantan
13 | 19624967C | I-PhIS049870519S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Request to add BSA (UNIT M2) | ISU/MASALAH : BSA (UNIT M2) PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI : UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT CATATAN : DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT | [5 empty] | Kelantan
14 | 19624953C | I-PhIS049870419S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - request to use full term of ROA in system | emauil from user : ROA YANG DINYATAKAN DI KERTAS KERJA MENGGUNAKAN SHORTFORM YANG MENGELIRUKAN Dan ia MENGELIRUKAN PENGGUNA, SILA GUNA SHORTFORM YANG STANDARD ATAU TULIS DENGAN PENUH | [5 empty] | Kelantan
15 | 19624983C | I-PhIS049871219S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR : Request To add Height in worksheet | From Email: TINGGI (UNIT CENTIMETRE)PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS. BERTUJUAN UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT Catatan Tujuan: DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT | [5 empty] | Kelantan
16 | 19624957C | I-PhIS049870219S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Memohon meletakkan Day of Infusion pada kertas kerja | Email: Issue number 10 Pengguna memohon meletakkan Day of Infusion pada kertas kerja PhIS. ISU/MASALAH: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS CATATAN: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS | [5 empty] | Kelantan
17 | 19624963C | I-PhIS049870319S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add age in worksheet | Email: Pengguna memohon penambahan column umur di kertas kerja PhIS ISU/MASALAH UMUR PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN CREATININE CLEARANCE (CrCl) CATATAN FORMULA CrCl BERGANTUNG KEPADA UMUR & JANTINA PESAKIT | [5 empty] | Kelantan
18 | 19624934C | I-PhIS049869319S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add gender in worksheet | Email: Issue number 2 Pengguna memohon penambahan jantina di kertas kerja PhIS. ISU/MASALAH JANTINA PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN CREATININE CLEARANCE (CrCl) CATATAN FORMULA CrCl BERBEZA BERGANTUNG KEPADA UMUR & JANTINA PESAKIT | [5 empty] | Kelantan
19 | 19624969C | I-PhIS049870619S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add weight (kilogram unit) in worksheet | Email: Pengguna memohon penambahan column berat dalam kertas kerja PhIS ISU/MASALAH BERAT (UNIT KILOGRAM) PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT CATATAN DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT | [5 empty] | Kelantan
20 | 19624661C | I-PhIS049845219S | 2019-02-03 | Hospital Raja Perempuan Zainab II | Order Management - Web | Medication Order - Request to add popup message if patient is active visit | User request to add popup message if patient has active visit. User claimed this request to avoid user create duplicate visit. User claimed most of the staff not realized for previous visit and most of the visit will be referral. | [5 empty] | Kelantan
21 | 19627003C | I-PhIS050029919S | 2019-02-13 | Klinik Kesihatan Bertam Baru | Outpatient Pharmacy | Drug Label (Insulin) - Request to provide print label for all insulin drug | En Azuan request system to provide print label for all insulin drug. Refer user attachment as reference. Purpose: They currently doing a project innovation and they want it integrate with PhIS and this request already agreed by JKN Kelantan List of Insulin:- A10AD01000P5001b A10AD04000P5002 A10AC01000P5001d A10AB01000P3001b A10AB01000P5001b A10AD01000P5001c A10AB01000P5001c A10AD01000P5001a A10AE05000P5001XX A10AD04000P5002a A10AC01000P5001a A10AE06000P5001 A10AC01000P5001e A10AC01000P5001c A10AB01000P3001a A10AB01000P5001a A10AD01000P3001a A10AD01000P5001d A10AB05000P3001a A10AC01000P5001b A10AD05000P3001XX A10AE04000P5001XX A10AC01000P3001a A10AB04000P5001XX A10AB06000P5001 A10AD04000P5001XX A10AB05000P3001XX A10AB01000P5001d A10AD06925P5001 | [5 empty] | Kelantan
22 | 19629115C | I-PhIS050203319S | 2019-02-19 | Hospital Tumpat | Report/Enquiry | Medication Counselling Registry - Request to add filter by patient visit location | Pn Hasanah request to add filter by patient visit location at screen medication counselling registry. Example patient location: ward. | [5 empty] | Kelantan
23 | 19626292C | I-PhIS049973519S | 2019-02-11 | Hospital Raja Perempuan Zainab II | Ward Pharmacy | Ward Pharmacy (CP1) - Request to add column Patient Diagnosis | User request to add column Patient Diagnosis in CPI Ward Pharmacy | [5 empty] | Kelantan
24 | 19629875C | I-PhIS050253119S | 2019-02-21 | Klinik Kesihatan Jasin | MTAC | Request Enhancement in module MTAC reporting. | Ms Tan suggest in MTAC reporting - User want system allowed user keyin MTAC type as POST. Because she said previously have manual record. So she want manual record to be transfer into this module MTAC Reporting.Even for first time MTAC record in system, user request able to select as post type | [5 empty] | Melaka
25 | 19625695C | I-PhIS049928619S | 2019-02-08 | Pejabat Kesihatan Daerah Jasin | Report/Enquiry | Stock balance by drug non drug - Item inactive still appear | Cik Alia reported Item inactive still appear at Stock balance by drug non drug. User already set status to inactive at drug non drug catalog. Example item : A10BF01000T1001XX M05BA04520T1001XX KPK00045 | [5 empty] | Melaka
26 | 19631218C | I-PhIS050341319S | 2019-02-26 | Klinik Kesihatan Seremban 2 | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - Unable to proceed for reporting | Puan Syarifah Nafisha reported unable to proceed for reporting. User select Process Type : outsource but the outsource facility still offline for TDM (Hospital Tuanku Jaafar) TDM No : TDM0000000005 & TDM0000000006 IC Patient : 491025055083 (Ramachandaran AL Ponnie) User want to cancel this transaction and create new transaction with other process type so user can proceed with TDM reporting. | [5 empty] | Negeri Sembilan
27 | 19624408C | I-PhIS049817519S | 2019-02-01 | Klinik Kesihatan Lenggeng | Report/Enquiry | Stock balance By Item and By drug non Drug - Request to able filter stock balance by date | Mr Eng request to able filter stock balance by date Purpose:- To check total price for medical and surgical item (APPL, LP and contract) in the beginning of the year/month. or better known as stok permulaan | [5 empty] | Negeri Sembilan
28 | 19626560C | I-PhIS049992019S | 2019-02-12 | Hospital Rompin | General Module | Drug Master - Dispense UOM - Request able create quarter & half tablet | Pn Atiqah request able create quarter & half tablet for dispense UOM Drug Code : A10BA02110T1001XX Metformin HCl 500 mg Tablet For dose : 250mg - need to give patient half tablet Pharmacy will provide to ward, the medication already cut into half or quarter. Dispense UOM Needed : 0.5 Tablet 0.25 Tablet | [5 empty] | Pahang
29 | 19626871C | I-PhIS050029319S | 2019-02-13 | Pejabat Kesihatan Daerah Temerloh | IWP | Request Order Status- Request PO still appear after payment complete | Pn Wahida request the PO still appear after payment complete Current Situation Request Order Status - PO will disappear after payment complete User request the PO still appear after payment complete Reason Pn Wahida want to monitor purchase order for facility under PKD. | [5 empty] | Pahang
30 | 19629879C | I-PhIS050251219S | 2019-02-21 | Klinik Kesihatan Bandar Tun Abdul Razak | Pharmacy Inventory | Receive item (inter facility): Request to allow partial receiving | Encik Azmi request to allow partial receiving in receive item (inter facility) as per receiving item from supplier. Current situation: Sometimes issuer unit issue all item in system but only issue partial in physically. (Example: Indent 10 items, only receive 5 items physical due to indenter request urgent. Balance will be send on next day) Request: Due to urgent, user will receive the urgent item first and pending the other item that issuer already give fully supply in PhIS. User hope consideration for this situation. | [5 empty] | Pahang
31 | 19626176C | I-PhIS049965519S | 2019-02-11 | Klinik Kesihatan Bandar Tun Abdul Razak | Pharmacy Inventory | Receive From Supplier (LOU item) - Request able to receive SKU | Encik Azmi request able to receive in SKU. Current Situation User return loose expired item to supplier. When receiving unable to make selection to receive by SKU. | [5 empty] | Pahang
32 | 19629506C | I-PhIS050230219S | 2019-02-20 | Klinik Kesihatan Pantai Remis | MTAC | MTAC Order: Request allow to edit appointment type after save | Puan Noratikah request allow to edit appointment type after save MTAC Order. Current situation: MTAC order able to save without put appointment type due to it's not mandatory. | [5 empty] | Perak
33 | 19631640C | I-PhIS050377119S | 2019-02-27 | Klinik Kesihatan Jelapang | MTAC | Request to simplify DFIT chart (understanding score) for medication counseling and MTAC reporting | Based on previous request report 18343276C. User not agreed the request being rejected. User insist to request simplify DFIT chart setting. Its ridiculous for pharmacist to tick YES/NO for individual drug since the step/flow is troublesome. Suggestion: To change the current DFIT chart setting. Instead of allowing Pharmacist to tick (Yes/No) on each individual drug on Dose, frequency, indication, time of administration. Suggest the system to tick on all drugs as Yes on Dose, frequency, indication, time of administration, so that pharmacist only tick NO on wrong dose, frequency, indication or time of administration. Refer user attachment for reference. Reason: To shorten documentation time on each individual drug, pharmacist only tick on drug (Dose, frequency, indication or time of adminstration) that patient taking wrongly. | [5 empty] | Perak
34 | 19631702C | I-PhIS050381919S | 2019-02-27 | Klinik Kesihatan Pantai Remis | Order Management - Web | Medication Order - Pharmacist Notes - Request to add Counselled/Report By into this column | Cik Anisah request to add Counselled/Report By into this column. User want to know who is create that transaction. | [5 empty] | Perak
35 | 19626485C | I-PhIS049989719S | 2019-02-12 | Jabatan Kesihatan Negeri Perak | Report/Enquiry | Stock Balance By Drug Non Drug - Request filter by date | Encik Ashrul request able to filter by date. user want to check stock balance on certain date. | [5 empty] | Perak
36 | 19628896C | I-PhIS050177919S | 2019-02-19 | Klinik Kesihatan Jalan Perak | Adverse Drug Reaction (ADR) | ADR Report Listing: Request to show total ADR report number | Miss Wong request to show total ADR report number. Current situation: Total number report based on active ingredient drug. Problem: One ADR number could have two or three suspected drug/active ingredient. Total of ADR number might be less than total number report based on active ingredient drug. Request: To show total ADR report number | [5 empty] | Pulau Pinang
37 | 19627709C | I-PhIS050083319S | 2019-02-14 | Klinik Kesihatan Seberang Jaya | General Module | External Notification - Request system only shows data that still not registered | User request system only shows data still not registered in external notification (Online SPUB R1 Request Received). Currently, system shows the value that enter in external notification but all the value still appear even user has click registered. User claimed she don't want to confused with the value. Untuk home page, untuk online SPUB R1 request received boleh tak once kita register patients online SPUB data tersebut tidak akan ditunjukkan lagi di home page notification itu? | [5 empty] | Pulau Pinang
38 | 19625429C | I-PhIS049907619S | 2019-02-07 | Hospital Pulau Pinang | Manufacturing - CDR | CDR Label-Kecilkan Size label CDR | Saiz label dicetak terlalu besar untuk sediaan bolus dan intrathecal. Label yang disediakan agak besar untuk dilekatkan pada syringe. cadangan 7cm x 5 cm - bolus 7cm x 4 cm- inthrathecal | [5 empty] | Pulau Pinang
39 | 19631269C | I-PhIS050343819S | 2019-02-26 | Hospital Pulau Pinang | MTAC | MTAC Reporting - Inhaler Technique Understanding - Request to add new inhaler | Ms Lee request to add new inhaler at Inhaler Technique Understanding. Type Of MTAC: Respiratory New Inhaler to add:- BREEZEHALER RESPIMAT ELLIPTA Purpose: new inhaler is available at facility but not provided in PhIS | [5 empty] | Pulau Pinang
40 | 19631897C | I-PhIS050396319S | 2019-02-28 | Hospital Bukit Mertajam | MTAC | MTAC Reporting - Request to provide cancel function after confirm | Ms Tan request to provide cancel function after confirm the transaction. Purpose:- Usually after confirm, they not realize regarding the 1st visit as follow up while it should be as new. Due to this, the report for new patient will not appear as 100%. | [5 empty] | Pulau Pinang
41 | 19631163C | I-PhIS050337419S | 2019-02-26 | Hospital Pulau Pinang | MTAC | MTAC Reporting- Add result Respiratory | User request in MTAC Reporting for Respiratory type user request to add for keyin result lung function test and laboratory monitory. | [5 empty] | Pulau Pinang
42 | 19627707C | I-PhIS050083219S | 2019-02-14 | Klinik Kesihatan Seberang Jaya | Report/Enquiry | Drug Utilisation - Request to add new column | User request to add new column for IC number and patient age in the list of report. Currently, both of the criteria not appear in the list of drug utilisation report. Untuk report, under pharmacy--> outpatient--> drug utilisation, bolehkah masukkan data umur pesakit dan no. K/P? Data ini adalah samgat penting dalam analisa data khasnya antibiotik. | [5 empty] | Pulau Pinang
43 | 19630909C | I-PhIS050316219S | 2019-02-25 | Klinik Kesihatan Tandek | Pharmacy Inventory | Indent(Inter Facility): Request to add column for supply approval quantity | Mr Goh request to add new column for supply approval quantity in indent(inter facility) - Indent List. New column between approved quantity (SKU) and Back Order. This column for user can trace back the item supplier did supply or not. | [5 empty] | Sabah
44 | 19627699C | I-PhIS050082819S | 2019-02-14 | Hospital Tawau | Pharmacy Inventory | Purchase Order (LP/Contract): Request allow proceed with eP approve even past delivery due date | Miss Ting request to allow proceed with eP approve even past delivery due date. Purchase Order (LP/Contract) also have penalty need to be calculate. Reason: User need to eP-approve the following LPO to proceed stock receiving (stock just received from supplier on 13 Feb 2019, which has exceeded the delivery due date on 30 Jan 2019) | [5 empty] | Sabah
45 | 19626456C | I-PhIS049988719S | 2019-02-12 | Hospital Tawau | Ward Pharmacy | Ward Pharmacy (CP2) - Request allow to enter CP2 after patient discharge | User request allow to enter CP2 within 5 days after patient discharge. Scenario: Patient already discharge at 10.00pm (11/2/2019) but user still not enter CP2 for patient. Today (12/2/2019) user unable to search patient at CP2 screen. User request allow to enter CP2 within 5 days after patient discharge. | [5 empty] | Sabah
46 | 19624370C | I-PhIS049811219S | 2019-02-01 | Hospital Lundu | Clinical Pharmacokinetic Services (CPS) & TDM | TDM (Outsource) - External facility unable to received TDM - Add Cancel function | Ms Lim reported that she had sent TDM (outsource) to HUS on 29/1/2019, but confirmed by HUS they not received that order. After that, on 31/1/2019 user at Hospital Lundu proceed to create new TDM outsource to HUS for same patient. Confirmed by HUS, they successfully received new TDM outsource. User request to cancel previous TDM outsource (TDM0000000089) due she already proceed with new TDM (TDM0000000090). TDM Order: TDM0000000089 (unsuccessful) - date 29/1/2019 TDM0000000090 (successful) - date 31/1/2019 MRN: HLUN00095879 Update proceed as request ticket. User request to add Cancel function for TDM Outsource after TDM is sent out to other facility. | [5 empty] | Sarawak
47 | 19624480C | I-PhIS049825319S | 2019-02-01 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | 4.Report Extemporaneous Registry Module comparison between phis and BI Tools not tally | User reported in Bi Tools Report figure not tally with phis report Example generated report prescription dispense from Oct until Nov 2018 From Email: Percanggahan Data dalam Bi tools :PF 6.6(a)_AKTIVITI SEDIAAN BUKAN STERIL Oct 7(30) dan Nov 4(6) Phis :Extemporaneous Registry Report show Oct 6(20) and Nov 11(29) | [5 empty] | Sarawak
48 | 19628678C | I-PhIS050157519S | 2019-02-18 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | BI Tools (PF 6.7) - Report not tally with TDM Registry | Email: Berikut ada senarai data yang bercanggah pada bulan Dis 2018. Dilampirkan laporan yang berkenaan. Sila rujuk lampiran. PF 6.7_AKTIVITI FARMAKOKINETIK KLINIKAL PERMONITORAN UBAT TERAPEUTIK and TDM Registry BI Tools: 0 PhIS: 8 | [5 empty] | Sarawak
49 | 19628702C | I-PhIS050159519S | 2019-02-18 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | BI Tools (PF6.6(a)) - Report no tally with Extemporaneous Registry | Email: Berikut ada senarai data yang bercanggah pada bulan Dis 2018. Dilampirkan laporan yang berkenaan. Sila rujuk lampiran. PF 6.6(a)_AKTIVITI SEDIAAN BUKAN STERIL and Extemporaneous Registry BI Tools: 2 PhIS: 6 | [5 empty] | Sarawak
50 | 19626894C | I-PhIS050017519S | 2019-02-13 | Hospital Sibu | General Module | Request unit follow login location | Mr Francis request unit follow login location that he select while login phis. He informed it will trouble if every time want to login/view other patient by always change the unit. Already inform user to create another account but user inform every staff available works at different location on weekend/night shift. So that he request if the unit can follow based on location user select while login system. Update: As i checked on transcribing page, i can transcribe patient's profile under different discipline thru record record Prescription My concern is... Dangerous Drugs required quantity of physical , Tally card(prescription book), and PHIS to be tally every week. If my profile is LOCKED in Outpatient Pharmacy, i couldn't trace the item movement for in patient/ Pharmacy DD account. For my concern, i only can select 1 store unit. If my request is approved, the pharmacy store unit can be change automatically when i select its location at login page. Sorry for the misunderstanding. To Summarize my request again, Request: Store / Substore unit can be change automatically when selecting location in login page. Justification: To allow pharmacist and Provasional Registered Pharmacist (PRP) check the quantity of stock (DANGEROUS DRUG) from various location (IPD DD/ OPD DD/ Store DD) without changing user profile everytime. | [5 empty] | Sarawak
51 | 19626247C | I-PhIS049968319S | 2019-02-11 | Hospital Sarikei | Manufacturing - Extemporaneous | Request Enhancement in Report/Enquiry Formula - Extemp | Mr Han request to add Extemporaneous Formula like Galenical formulation. He want to print and keep because if phis down he can refer and make work order to patient. | [5 empty] | Sarawak
52 | 19627036C | I-PhIS050031219S | 2019-02-13 | Hospital Sarikei | Order Management - Web | SPUB patient list - Unable to add new SPUB - Dispensing Location IP | User Mr Lim reported user unable to add new SPUB due when user search no record for reported MRN.User inform he dispense for 2 month but it appear fully dispense at clinical summary. Location : Inpatient pharmacy MRN : HSRK00093456 | [5 empty] | Sarawak
53 | 19631255C | I-PhIS050343319S | 2019-02-26 | Klinik Kesihatan Kalumpang | Data Mining - PhARM | PF6.6b - Screen sturcture not similar with PF6.6b from MOH | En Omar reported the screen structure of PF6.6b not similar as PF6.6b from MOH. 1. Merujuk kepada aduan di atas, saya ingin tahu kenapakah format lapuran yang saya perlu buat secara manual tidak sama dengan yang di dalam PhIS Kenapalah perkara ini boleh berlaku ? Pihak yang empunya modul ini tidak dapatkah format baru lapuran PF 6.6(b) ini ? 2. Bilakah pihak PhIS akan memaklumkan kepada fasiliti bahawa tidak perlu lagi membuat lapuran manual kerana data tersebut telah ada di dalam PhIS dan maklumat ini bole di 'akss' oleh pegawai yang berkenaan pengumpulan data ini Justeru itu saya masih perlu merekod secara manual ungtuk repot ini dan sia sialah kemudahan ini yang ada di dalam PhIS. | [5 empty] | Selangor
54 | 19624454C | I-PhIS049823119S | 2019-02-01 | Hospital Kuala Kubu Bharu | Order Management - Web | Medication Order- Add column for Reaction Details in Allergy History | Ms Suraya request enhancement at Medication Order screen at Allergy History only show 5 column when open such as Allergen,Allergen type, Severity,Status and Identification Date. She want add column Reaction Details for easy to read. Please refer attachment given for more detail to understanding. | [5 empty] | Selangor
55 | 19626797C | I-PhIS050009219S | 2019-02-12 | Klinik Kesihatan Kalumpang | Order Management - Web | Request to minimize the transcribe stage | Berkenaan perkara di atas, saya ingin bertanya tentang langkah: 1. Menanda 'Tik' untuk 'Patient Arrived' Salah satu tujuan membuka skrin ini ialah untuk transkrib ubat pesakit. Membukanya secara sendiri menandakan pesakit telah tiba, mengapa perlu langkah menanda 'tik' pada 'patient arrive'? Masa 'waiting time' sendiri boleh bermula apabila 'single stage dispensing' ini dibuka. Jika modul ini dibuka bukan dengan tujuan transkrib, sistem sendiri boleh diprogram untuk membatalkan masa menunggu itu sendiri. Ini akan menjimatkan masa dan langkah dapat dipendekkan. 2. Langkah memilih 'allocate', label, dispense' Sistem sendiri akan mengira secara 'auto' berapakah baki hari untuk ubat dibekalkan . ini ditunjukkan pada skrin pada 'supply duration'. Jika modul ini dibuka dengan tujuan pesakit telah datang maka dengan sendiri jumlah hari akan diikuti. Kecuali lah jika 'supply duration' itu diubah, maka untuk pengesahan boleh ditanya untuk memilih langkah 'allocate'. Bukankah satu langkah dapat dipendekkan ? Kedua - dua faktor ini menjadikan sistem program ini cerdik, kerana tujuannya telah nyata. Ini yang saya dapat lihat. Tidak tahulah saya jika ia mempunyai tujuan yang lain. | [5 empty] | Selangor
56 | 19626309C | I-PhIS049975119S | 2019-02-11 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Dispensing - Request to pop up notification when proceed dispense for Insulin | User request pop up notification when proceed dispense for drug under insulin.Example : Are you sure want to proceed to dispense due expired item is 6 week or 42 days?' Example item : Insulin regular/isophane (Mixtard-30) 100 IU/mL Penfill | [5 empty] | Selangor
57 | 19626553C | I-PhIS049991819S | 2019-02-12 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Medication order - request system will decrease if patient came late for next appointment. | User Mr Omar request system will decrease if patient came late for next appointment.User request duration been deduct for day patient late from appointment date. Current : when patient came late 7 days from the appointment, system still proceed to dispense for 30 days. Request : Patient came 7 days late from appoinment, duration been deduct days and patient will receive for duration only for 23 days. | [5 empty] | Selangor
58 | 19626303C | I-PhIS049973919S | 2019-02-11 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Transcribe order - Request duration been auto calculate after change clinic TCA and supply duration | User Mr Omar inquiry : 1. inquiry able to change date for supply duration 2.Inquiry able to change TCA date or not and order detail will change or not 3.Inquiry able to search patient for add manual in system 4.Patient came late from date for supply, will decrease or depand on duration for partial supply. Example MRN : 83102 User Mr Omar request duration been auto calculate after he change clinic TCA and supply duration for partial supply | [5 empty] | Selangor
59 | 19629594C | I-PhIS050233719S | 2019-02-20 | Klinik Kesihatan Kalumpang | Report/Enquiry | Drug Utilisation - Request to add new column for IC Patient | Encik Omar request to add new column (IC Patinet) in Drug Utilization report. They not use MRN number in practice and doctor and nurse not using PhIS for pharmacy based. | [5 empty] | Selangor
60 | 19624895C | I-PhIS049863119S | 2019-02-04 | Hospital Kajang | Report/Enquiry | MTAC Registry - Request to enhancement | User Ms Ani request to add column for numbering or total report when she print. Current : User need to calculate manual for hardcopy. | [5 empty] | Selangor
61 | 19630234C | I-PhIS050276019S | 2019-02-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Return to Supplying Unit - Request Return Type remark as mandatory | En Omar request to remark Return Type as mandatory. Since in current version not remark as Mandatory, if user did not select Return Type , user cannot proceed to add item. | [5 empty] | Selangor
62 | 19628912C | I-PhIS050179319S | 2019-02-19 | Hospital Setiu | Manufacturing - Extemporaneous | Extemporaneous - Worksheet - Request to add batch no. column | User request to add batch no. column at screen worksheet extemporaneous. User request system auto generate that batch no. User informed currently only appear batch no. for material item. But now user request to add batch no. for the whole preparation. | [5 empty] | Terengganu
63 | 19625632C | I-PhIS049924019S | 2019-02-08 | Pejabat Kesihatan Putrajaya | Report/Enquiry | Stock Balance By Drug/Non Drug - Request to remove drug from list after inactive | Request to remove drug from list of stock balance by drug/non drug after user inactive the item at drug/non drug catalogue. Purpose:- Everytime when user want to generate from from stock balance by drug/non drug screen, she unable to direct print the report. She need to export to excel first to filter the required item and remove the unwanted item. | [5 empty] | W. Persekutuan

## HQ(BPF)
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19628653C | I-PhIS050153219S | 2019-02-18 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | PF Report - To exclude Methadone dispensing in PF report | Methadone dispensing record should be excluded from PF reports (PF5.1, PF 5.4, PF 6.3 and others) that have dispensing records. Current practice also ( manually) , for methadone dispensing activities the reporting is done in specific PF 5.7 a-c report only.
2 | 19632177C | I-PhIS050417319S | 2019-02-28 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | BI TOOLS-Request to provide report Drug Allergy Card Registry in BI Tools | Receive email from Ms Norazimah : Dear Helpdesk, Kindly please provide report Drug Allergy Card Registry in PhIS to made available in BI Tools.
3 | 19624340C | I-PhIS049809319S | 2019-02-01 | Bahagian Perkhidmatan Farmasi (BPF) | Special Drug Request | request to add filtering Submission date at both screen Special Drug Request and report Permohonan | received email from user : I would like to request to add filtering Submission date at both screen Special Drug Request and report Permohonan KPK. When can i have it? kindly refer file upload
4
5
6
7
8
9
10
11
12

## Johor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10
11
12

## Kedah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19628894C | I-PhIS050177719S | 2019-02-19 | Klinik Kesihatan Sungai Lalang | Report/Enquiry | Issue Report - Request to filter report for Offline Issue | Encik Amir request to filter report for Offline Issue Reason User want to check back issue offline to facility not using PhIS, easier for user to check thru online.
2 | 19624653C | I-PhIS049843219S | 2019-02-03 | Hospital Sik | Report/Enquiry | Item Movement - Request to add count sheet transaction & created by column | User request to add count sheet transaction and created by column in item movement. User claimed she has perform count sheet but no record appear in item movement. User informed flow of MOF is should appear verification report in item movement even user did not perform any adjustment. User also want to add column created by column for each transaction.
3 | 19631210C | I-PhIS050339419S | 2019-02-26 | Klinik Kesihatan Bandar Baharu | Report/Enquiry | Request to cater issue for data not generated if server down during monthly scheduler process | Based on report 19628257C, user want to proceed request to cater issue for data not generated if server down at facility during monthly scheduler process as per suggested at activity A12.
4
5
6
7
8
9
10

## Kelantan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19626257C | I-PhIS049969219S | 2019-02-11 | Hospital Gua Musang | Adverse Drug Reaction (ADR) | ADR Reporting - No notification pop up inform order already sent to NPRA | User Ms Hafiza reported after she proceed sent to NPRA no notification pop up.User inquiry order already sent to NPRA or not.
2 | 19624975C | I-PhIS049871019S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Permintaan untuk Cycle/kitaran kemoterapi | Email from user : Cycle/kitaran kemoterapi tidak dinyatakan pada kertas kerja phis Untuk pemantauan kitaran kemoterapi pesakit. Setiap regimen kemoterapi mempunyai kitaran hari yang berbeza. Data di isi ketika proses
3 | 19624955C | I-PhIS049870119S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Regimen kemoterapi tidak dinayatakan pada kertas kerja phis | Isu: Regimen kemoterapi tidak dinayatakan pada kertas kerja phis Justifikasi: Untuk pemantauan jenis regimen kemoterapi yang diberikan pesakit Catatan: Bagi memastikan pesakit menerima regimen yang sepatutnya. Data di isi ketika proses transcribing.
4 | 19624967C | I-PhIS049870519S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - Request to add BSA (UNIT M2) | ISU/MASALAH : BSA (UNIT M2) PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI : UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT CATATAN : DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT
5 | 19624953C | I-PhIS049870419S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR - request to use full term of ROA in system | emauil from user : ROA YANG DINYATAKAN DI KERTAS KERJA MENGGUNAKAN SHORTFORM YANG MENGELIRUKAN Dan ia MENGELIRUKAN PENGGUNA, SILA GUNA SHORTFORM YANG STANDARD ATAU TULIS DENGAN PENUH
6 | 19624983C | I-PhIS049871219S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR : Request To add Height in worksheet | From Email: TINGGI (UNIT CENTIMETRE)PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS. BERTUJUAN UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT Catatan Tujuan: DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT
7 | 19624957C | I-PhIS049870219S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Memohon meletakkan Day of Infusion pada kertas kerja | Email: Issue number 10 Pengguna memohon meletakkan Day of Infusion pada kertas kerja PhIS. ISU/MASALAH: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS CATATAN: DAY OF INFUSION TIDAK DINYATAKAN PADA KERTAS KERJA PHIS
8 | 19624963C | I-PhIS049870319S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add age in worksheet | Email: Pengguna memohon penambahan column umur di kertas kerja PhIS ISU/MASALAH UMUR PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN CREATININE CLEARANCE (CrCl) CATATAN FORMULA CrCl BERGANTUNG KEPADA UMUR & JANTINA PESAKIT
9 | 19624934C | I-PhIS049869319S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add gender in worksheet | Email: Issue number 2 Pengguna memohon penambahan jantina di kertas kerja PhIS. ISU/MASALAH JANTINA PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN CREATININE CLEARANCE (CrCl) CATATAN FORMULA CrCl BERBEZA BERGANTUNG KEPADA UMUR & JANTINA PESAKIT
10 | 19624969C | I-PhIS049870619S | 2019-02-04 | Hospital Raja Perempuan Zainab II | Manufacturing - CDR | CDR: Request to add weight (kilogram unit) in worksheet | Email: Pengguna memohon penambahan column berat dalam kertas kerja PhIS ISU/MASALAH BERAT (UNIT KILOGRAM) PESAKIT TIDAK DINYATAKAN PADA KERTAS KERJA PHIS JUSTIFIKASI UNTUK PROSES COUNTERCHECKING KERTAS KERJA TERUTAMA BAGI PENGIRAAN DOS UBAT CATATAN DOS UBAT BERGANTUNG KEPADA BERAT, TINGGI & BSA PESAKIT
11 | 19624661C | I-PhIS049845219S | 2019-02-03 | Hospital Raja Perempuan Zainab II | Order Management - Web | Medication Order - Request to add popup message if patient is active visit | User request to add popup message if patient has active visit. User claimed this request to avoid user create duplicate visit. User claimed most of the staff not realized for previous visit and most of the visit will be referral.
12 | 19627003C | I-PhIS050029919S | 2019-02-13 | Klinik Kesihatan Bertam Baru | Outpatient Pharmacy | Drug Label (Insulin) - Request to provide print label for all insulin drug | En Azuan request system to provide print label for all insulin drug. Refer user attachment as reference. Purpose: They currently doing a project innovation and they want it integrate with PhIS and this request already agreed by JKN Kelantan List of Insulin:- A10AD01000P5001b A10AD04000P5002 A10AC01000P5001d A10AB01000P3001b A10AB01000P5001b A10AD01000P5001c A10AB01000P5001c A10AD01000P5001a A10AE05000P5001XX A10AD04000P5002a A10AC01000P5001a A10AE06000P5001 A10AC01000P5001e A10AC01000P5001c A10AB01000P3001a A10AB01000P5001a A10AD01000P3001a A10AD01000P5001d A10AB05000P3001a A10AC01000P5001b A10AD05000P3001XX A10AE04000P5001XX A10AC01000P3001a A10AB04000P5001XX A10AB06000P5001 A10AD04000P5001XX A10AB05000P3001XX A10AB01000P5001d A10AD06925P5001
13 | 19629115C | I-PhIS050203319S | 2019-02-19 | Hospital Tumpat | Report/Enquiry | Medication Counselling Registry - Request to add filter by patient visit location | Pn Hasanah request to add filter by patient visit location at screen medication counselling registry. Example patient location: ward.
14 | 19626292C | I-PhIS049973519S | 2019-02-11 | Hospital Raja Perempuan Zainab II | Ward Pharmacy | Ward Pharmacy (CP1) - Request to add column Patient Diagnosis | User request to add column Patient Diagnosis in CPI Ward Pharmacy
15
16
17
18
19
20

## Melaka
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19629875C | I-PhIS050253119S | 2019-02-21 | Klinik Kesihatan Jasin | MTAC | Request Enhancement in module MTAC reporting. | Ms Tan suggest in MTAC reporting - User want system allowed user keyin MTAC type as POST. Because she said previously have manual record. So she want manual record to be transfer into this module MTAC Reporting.Even for first time MTAC record in system, user request able to select as post type
2 | 19625695C | I-PhIS049928619S | 2019-02-08 | Pejabat Kesihatan Daerah Jasin | Report/Enquiry | Stock balance by drug non drug - Item inactive still appear | Cik Alia reported Item inactive still appear at Stock balance by drug non drug. User already set status to inactive at drug non drug catalog. Example item : A10BF01000T1001XX M05BA04520T1001XX KPK00045
3
4
5
6
7
8
9
10
11
12

## N_Sembilan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19631218C | I-PhIS050341319S | 2019-02-26 | Klinik Kesihatan Seremban 2 | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - Unable to proceed for reporting | Puan Syarifah Nafisha reported unable to proceed for reporting. User select Process Type : outsource but the outsource facility still offline for TDM (Hospital Tuanku Jaafar) TDM No : TDM0000000005 & TDM0000000006 IC Patient : 491025055083 (Ramachandaran AL Ponnie) User want to cancel this transaction and create new transaction with other process type so user can proceed with TDM reporting.
2 | 19624408C | I-PhIS049817519S | 2019-02-01 | Klinik Kesihatan Lenggeng | Report/Enquiry | Stock balance By Item and By drug non Drug - Request to able filter stock balance by date | Mr Eng request to able filter stock balance by date Purpose:- To check total price for medical and surgical item (APPL, LP and contract) in the beginning of the year/month. or better known as stok permulaan
3
4
5
6
7
8
9

## Pahang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19626560C | I-PhIS049992019S | 2019-02-12 | Hospital Rompin | General Module | Drug Master - Dispense UOM - Request able create quarter & half tablet | Pn Atiqah request able create quarter & half tablet for dispense UOM Drug Code : A10BA02110T1001XX Metformin HCl 500 mg Tablet For dose : 250mg - need to give patient half tablet Pharmacy will provide to ward, the medication already cut into half or quarter. Dispense UOM Needed : 0.5 Tablet 0.25 Tablet
2 | 19626871C | I-PhIS050029319S | 2019-02-13 | Pejabat Kesihatan Daerah Temerloh | IWP | Request Order Status- Request PO still appear after payment complete | Pn Wahida request the PO still appear after payment complete Current Situation Request Order Status - PO will disappear after payment complete User request the PO still appear after payment complete Reason Pn Wahida want to monitor purchase order for facility under PKD.
3 | 19629879C | I-PhIS050251219S | 2019-02-21 | Klinik Kesihatan Bandar Tun Abdul Razak | Pharmacy Inventory | Receive item (inter facility): Request to allow partial receiving | Encik Azmi request to allow partial receiving in receive item (inter facility) as per receiving item from supplier. Current situation: Sometimes issuer unit issue all item in system but only issue partial in physically. (Example: Indent 10 items, only receive 5 items physical due to indenter request urgent. Balance will be send on next day) Request: Due to urgent, user will receive the urgent item first and pending the other item that issuer already give fully supply in PhIS. User hope consideration for this situation.
4 | 19626176C | I-PhIS049965519S | 2019-02-11 | Klinik Kesihatan Bandar Tun Abdul Razak | Pharmacy Inventory | Receive From Supplier (LOU item) - Request able to receive SKU | Encik Azmi request able to receive in SKU. Current Situation User return loose expired item to supplier. When receiving unable to make selection to receive by SKU.
5
6
7
8
9
10
11
12

## Perak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19629506C | I-PhIS050230219S | 2019-02-20 | Klinik Kesihatan Pantai Remis | MTAC | MTAC Order: Request allow to edit appointment type after save | Puan Noratikah request allow to edit appointment type after save MTAC Order. Current situation: MTAC order able to save without put appointment type due to it's not mandatory.
2 | 19631640C | I-PhIS050377119S | 2019-02-27 | Klinik Kesihatan Jelapang | MTAC | Request to simplify DFIT chart (understanding score) for medication counseling and MTAC reporting | Based on previous request report 18343276C. User not agreed the request being rejected. User insist to request simplify DFIT chart setting. Its ridiculous for pharmacist to tick YES/NO for individual drug since the step/flow is troublesome. Suggestion: To change the current DFIT chart setting. Instead of allowing Pharmacist to tick (Yes/No) on each individual drug on Dose, frequency, indication, time of administration. Suggest the system to tick on all drugs as Yes on Dose, frequency, indication, time of administration, so that pharmacist only tick NO on wrong dose, frequency, indication or time of administration. Refer user attachment for reference. Reason: To shorten documentation time on each individual drug, pharmacist only tick on drug (Dose, frequency, indication or time of adminstration) that patient taking wrongly.
3 | 19631702C | I-PhIS050381919S | 2019-02-27 | Klinik Kesihatan Pantai Remis | Order Management - Web | Medication Order - Pharmacist Notes - Request to add Counselled/Report By into this column | Cik Anisah request to add Counselled/Report By into this column. User want to know who is create that transaction.
4 | 19626485C | I-PhIS049989719S | 2019-02-12 | Jabatan Kesihatan Negeri Perak | Report/Enquiry | Stock Balance By Drug Non Drug - Request filter by date | Encik Ashrul request able to filter by date. user want to check stock balance on certain date.
5
6
7
8
9
10
11
12

## P.Pinang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19628896C | I-PhIS050177919S | 2019-02-19 | Klinik Kesihatan Jalan Perak | Adverse Drug Reaction (ADR) | ADR Report Listing: Request to show total ADR report number | Miss Wong request to show total ADR report number. Current situation: Total number report based on active ingredient drug. Problem: One ADR number could have two or three suspected drug/active ingredient. Total of ADR number might be less than total number report based on active ingredient drug. Request: To show total ADR report number
2 | 19627709C | I-PhIS050083319S | 2019-02-14 | Klinik Kesihatan Seberang Jaya | General Module | External Notification - Request system only shows data that still not registered | User request system only shows data still not registered in external notification (Online SPUB R1 Request Received). Currently, system shows the value that enter in external notification but all the value still appear even user has click registered. User claimed she don't want to confused with the value. Untuk home page, untuk online SPUB R1 request received boleh tak once kita register patients online SPUB data tersebut tidak akan ditunjukkan lagi di home page notification itu?
3 | 19625429C | I-PhIS049907619S | 2019-02-07 | Hospital Pulau Pinang | Manufacturing - CDR | CDR Label-Kecilkan Size label CDR | Saiz label dicetak terlalu besar untuk sediaan bolus dan intrathecal. Label yang disediakan agak besar untuk dilekatkan pada syringe. cadangan 7cm x 5 cm - bolus 7cm x 4 cm- inthrathecal
4 | 19631269C | I-PhIS050343819S | 2019-02-26 | Hospital Pulau Pinang | MTAC | MTAC Reporting - Inhaler Technique Understanding - Request to add new inhaler | Ms Lee request to add new inhaler at Inhaler Technique Understanding. Type Of MTAC: Respiratory New Inhaler to add:- BREEZEHALER RESPIMAT ELLIPTA Purpose: new inhaler is available at facility but not provided in PhIS
5 | 19631897C | I-PhIS050396319S | 2019-02-28 | Hospital Bukit Mertajam | MTAC | MTAC Reporting - Request to provide cancel function after confirm | Ms Tan request to provide cancel function after confirm the transaction. Purpose:- Usually after confirm, they not realize regarding the 1st visit as follow up while it should be as new. Due to this, the report for new patient will not appear as 100%.
6 | 19631163C | I-PhIS050337419S | 2019-02-26 | Hospital Pulau Pinang | MTAC | MTAC Reporting- Add result Respiratory | User request in MTAC Reporting for Respiratory type user request to add for keyin result lung function test and laboratory monitory.
7 | 19627707C | I-PhIS050083219S | 2019-02-14 | Klinik Kesihatan Seberang Jaya | Report/Enquiry | Drug Utilisation - Request to add new column | User request to add new column for IC number and patient age in the list of report. Currently, both of the criteria not appear in the list of drug utilisation report. Untuk report, under pharmacy--> outpatient--> drug utilisation, bolehkah masukkan data umur pesakit dan no. K/P? Data ini adalah samgat penting dalam analisa data khasnya antibiotik.
8
9
10
11
12
13
14
15

## Perlis
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10

## Sabah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19630909C | I-PhIS050316219S | 2019-02-25 | Klinik Kesihatan Tandek | Pharmacy Inventory | Indent(Inter Facility): Request to add column for supply approval quantity | Mr Goh request to add new column for supply approval quantity in indent(inter facility) - Indent List. New column between approved quantity (SKU) and Back Order. This column for user can trace back the item supplier did supply or not.
2 | 19627699C | I-PhIS050082819S | 2019-02-14 | Hospital Tawau | Pharmacy Inventory | Purchase Order (LP/Contract): Request allow proceed with eP approve even past delivery due date | Miss Ting request to allow proceed with eP approve even past delivery due date. Purchase Order (LP/Contract) also have penalty need to be calculate. Reason: User need to eP-approve the following LPO to proceed stock receiving (stock just received from supplier on 13 Feb 2019, which has exceeded the delivery due date on 30 Jan 2019)
3 | 19626456C | I-PhIS049988719S | 2019-02-12 | Hospital Tawau | Ward Pharmacy | Ward Pharmacy (CP2) - Request allow to enter CP2 after patient discharge | User request allow to enter CP2 within 5 days after patient discharge. Scenario: Patient already discharge at 10.00pm (11/2/2019) but user still not enter CP2 for patient. Today (12/2/2019) user unable to search patient at CP2 screen. User request allow to enter CP2 within 5 days after patient discharge.
4
5
6
7
8
9
10
11
12

## Sarawak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19624370C | I-PhIS049811219S | 2019-02-01 | Hospital Lundu | Clinical Pharmacokinetic Services (CPS) & TDM | TDM (Outsource) - External facility unable to received TDM - Add Cancel function | Ms Lim reported that she had sent TDM (outsource) to HUS on 29/1/2019, but confirmed by HUS they not received that order. After that, on 31/1/2019 user at Hospital Lundu proceed to create new TDM outsource to HUS for same patient. Confirmed by HUS, they successfully received new TDM outsource. User request to cancel previous TDM outsource (TDM0000000089) due she already proceed with new TDM (TDM0000000090). TDM Order: TDM0000000089 (unsuccessful) - date 29/1/2019 TDM0000000090 (successful) - date 31/1/2019 MRN: HLUN00095879 Update proceed as request ticket. User request to add Cancel function for TDM Outsource after TDM is sent out to other facility.
2 | 19624480C | I-PhIS049825319S | 2019-02-01 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | 4.Report Extemporaneous Registry Module comparison between phis and BI Tools not tally | User reported in Bi Tools Report figure not tally with phis report Example generated report prescription dispense from Oct until Nov 2018 From Email: Percanggahan Data dalam Bi tools :PF 6.6(a)_AKTIVITI SEDIAAN BUKAN STERIL Oct 7(30) dan Nov 4(6) Phis :Extemporaneous Registry Report show Oct 6(20) and Nov 11(29)
3 | 19628678C | I-PhIS050157519S | 2019-02-18 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | BI Tools (PF 6.7) - Report not tally with TDM Registry | Email: Berikut ada senarai data yang bercanggah pada bulan Dis 2018. Dilampirkan laporan yang berkenaan. Sila rujuk lampiran. PF 6.7_AKTIVITI FARMAKOKINETIK KLINIKAL PERMONITORAN UBAT TERAPEUTIK and TDM Registry BI Tools: 0 PhIS: 8
4 | 19628702C | I-PhIS050159519S | 2019-02-18 | Klinik Kesihatan Sibu Jaya | Data Mining - PhARM | BI Tools (PF6.6(a)) - Report no tally with Extemporaneous Registry | Email: Berikut ada senarai data yang bercanggah pada bulan Dis 2018. Dilampirkan laporan yang berkenaan. Sila rujuk lampiran. PF 6.6(a)_AKTIVITI SEDIAAN BUKAN STERIL and Extemporaneous Registry BI Tools: 2 PhIS: 6
5 | 19626894C | I-PhIS050017519S | 2019-02-13 | Hospital Sibu | General Module | Request unit follow login location | Mr Francis request unit follow login location that he select while login phis. He informed it will trouble if every time want to login/view other patient by always change the unit. Already inform user to create another account but user inform every staff available works at different location on weekend/night shift. So that he request if the unit can follow based on location user select while login system. Update: As i checked on transcribing page, i can transcribe patient's profile under different discipline thru record record Prescription My concern is... Dangerous Drugs required quantity of physical , Tally card(prescription book), and PHIS to be tally every week. If my profile is LOCKED in Outpatient Pharmacy, i couldn't trace the item movement for in patient/ Pharmacy DD account. For my concern, i only can select 1 store unit. If my request is approved, the pharmacy store unit can be change automatically when i select its location at login page. Sorry for the misunderstanding. To Summarize my request again, Request: Store / Substore unit can be change automatically when selecting location in login page. Justification: To allow pharmacist and Provasional Registered Pharmacist (PRP) check the quantity of stock (DANGEROUS DRUG) from various location (IPD DD/ OPD DD/ Store DD) without changing user profile everytime.
6 | 19626247C | I-PhIS049968319S | 2019-02-11 | Hospital Sarikei | Manufacturing - Extemporaneous | Request Enhancement in Report/Enquiry Formula - Extemp | Mr Han request to add Extemporaneous Formula like Galenical formulation. He want to print and keep because if phis down he can refer and make work order to patient.
7 | 19627036C | I-PhIS050031219S | 2019-02-13 | Hospital Sarikei | Order Management - Web | SPUB patient list - Unable to add new SPUB - Dispensing Location IP | User Mr Lim reported user unable to add new SPUB due when user search no record for reported MRN.User inform he dispense for 2 month but it appear fully dispense at clinical summary. Location : Inpatient pharmacy MRN : HSRK00093456
8
9
10
11
12
13
14
15

## Selangor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19631255C | I-PhIS050343319S | 2019-02-26 | Klinik Kesihatan Kalumpang | Data Mining - PhARM | PF6.6b - Screen sturcture not similar with PF6.6b from MOH | En Omar reported the screen structure of PF6.6b not similar as PF6.6b from MOH. 1. Merujuk kepada aduan di atas, saya ingin tahu kenapakah format lapuran yang saya perlu buat secara manual tidak sama dengan yang di dalam PhIS Kenapalah perkara ini boleh berlaku ? Pihak yang empunya modul ini tidak dapatkah format baru lapuran PF 6.6(b) ini ? 2. Bilakah pihak PhIS akan memaklumkan kepada fasiliti bahawa tidak perlu lagi membuat lapuran manual kerana data tersebut telah ada di dalam PhIS dan maklumat ini bole di 'akss' oleh pegawai yang berkenaan pengumpulan data ini Justeru itu saya masih perlu merekod secara manual ungtuk repot ini dan sia sialah kemudahan ini yang ada di dalam PhIS.
2 | 19624454C | I-PhIS049823119S | 2019-02-01 | Hospital Kuala Kubu Bharu | Order Management - Web | Medication Order- Add column for Reaction Details in Allergy History | Ms Suraya request enhancement at Medication Order screen at Allergy History only show 5 column when open such as Allergen,Allergen type, Severity,Status and Identification Date. She want add column Reaction Details for easy to read. Please refer attachment given for more detail to understanding.
3 | 19626797C | I-PhIS050009219S | 2019-02-12 | Klinik Kesihatan Kalumpang | Order Management - Web | Request to minimize the transcribe stage | Berkenaan perkara di atas, saya ingin bertanya tentang langkah: 1. Menanda 'Tik' untuk 'Patient Arrived' Salah satu tujuan membuka skrin ini ialah untuk transkrib ubat pesakit. Membukanya secara sendiri menandakan pesakit telah tiba, mengapa perlu langkah menanda 'tik' pada 'patient arrive'? Masa 'waiting time' sendiri boleh bermula apabila 'single stage dispensing' ini dibuka. Jika modul ini dibuka bukan dengan tujuan transkrib, sistem sendiri boleh diprogram untuk membatalkan masa menunggu itu sendiri. Ini akan menjimatkan masa dan langkah dapat dipendekkan. 2. Langkah memilih 'allocate', label, dispense' Sistem sendiri akan mengira secara 'auto' berapakah baki hari untuk ubat dibekalkan . ini ditunjukkan pada skrin pada 'supply duration'. Jika modul ini dibuka dengan tujuan pesakit telah datang maka dengan sendiri jumlah hari akan diikuti. Kecuali lah jika 'supply duration' itu diubah, maka untuk pengesahan boleh ditanya untuk memilih langkah 'allocate'. Bukankah satu langkah dapat dipendekkan ? Kedua - dua faktor ini menjadikan sistem program ini cerdik, kerana tujuannya telah nyata. Ini yang saya dapat lihat. Tidak tahulah saya jika ia mempunyai tujuan yang lain.
4 | 19626309C | I-PhIS049975119S | 2019-02-11 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Dispensing - Request to pop up notification when proceed dispense for Insulin | User request pop up notification when proceed dispense for drug under insulin.Example : Are you sure want to proceed to dispense due expired item is 6 week or 42 days?' Example item : Insulin regular/isophane (Mixtard-30) 100 IU/mL Penfill
5 | 19626553C | I-PhIS049991819S | 2019-02-12 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Medication order - request system will decrease if patient came late for next appointment. | User Mr Omar request system will decrease if patient came late for next appointment.User request duration been deduct for day patient late from appointment date. Current : when patient came late 7 days from the appointment, system still proceed to dispense for 30 days. Request : Patient came 7 days late from appoinment, duration been deduct days and patient will receive for duration only for 23 days.
6 | 19626303C | I-PhIS049973919S | 2019-02-11 | Klinik Kesihatan Kalumpang | Outpatient Pharmacy | Transcribe order - Request duration been auto calculate after change clinic TCA and supply duration | User Mr Omar inquiry : 1. inquiry able to change date for supply duration 2.Inquiry able to change TCA date or not and order detail will change or not 3.Inquiry able to search patient for add manual in system 4.Patient came late from date for supply, will decrease or depand on duration for partial supply. Example MRN : 83102 User Mr Omar request duration been auto calculate after he change clinic TCA and supply duration for partial supply
7 | 19629594C | I-PhIS050233719S | 2019-02-20 | Klinik Kesihatan Kalumpang | Report/Enquiry | Drug Utilisation - Request to add new column for IC Patient | Encik Omar request to add new column (IC Patinet) in Drug Utilization report. They not use MRN number in practice and doctor and nurse not using PhIS for pharmacy based.
8 | 19624895C | I-PhIS049863119S | 2019-02-04 | Hospital Kajang | Report/Enquiry | MTAC Registry - Request to enhancement | User Ms Ani request to add column for numbering or total report when she print. Current : User need to calculate manual for hardcopy.
9 | 19630234C | I-PhIS050276019S | 2019-02-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Return to Supplying Unit - Request Return Type remark as mandatory | En Omar request to remark Return Type as mandatory. Since in current version not remark as Mandatory, if user did not select Return Type , user cannot proceed to add item.
10
11
12
13
14
15
16
17
18

## Terengganu
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19628912C | I-PhIS050179319S | 2019-02-19 | Hospital Setiu | Manufacturing - Extemporaneous | Extemporaneous - Worksheet - Request to add batch no. column | User request to add batch no. column at screen worksheet extemporaneous. User request system auto generate that batch no. User informed currently only appear batch no. for material item. But now user request to add batch no. for the whole preparation.
2
3
4
5
6
7
8
9
10

## HKL
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19625818C | I-PhIS049939319S | 2019-02-08 | Hospital Kuala Lumpur | General Module | Permohonan CR: User Profile & User Role - khas untuk Pentadbir Jururawat & Pegawai Perubatan | Receive email from user : Untuk makluman, pihak kami menghadapi kesukaran dalam menyelenggara akaun pengguna terutamanya bagi Jururawat dan Pegawai Perubatan setelah tiga (3) tahun PhIS dijalankan di HKL. Seperti yang diketahui, proses penyelenggaraan akaun pengguna (maintenance of user account/profile) ini penting bagi memastikan hanya pengguna yang aktif sahaja wujud supaya tidak berlaku isu data integrity (contoh: nama prescriber yang tidak lagi wujud digunakan semasa Record Prescription). Tambahan pula, ekoran daripada peluasan PhIS di wad-wad HKL (bagi pelaksaaan imprest stock) memerlukan penyelenggaraan akaun Jururawat yang lebih komprehensif. Oleh sebab pergerakan anggota di HKL adalah sangat kerap dan bilangan anggota yang terlalu ramai, pihak kami memerlukan Pentadbir khusus daripada pihak Jururawat/Pegawai Perubatan. Namun demikian, didapati Role â€œFacility Admin Generalâ€ bagi menyelenggara User Profile dan User Role adalah terikat dengan Role-Group lain seperti Calendar, Mobile_Security, Inventory Notification, Hospital Information yang didapati agak sensitif/boleh membahayakan tetapan sistem di fasiliti menyebabkan ianya tidak sesuai untuk diâ€™enableâ€™kan kepada Pentadbir (Jururawat/Pegawai Perubatan). Oleh yang demikian, pihak kami ingin memohon Change Request bagi mewujudkan Role khusus untuk pentadbir pihak luar daripada Farmasi (pihak Jururawat/Pegawai Perubatan/Pentadbir) untuk membolehkan mereka menyelenggara akaun bagi anggota di bawah jagaan masing-masing. Dilampirkan beberapa screenshot untuk rujukan pihak tuan/puan. Besarlah harapan kami sekiranya permohonan ini dapat dipertimbangkan.
2 | 19627685C | I-PhIS050082319S | 2019-02-14 | Hospital Kuala Lumpur | Pharmacy Inventory | request - system to allow indent same drug.non drug code for different item code | user request system to allow indent same drug/non drug code for different item code. For example item: GLN0200022(Bismuth, Iodoform, Liquid Paraffin (BIPP) Paste, Gauze) got 3 different item code, and user need to order 2 different item code , system will prompt alert message item already in list
3 | 19631058C | I-PhIS050325119S | 2019-02-25 | Hospital Kuala Lumpur | MTAC | MTAC reporting - Request enhancement | Tuan/puan, Dengan segala hormatnya saya merujuk kepada perkara di atas. Pihak kami ingin membuat Change Request untuk menambah collapsible box Specific Details ke dalam modul MTAC Reporting bagi Cardiac Rehab Program (CRP) (seperti dalam screenshots) yang dilampirkan. Antara fields yang akan dimasukkan di bawah Specific Details adalah seperti berikut (Rujuk lampiran): 1- Thrombolysis - Checkbox (Yes/No) - If yes, Thrombolytic agents; Checkbox: Streptokinase or Tenecteplase or Others (Please specify: Open short text field) - Date given; Calendar field 2- ECHO - At discharge: Numeric field (suffix %) - Date ECHO done: Calendar field - After 6 months: Numeric field (suffix %) - Date ECHO done: Calendar field 3- Stress Test Results - Date Test done: Calendar field - Checkbox: Positive or Negative 4- Percutaneous Coronary Intervention (PCI) Status - Checkbox (Yes/No) - If yes, Types; Checkbox: Drug-eluting Stent (DES) or Bare-metal Stent (BMS) or Drug-eluting Balloon or Bioresorbable Vascular Scaffold (BVS) or Others (Please specity: Open short text field) Memandangkan kami merupakan antara perintis program MTAC CRP, kami amat mengharapkan agar Change Request ini dapat dilaksanakan bagi memudahkan aktiviti PhIS MTAC Reporting dijalankan. Justeru menjadikan PhIS sebagai platform utama untuk rujukan bagi menjalankan aktiviti MTAC CRP di masa akan datang. Besarlah harapan kami sekiranya permohonan ini dapat dipertimbangkan.
4
5
6
7
8
9
10
11
12

## WLabuan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6

## WP
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 19625632C | I-PhIS049924019S | 2019-02-08 | Pejabat Kesihatan Putrajaya | Report/Enquiry | Stock Balance By Drug/Non Drug - Request to remove drug from list after inactive | Request to remove drug from list of stock balance by drug/non drug after user inactive the item at drug/non drug catalogue. Purpose:- Everytime when user want to generate from from stock balance by drug/non drug screen, she unable to direct print the report. She need to export to excel first to filter the required item and remove the unwanted item.
2
3
4
5
6

## Institut
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10