## Summ_Module
Summary by Status
No | Issue Type | Request
1 | Pharmacy Inventory | 32
2 | Patient Management | 0
3 | Order Management - Web | 12
4 | Order Management - Mobile | 0
5 | Special Drug Request | 4
6 | Outpatient Pharmacy | 5
7 | Inpatient Pharmacy | 3
8 | MAR - Web | 0
9 | MAR - Mobile | 0
10 | MTAC | 1
11 | Ward Pharmacy | 3
12 | Medication Counseling | 0
13 | Adverse Drug Reaction (ADR) | 5
14 | Clinical Pharmacokinetic Services (CPS) & TDM | 0
15 | Drug Information & Consumer Education | 2
16 | PhIS Portal | 0
17 | Manufacturing - CDR | 0
18 | Manufacturing - Extemporaneous | 1
19 | Manufacturing - Galenical | 0
20 | Manufacturing - IV | 2
21 | Manufacturing - PN | 0
22 | Manufacturing - Radiopharmaceutical | 0
23 | Data Mining - PhARM | 8
24 | Report/Enquiry | 17
25 | IWP | 0
26 | General Module | 8
27 | BCP | 0
| Total | 103

## Summ_State
No | Issue Type | Request
1 | BPF | 15
2 | Johor | 3
3 | Kedah | 0
4 | Kelantan | 6
5 | Melaka | 0
6 | Pahang | 5
7 | Perak | 14
8 | Pulau Pinang | 4
9 | Sabah | 14
10 | Sarawak | 9
11 | Selangor | 18
12 | Terengganu | 3
13 | W. Persekutuan | 6
14 | Negeri Sembilan | 1
15 | Perlis | 1
16 | HKL | 3
17 | W. Labuan | 1
18 | Institut | 0
| Total | 103

## Total
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks | State
1 | 18472413C | I-PhIS038817218S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools(Medicines Utilisation Report) - Request to add additional tab for Receive Category | Request to add additional tab for Receive Category: drop down 1. Blank/Online Procurement 2. Free of Charge (FOC) 3. Replacement 4. Bonus (PASC) 5. Offline Procurement | [5 empty] | BPF
2 | 18472474C | I-PhIS038821118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools - Request to add additional column for Receive Category in the Medicines Utilisation Report | Request to add additional column for Receive Category in the Medicines Utilisation Report | [5 empty] | BPF
3 | 18480713C | I-PhIS039289118S | 2018-06-12 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools-Kemaskini format application usage KPI Indication report | Request to update format for Report of application usage KPI Indication in BI Tools. Refer user attachment at format reference. From Email:- format terbaru bagi laporan application usage KPI Indication untuk dikemaskini dalam BI Tools dengan kadar segera kerana pihak negeri akan mula menghantar pelaporan KPI bagi tempoh Jan-Jun 2018 bermula bulan Julai berdasarkan kepada laporan application usage KPI Indication ini. | [5 empty] | BPF
4 | 18472293C | I-PhIS038799118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(LP) - Request to add drop down menu for Item Scheme | Request to add drop down menu for Item Scheme: 1. Normal/Non PASC 2. PASC | [5 empty] | BPF
5 | 18472319C | I-PhIS038803118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(Contract) - Request to add drop down menu for Item Scheme | Request to add drop down menu for Item Scheme: 1. Normal/Non PASC 2. PASC | [5 empty] | BPF
6 | 18472334C | I-PhIS038805218S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(AP) - Request to add drop down menu for Item Scheme | To add radio button Offline Procurement and Online Procurement (Mandatory) in AP Purchase Order | [5 empty] | BPF
7 | 18472341C | I-PhIS038807118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Receive From Supplier - Request to add additional drop down menu for Receive Category | Request to add additional drop down menu for Receive Category: 1. Bonus (PASC) 2. Offline Procurement | [5 empty] | BPF
8 | 18472355C | I-PhIS038809118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Receive From Supplier - Request to indicate as mandatory fields for Receive Category : Bonus (PASC) | Request to indicate as mandatory fields for Receive Category : Bonus (PASC) 1. Receive Item Against 2. LPO No. 3. Supplier Name 4. Item Group 5. DO No. 6. Goods Received Date & Time | [5 empty] | BPF
9 | 18477455C | I-PhIS039093118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order - Request for date range as LPO approved date instead of created date | User request filter date range change to LPO approved date instead of created date. But, user still want the created date remain at listing record. | [5 empty] | BPF
10 | 18472377C | I-PhIS038811118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Report/Enquiry - Request to add new report for item received including Bonus PASC | Request to add new report for item received including Bonus PASC Menu >>> Report/Enquiry >>> Inventory >>> Procurement >>> YTD Received Item Supplier | [5 empty] | BPF
11 | 18472632C | I-PhIS038825118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Drug Utilisation Report - Request to add a tab for Indication | Request to add a tab for Indication: - drop down ALL - drop down Specific Indication | [5 empty] | BPF
12 | 18472653C | I-PhIS038827118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Drug Utilisation Report - Request to add information on: Total Number of Patients per Indication | Request to add information on: Total Number of Patients per Indication | [5 empty] | BPF
13 | 18476872C | I-PhIS039039318S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | PF5.5b - Request to change specification from PhIS and BI Tools | Mohon untuk tukar spesifikasi teknikal bagi PF 5.5(b) dalam PhIS dan BI Tools seperti berikut: Bagi semua kolum pre , mohon guna appointment type=new sebagai formula kepada kolum tersebut bagi menggantikan formula visit number=1 | [5 empty] | BPF
14 | 18477693C | I-PhIS039089118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | CDR Registry - Request to add new field/filtering | User request to add new field/filtering for CDR Registry Future Column and Filtering: 1. Prepare admixture: Yes/No 2. Dispensed status: All 3. Age group: Adult or paediatric At CDR order screen, to identify order for adult or paediatric | [5 empty] | BPF
15 | 18477732C | I-PhIS039091118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | PN Registry - Request to add new field/filtering | User request to add new field/filtering for PN Registry Future Column and Filtering: 1. Dispensed Status: All | [5 empty] | BPF
16 | 18456493C | I-PhIS037889118S | 2018-06-01 | Hospital Kuala Lumpur | Inpatient Pharmacy | Fill list - Request to remove Refresh Option | User request to remove Message stock has been modified as he need to click refresh button. Once click refresh button he need to start all over again. | [5 empty] | HKL
17 | 18484295C | I-PhIS039551218S | 2018-06-14 | Hospital Kuala Lumpur | Report/Enquiry | Drug Supply Registry - Request on Discharge Referred | Miss Chia request on discharge referred 1) Sent To need to auto popup according facility on referred facility that user choose 2) Able to add multiple drug name at prescription details. Current situation, if one patient have two drugs need to do one by one drug supply transaction. 3) Cost need to auto calculate base on drug price in PhIS | [5 empty] | HKL
18 | 18486373C | I-PhIS039693118S | 2018-06-18 | Hospital Kuala Lumpur | Report/Enquiry | report / inquiry - request to add new column Counselling by unit at Medication Counselling | user request to add new column Counselling by unit at Medication Counselling Reporting specific by unit that given the Medication Counselling as user inform at HKL few unit will give Medication Counselling to patient as user unable to identify which unit give the Medication Counselling. | [5 empty] | HKL
19 | 18480974C | I-PhIS039307118S | 2018-06-12 | Hospital Pontian | General Module | Unit Catalogue List - Request to add one column for item type in stock available | User request to add one column for item type in stock available. User want to know stock available under which category of item. Kindly refer attachment for reference. | [5 empty] | Johor
20 | 18482193C | I-PhIS039397118S | 2018-06-13 | Hospital Sultanah Aminah | Manufacturing - IV | IV ad - ROA on label to be in full sentence | User request ROA on label to be in full sentence. ROA on label is in short form eg IVF, IVB as seen which can cause confusion for nurses while doing administration. Possible to label in full sentences eg ' IV Infusion' , 'IV Push' or 'IV Bolus', 'Intraventricular' , 'Intrathecal'. Please add in 'Intraventricular' and 'Intrathecal', only for Vancomycin and Polymycin B. | [5 empty] | Johor
21 | 18482453C | I-PhIS039409118S | 2018-06-13 | Hospital Sultanah Aminah | Manufacturing - IV | IV Admixture - Preset expiry date and final concentration | In order to prevent medication error, user hope that the expiry date can be preset according to our formulary CIVAS (as attached). Other than that, user's preparations are all done in standardized final concentration as shown in 'Drug Description' in formulary CIVAS (as attached). User are suggesting that once user key in the drug dose, the system can automatically calculate the drug volume and final volume according to this preset final concentration instead of key in the final volume ourselves. This can reduce workload and reduce medication error. | [5 empty] | Johor
22 | 18505494C | I-PhIS041031218S | 2018-06-28 | Hospital Tanah Merah | Drug Information & Consumer Education | Drug Info : Request to allowed for Edit Enquiry Date & Time | User request to allowed for Edit Enquiry Date & Time . | [5 empty] | Kelantan
23 | 18480433C | I-PhIS039279118S | 2018-06-12 | Klinik Kesihatan Labok | Order Management - Web | Record Prescription - Request cursor default on Original Prescription Serial Number | Pn Hidayah request cursor default on Original Prescription Serial Number. This is due to current v1716, cursor default on drug and it take time for user to key in data patient. | [5 empty] | Kelantan
24 | 18491313C | I-PhIS040039118S | 2018-06-21 | Klinik Kesihatan Kuala Balah | Order Management - Web | Allergy - Request pop up allergy base on active ingredients | Encik Mohd Azwan request pop up allergy base on active ingredients and request to revise back the substance class for active ingredients. Current Situation- Please refer remarks & File Upload : User attachment Additional : Some active ingredients got substances class that not related. Example Amlodipine : As confirmed by user the substances class for Amlodipine suppose only : Calcium channel blocking agents - dihydropyridines Currently in system, got 3 substance appear when select Active Ingredients Amlodipine. | [5 empty] | Kelantan
25 | 18465454C | I-PhIS038473318S | 2018-06-06 | Hospital Tumpat | Pharmacy Inventory | Penalty - Expected Delivery Date shows wrong | Pn Fatimah reported Expected Delivery Date shows wrong in penalty screen. She informed eP approved Date and Time is on 14/5 but for Expected Delivery Date state 16/5. User already received stock on 20/5. Delay days shows 4 days. She claim supposedly Expected Delivery Date is 22/5/18. Kindly refer attachment. | [5 empty] | Kelantan
26 | 18480533C | I-PhIS039283118S | 2018-06-12 | Klinik Kesihatan Wakaf Bharu | Pharmacy Inventory | issue RIQ - preferred item that requester unit select during indenting not appear | user request supplying unit able to see preferred item that requester unit select during indenting as user inform user need to supply same as user request at preferred item. user inform currently when user checked at RIQ, system not display preferred item that requester unit select during indenting. kindly refer file upload | [5 empty] | Kelantan
27 | 18495495C | I-PhIS040343218S | 2018-06-24 | Hospital Tanah Merah | Ward Pharmacy | Ward Pharmacy - Request enhancement for Ward Pharmacy | Miss Lee Wan Nee request able to key in daily review and C&S without need to complete CP2 first. Current Situation : User unable to key in daily review and C&S without complete CP2 first. Related Report : 18495333C | [5 empty] | Kelantan
28 | 18494274C | I-PhIS040245118S | 2018-06-22 | Klinik Kesihatan Seremban (TPC) | Data Mining - PhARM | BI Tools [Farmakokinetik (TDM)] - Don't have specific report in BI Tools | Email: Pengguna melaporkan data BI Tools Farmakokinetik (TDM), hanya ada bil kes.Tiada bil jenis ubat dipantau, bil.permohonan yg diterima dan bil. pemantauan kes dijalankan oleh makmal. | [5 empty] | Negeri Sembilan
29 | 18474034C | I-PhIS038893118S | 2018-06-09 | Klinik Kesihatan Bandar Tun Abdul Razak | General Module | Setting current date in system | User inform date(calender) setting in system PhIS always default to 1 January. So when user would like to set date user would have to scroll the calender untill met the latest date and save. Sometimes if user would like to ammend data in system, system will auto change to 1st January back before able to save. User request to easily set the current date. | [5 empty] | Pahang
30 | 18480793C | I-PhIS039301118S | 2018-06-12 | Hospital Tengku Ampuan Afzan | General Module | Request to add number of counter from 10 to 15 | Puan Elina request to add number of counter from 10 to 15. Number of counter in login page. | [5 empty] | Pahang
31 | 18477656C | I-PhIS039085118S | 2018-06-11 | Hospital Jerantut | Outpatient Pharmacy | Request to add column select check box at screen dispensing | User request to add column select check box at screen dispensing to allow user select few patient for dispensing in one time. user inform if there have 1000 record of patient, user have to enter one by one to clear patient name at screen dispensing. | [5 empty] | Pahang
32 | 18471335C | I-PhIS038747118S | 2018-06-08 | Hospital Kuala Lipis | Pharmacy Inventory | Returned Item - Request able to return item to inter facility | Miss Tan request have a module to able to return item to inter facility. | [5 empty] | Pahang
33 | 18456953C | I-PhIS037925118S | 2018-06-01 | Hospital Tengku Ampuan Afzan | Ward Pharmacy | Ward Pharmacy(CP2) - Request to change name for transcribe by | En Nasri request to change name for transcribe by to created by at screen ward pharmacy CP 2 and CP1. Due to currently system show who login the system. Refer file upload. step by user : clinical summary>click CP1/CP2>click link at CP1/CP2 | [5 empty] | Pahang
34 | 18462152C | I-PhIS038241118S | 2018-06-05 | Hospital Sg Siput | Adverse Drug Reaction (ADR) | ADR Reporting (Drug Details) - Request to rename Total daily dosage given | Ms Fong request to rename 'Total daily dosage given' to 'Dosage given' due to it really confusing to user. Situation: Supply drug to patient for frequency TDS (three times a day) with dosage 275 mg. User key in Total daily dosage given as 825 mg which is 275 mg*3. However when print the reporting, it supposed means user to key in 275 mg only (not total). | [5 empty] | Perak
35 | 18498854C | I-PhIS040563318S | 2018-06-26 | Hospital Seri Manjung | Data Mining - PhARM | Bi Tools - Request able to filter data by range of month for all report in Bi Tools | User request able to filter report by range of month. Example : Jan 2018 until June 2018 Currently only able to filter by monthly or all. | [5 empty] | Perak
36 | 18466213C | I-PhIS038511218S | 2018-06-06 | Hospital Seri Manjung | General Module | Order Routing - Request to enable set more than 1 unit | Pn Zuraidah inform that during working hours, satelite pharmacy is under Inpatient. But after working hours, satelite pharmacy can be both inpatient and outpatient (ED). However Order Routing screen only allow user to select one unit only. | [5 empty] | Perak
37 | 18471833C | I-PhIS038777118S | 2018-06-08 | Hospital Bahagia Ulu Kinta | Inpatient Pharmacy | Inpatient drug label - Request to know the purpose of box date supply | En Hilmi request to know the purpose/function of box date supply at inpatient drug label. As per inform by user, he want to know the right purpose by module owner since facility don't use the box. If follow the 'Carta Ubat' at facility that they can sign or check who transcribe the drug and only have 1 box. User query why have 7 box of date supply in the inpatient drug label. User request to remove the box of date supply and make all the details in drug label become bigger IF APPLICABLE. Related report: 16075640C, 17156176C Updated: User request to remove the box date supply since it is not necessary at his hospital and request to make other details font become bigger. | [5 empty] | Perak
38 | 18463596C | I-PhIS038345118S | 2018-06-05 | Klinik Kesihatan Manong | Order Management - Web | Record Prescription - Request to display confirmation popup | Saya ingin mengemukan beberapa cadangan penambahbaikan bagi versi berikutnya. A. Mencadangkan diwujudkan semula conformation pop up semasa Medication Order setelah menekan butang Conform. Hal ini bagi membolehkan ubat yang tertinggal atau tersilap order boleh dibuat pembetulan. | [5 empty] | Perak
39 | 18466673C | I-PhIS038537118S | 2018-06-06 | Hospital Raja Permaisuri Bainun | Order Management - Web | Request to have print prescription button/link at Medication Profile page | Request to have print prescription button/link at Medication Profile. Sometimes doctor may not print immediately after order but they can print PS later when the visit patient medication profile. | [5 empty] | Perak
40 | 18503813C | I-PhIS040913118S | 2018-06-27 | Klinik Kesihatan Buntong | Order Management - Web | Medication Order (SPUB) - Request to allow multiple prescription with same patient | User request to allow multiple prescription with same patient without proceed until verification screen. Currently, user need to verify the prescription in verification screen before user transcribe new offline SPUB from others facility. User claimed one patient can have many prescription from different facility. This purpose is to make sure user not confused to check one by one screen when user has complete until verification. | [5 empty] | Perak
41 | 18456793C | I-PhIS037915118S | 2018-06-01 | Hospital Tapah | Outpatient Pharmacy | Preparation - Extemporaneous - Request to auto allocate X-Tempt | Based on report no: 18454873C. User reported there is no item batch and expiry date for X-Tempt item. User was advise to do Issue-Consumption to deduct stock from Unit Catalog List to tally stock. Therefore, user request to auto allocate X-Tempt item. | [5 empty] | Perak
42 | 18471496C | I-PhIS038751118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | SPUB - Request proceed offline SPUB without proceed online SPUB | User request to allow proceed offline SPUB without proceed with online SPUB to confirm order. Currently he unable to add item at Medication Order . User do request since he refuse to proceed online SPUB before proceed Offline SPUB. User claimed patient came to facility not to collect Online SPUB. | [5 empty] | Perak
43 | 18471535C | I-PhIS038753118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | Indent SPUB - request to allow indent for item standard and non standard | User request to allow indent for all item standard and non standard. Currently user able to indent for item non standard only. | [5 empty] | Perak
44 | 18471578C | I-PhIS038755118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | Record Prescription - Request cursor mouse auto appear at empty column | User request cursor mouse auto appear at empty column for screen record prescription, so that pharmacist not required to move the mouse cursor to the empty column when type patient ID . Currently cursor auto appear at Select Registration Patient All not at empty column. | [5 empty] | Perak
45 | 18485213C | I-PhIS039623518S | 2018-06-18 | Hospital Tapah | Pharmacy Inventory | report / inquiry -request to add new column search by drug/ non code at item movement | user request to add new column search by drug/ non code at screen item movement to make user select drug/non drug code before select item code.as current version user have to select specific item code for same item. | [5 empty] | Perak
46 | 18490073C | I-PhIS039959118S | 2018-06-20 | Hospital Sg Siput | Pharmacy Inventory | Stock transfer - Able to add more than 1 item | User Miss Tan request able to add more than 1 item when do stock transfer.Purpose user request due to user need to create more than 1 transaction if user want to stock transfer more than 1 item. | [5 empty] | Perak
47 | 18501933C | I-PhIS040791118S | 2018-06-27 | Hospital Teluk Intan | Pharmacy Inventory | KEWPS 10 - Request for amend SKU or PKU column | En Amir request amend SKU or PKU column on KEWPS10 beside Issue Quantity column. So that user will be not confused either he will issue in SKU or PKU quantity. | [5 empty] | Perak
48 | 18486433C | I-PhIS039697118S | 2018-06-18 | Hospital Tuanku Fauziah | Report/Enquiry | report/inquiry - request to add column Total number of item dispensed at Prescription Management IP | user request at screen report/ inquiry - Inpatient Prescription to show report for Total number of item dispensed as user inform user need to collect data that user already dispense for each unit | [5 empty] | Perlis
49 | 18458974C | I-PhIS038069218S | 2018-06-04 | Klinik Kesihatan Kepala Batas | Order Management - Web | Medication order - Request to move search listing | Cik Farah request search listing do not cover the Original Prescriber Name column during typing . Refer file upload. | [5 empty] | Pulau Pinang
50 | 18483134C | I-PhIS039455318S | 2018-06-13 | Hospital Bukit Mertajam | Order Management - Web | Record Prescription (Med Order) - Request starting cursor default at queue no | Ms Tan request starting cursor default at queue no. User inform for current system, cursor default at drug. User claim they have to key in all mandatory field before proceed. If starting cursor start from queue no, supposedly there is no left field required to fill in. | [5 empty] | Pulau Pinang
51 | 18483152C | I-PhIS039455418S | 2018-06-13 | Hospital Bukit Mertajam | Order Management - Web | Record Prescription (Med Order) - Request to extend running time of drug selection | Ms Tan request to extend running time of drug selection. She inform when she select drug to transcribing, for example user choose simvastatin, system appear selection different strength but when user try to use arrow down at keyboard, the running time is too fast. Sometimes, user want to select 40 mg but system auto select 20 mg after user press down arrow keyboard. She inform pharmacist usually use keyboard and not always use mouse for fast transcribing. | [5 empty] | Pulau Pinang
52 | 18483633C | I-PhIS039499118S | 2018-06-14 | Hospital Seberang Jaya | Pharmacy Inventory | Task List-Unable to reject status pending to receive | User reported there has transaction receive internal with status pending to receive exist in task list. When user double click the transaction there has no reject button. User want to reject the transaction due main store did not receive the physical item. RT17000021 RT17000024 RT18000003 RT18000014 | [5 empty] | Pulau Pinang
53 | 18484673C | I-PhIS039581118S | 2018-06-16 | Hospital Beluran | Adverse Drug Reaction (ADR) | NPRA- Request to have Notification Message once NPRA Send | Mr.Quah request to have Notification Message once NPRA Send. This is due user did not know if NPRA has been send or not. | [5 empty] | Sabah
54 | 18507853C | I-PhIS041187118S | 2018-06-29 | Hospital Queen Elizabeth | MTAC | Request to allow selected users to view the MTAC RVD | User Miss Melinda request to allow only certain users to use the MTAC RVD module in PhIS to maintain patient's privacy and confidentiality. | [5 empty] | Sabah
55 | 18493733C | I-PhIS040205118S | 2018-06-22 | Hospital Dutchess of Kent | Order Management - Web | Record Prescription - Request to add brand name column at allergy details | Ms Lam request to add new column as 'Brand name' at allergy details. She inform for example patient have allergy to a Specific Brand only, user had key in the specific brand that patient allergy. After that when user want to view details back, the brand is not appear. User also unable to double click to view the allergy details. Example: Record prescription > search patient IC > click down arrow at allergy > click details > brand name not appear. User inform it difficult if patient admit ward and want to prescribe drug to that patient. If pharmacist unable to see correct details, they don't give the drug to patient at all. Besides patient just allergy to specific brand only. | [5 empty] | Sabah
56 | 18501912C | I-PhIS040793118S | 2018-06-27 | Klinik Kesihatan Suan Lamba | Order Management - Web | Transcribe order - Request to proceed verified,prepare and dispense without closed page | Mr Joey request to proceed verified,prepare and dispense without closed page. Current system : After click verify page close and user need to click module preparation to proceed other screen. User need to use more time to proceed dispense and also the waiting time is higher. User inform facility only have 1 pc and user not have many times to do many step. | [5 empty] | Sabah
57 | 18464133C | I-PhIS038383218S | 2018-06-06 | Hospital Tawau | Pharmacy Inventory | Purchase Order (Contract) - request to allow eP approved even delivery due date already past | User reported unable to proceed eP approved due to delivery due date already past. She inform if want to proceed eP approved need to adjust the date for delivery. According to user if she adjust the date, it will affect the delivery lead period. Then it also effect for penalty. Therefore she request to allow eP approved even delivery due date already past. | [5 empty] | Sabah
58 | 18489893C | I-PhIS039945118S | 2018-06-20 | Cawangan Farmasi Logistik Negeri | Pharmacy Inventory | Issuing - Request system not auto issue for Purchase Order : Quotation and Request type: Indent | En Humam reported when proceed receiving for LP Purchase Order : Quotation and Request Type : Indent system will auto issuing. Therefore he request system not auto issuing when proceed receiving by same person. According to user in his facility procedure there have their own person in change for receiving and issuing. | [5 empty] | Sabah
59 | 18495753C | I-PhIS040369118S | 2018-06-25 | Hospital Beluran | Pharmacy Inventory | Label prepacking - Request to center the label | Mr Quah request to center the label when print due currently label not center and have more space empty. Refer attachment. | [5 empty] | Sabah
60 | 18505313C | I-PhIS041021118S | 2018-06-28 | Hospital Queen Elizabeth | Pharmacy Inventory | Purchase order - Request to add in the packaging description when search item | Mdm Tee Swee Pin request to add in the packaging description when search item. Email user: Is it possible to add in the packaging description in item purchase order for purchase order like the one product search in quotation? The problem user are facing are: need to guest packaging (Kindly refer attachment) | [5 empty] | Sabah
61 | 18475853C | I-PhIS038975218S | 2018-06-11 | Hospital Dutchess of Kent | Report/Enquiry | Drug Utilisation - Request to add new column - Identification Card | Ms Tham request to add new column (identification card) in Drug Utilization report. It will easier for user to filter or search patient using IC number. | [5 empty] | Sabah
62 | 18491694C | I-PhIS040063118S | 2018-06-21 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Stock Balance By Drug/Non-Drug - Add column last transaction issue out | User Mr Human request to add column last transaction issue out for the item.Purpose user request due user unable to find item that not been issue out more than 6 month.If user search using module slow processing,only item have slow moving within 6 month. | [5 empty] | Sabah
63 | 18498233C | I-PhIS040517118S | 2018-06-25 | Hospital Dutchess of Kent | Report/Enquiry | Extemporaneous Registry - Request to add patient name and IC No | Ms Tham request to add patient name and patient IC No on extemporaneous registry report. | [5 empty] | Sabah
64 | 18488052C | I-PhIS039813118S | 2018-06-19 | Cawangan Farmasi Logistik Negeri | Special Drug Request | Special Drug Request - Unable to Recomended request | User Ms Pamela reported she unable to recommend any Special Drug Request due to when user click on Recommend button, nothing happen. The status still appear new request. Facility Request No.: PKDSB130002/2018 User ID: 830225125588 V1.7.1.6 | [5 empty] | Sabah
65 | 18503293C | I-PhIS040879118S | 2018-06-27 | Hospital Tawau | Special Drug Request | Special Drug Request - Cannot enter Strength in Decimal Value | Ms Diana informed user want to enter strength in decimal value since strength this drug in decimal but system shows You must specify a number . User informed it should be strength in value decimal due to not accurate if user round number to into Even Number. Drug: Sodium Dihydrogen Phosphate Dihydrate & Disodium Phospate Dodecahydrate Strength: 24.4, 10.8 | [5 empty] | Sabah
66 | 18477553C | I-PhIS039075318S | 2018-06-11 | Hospital Beaufort | Ward Pharmacy | Ward Pharmacy CP2 - CP1 - Request to add new column for Pharmacist recommendation | User request to add column Pharmacist note for pharmacist able to remark general recommendation. Refer user attachment as further reference. | [5 empty] | Sabah
67 | 18491753C | I-PhIS040065218S | 2018-06-21 | Hospital Umum Sarawak | Adverse Drug Reaction (ADR) | ADR Reporting (Drug Details) - Request to rename Total daily dosage given | Miss Phang Lie Jin request to rename 'Total daily dosage given' to 'Dose' due to it really confusing to user. Situation: Supply drug to patient for frequency TDS (three times a day) with dosage 500 mg. User key in Total daily dosage given as 1500 mg which is 500 mg*3. However when print the reporting, it supposed means user to key in 500 only (not total). | [5 empty] | Sarawak
68 | 18501438C | I-PhIS040751318S | 2018-06-26 | Hospital Sibu | Data Mining - PhARM | BI Tools - No Report to be compare with PhIS | Mr Ting Su Hock reported no report in BI Tools to be compare with PhIS. He inform he generate Purchase Order by Drug/Item report in PhIS. He notice that BI Tools has no report that enable him to compare with. | [5 empty] | Sarawak
69 | 18505933C | I-PhIS041057118S | 2018-06-28 | Makmal Ubat dan Stor Bahagian Sibu | General Module | Change Password - Request to extend password expiry validity | Mr Francis request to extend password expiry date due to he inform have to change the password always. She inform it can disturb their work if every time popup appear to change password. Currently maximum password expiry validity is only 90 days. He request if can extend the password expiry date as 2 years in phis. | [5 empty] | Sarawak
70 | 18465633C | I-PhIS038483118S | 2018-06-06 | Hospital Miri | Pharmacy Inventory | REQUEST TO ENABLE USER ABLE TO INDENT SPUB TO LOCATION BESIDE OUTPATIENT | Email: User reported current PHIS system only enable user to indent SPUB items to Outpatient Pharmacy. Actually, some SPUB is refer out by satellite pharmacy, and means the indent need send to satellite pharmacy because satellite pharmacy will supply the items to facility request the items. Temporarily all indent and supply process manually without go through PHIS. | [5 empty] | Sarawak
71 | 18493532C | I-PhIS040193218S | 2018-06-22 | Hospital Saratok | Pharmacy Inventory | RIQ (Intra) - Request able to change supplying unit after save | Ms Karen request able to change supplying unit after save transaction. Example situation: User must select supplying unit as IPD nut wrongly select as Substore unit. She inform the transaction already save. User unable to change back the supplying unit to the correct unit. Also there is no reject button to reject the transaction. | [5 empty] | Sarawak
72 | 18467773C | I-PhIS038611118S | 2018-06-07 | Hospital Umum Sarawak | Report/Enquiry | Generator Elution Record - Request to change last 6 digit Elution Batch No. to as Measured Date | User request to change last 6 digit of Elution Batch No. to as Measured Date instead of Date. Refer user attachment as reference. | [5 empty] | Sarawak
73 | 18499122C | I-PhIS040593118S | 2018-06-26 | Hospital Kanowit | Report/Enquiry | PF 6.3(b) - Report not tally | Ms Ngo reported that PF 6.3(b) not tally. She informed that she had dispensed prescription for 1 patient today (26/6/2018). When she check on Prescription Management IP have recorded 1 data for that patient. She check on Inpatient Prescription report also have recorded 1 data for that patient on column No of Rx Generated. But when she check on PF 6.3(b), shows 0 record for that patient. IC No: 700906135778 | [5 empty] | Sarawak
74 | 18499154C | I-PhIS040597418S | 2018-06-26 | Hospital Kanowit | Report/Enquiry | Inpatient Prescription - Report not tally | Ms Ngo reported that report for Prescription Management IP not tally. She mention she have dispensed 2 prescription today (26/6/2018). Total drug for both prescription is 12. But when she check on No of Rx Generated column shows as 12, while on No of Rx Dispensed also shows as 12. She mention supposedly both column shows 2 prescription only even the total number of item prescribed is 12. Ms Ngo also inform on Prescription Received column at PF 6.3(b) also shows as 12. MRN No: 1) 780527135500 - 4 drug order for 1 prescription 2) 620119135170 - 8 drug order for 1 prescription | [5 empty] | Sarawak
75 | 18504953C | I-PhIS040997118S | 2018-06-28 | Hospital Kanowit | Report/Enquiry | Inpatient Prescription - Request to follow report PF 6.1 | Ms Ngo request for Inpatient Prescription report for number of supplied for daily follow the calculation UDS on PF 6.1 report. Kindly refer calculation UDS provided by Ms Ngo. | [5 empty] | Sarawak
76 | 18459454C | I-PhIS038097118S | 2018-06-04 | Jabatan Kesihatan Negeri Selangor | Data Mining - PhARM | BI Tools - Inventory not follow Manual KPI 2018 | Puan Anis reported Inventory not follow Manual KPI 2018. According to Manual KPI 2018 from Program Perkhidmatan Farmasi , the column No. of item issued should be Bil Pesanan Kerajaan (LPO) dikeluarkan . Kindly refer attachment | [5 empty] | Selangor
77 | 18464554C | I-PhIS038417118S | 2018-06-06 | Jabatan Kesihatan Negeri Selangor | Data Mining - PhARM | Change Request untuk BI Tools | Cadangan penambaikan ini telah dibuat dalam Mesyuarat Teknikal Farmasi Informatik pada 1-2 Mac yang lalu. Tak pasti samada dah masuk jadi CR atau tidak. Saya lihat tiada perubahan as of today jadi saya log cadangan ini semula. 1. KPI Indication Report dalam BI Tools - mohon tambahkan pilihan bulan untuk data dijana (rujuk lampiran) 2. Laporan PF 5.1 dalam BI Tools - mohon tambahkan pilihan bulan untuk data dijana (rujuk lampiran) | [5 empty] | Selangor
78 | 18503254C | I-PhIS040875118S | 2018-06-27 | Hospital Kuala Kubu Bharu | Drug Information & Consumer Education | Drug information - Request Question not been default to relevant or irrelevant | User Miss Suraya request to no not been default to relevant or irrelevant.Purpose due user sometimes not aware question not been default to Irrelevant. | [5 empty] | Selangor
79 | 18477613C | I-PhIS039079118S | 2018-06-11 | Klinik Kesihatan Kalumpang | General Module | Request to add a few info in Maintenance-item batch screen. | En Omar requested to add info below in item batch screen: 1.No Pendaftaran produk(Product registration number) 2.Tarikh Pengilangan(Manufactured date) 3. Jenis Pembekalan(Type of supply eg.: APPL) This info needed when user need to fill up Borang aduan produk berdaftar dengan pihakberkuasa kawalan dadah No Siri Borang : NPRA418.5 | [5 empty] | Selangor
80 | 18479912C | I-PhIS039235218S | 2018-06-12 | Hospital Tengku Ampuan Rahimah | General Module | Change Password - Request no need to change password | Pn Asmahani request no need to change password for phis password. She inform staff have to change password every 3 month and if staff forgot the password, she have to reset back. User also inform unable to renew password to the old one. She find out this only disturb her work since she not see any significant reason to every time to change password. | [5 empty] | Selangor
81 | 18470135C | I-PhIS038727118S | 2018-06-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Profile - Request to add remarks in additional info | User request to add remarks in additional info. User claimed currently when user put remarks, it will not appear in additional info. Kindly refer attachment for reference. Remarks typed when dispensing medicines not appeared at Medication Profile patient. Purpose of request: to notify next staff about specific patient Example: MRN KKE10002500079518 | [5 empty] | Selangor
82 | 18461612C | I-PhIS038209118S | 2018-06-05 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Prescriber - Request to remove column Prescriber Type & Category | En Omar request to remove column Prescriber Type & Category in Prescriber screen due to for both column user already enter in User Profile screen. User informed no need to enter same details in different screen. V1.7.1.6 | [5 empty] | Selangor
83 | 18475812C | I-PhIS038973318S | 2018-06-11 | Hospital Kajang | Pharmacy Inventory | Purchase Order (LP) - Unit price unable to insert more than 2 decimal point | Ms Kelly reported unable to insert unit price more than 2 decimal point. Issue happen since facility upgrade v1716. She inform able to insert unit price more than 2 decimal point for previous version. She seek an advice the solution since if she proceed, the total amount become greater and effect her budget. The status for this PO is still Open. As of now, user will proceed with manual purchasing since she urgent to purchase that item. PO no: PO18001231 Non-drug code: L2120580014 | [5 empty] | Selangor
84 | 18478115C | I-PhIS039121218S | 2018-06-11 | Klinik Kesihatan Ampang | Pharmacy Inventory | Issue (Inter Facility) - Request to exclude indent transaction | User request to exclude indent transaction in issue (inter facility) due to this record can make her confused. User claimed there is same transaction in 3 screen which are indent (inter), issue (inter) and receive (inter). For example, user indent to others facility then she has create indent (inter), but transaction shows in issue (inter). | [5 empty] | Selangor
85 | 18481635C | I-PhIS039357218S | 2018-06-13 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive Item (APPL) - Request to receive online even though user Purchase Order manually | User request to receive online even though user purchase order manual. Example: User purchase order manual through 1GFMAS/EP, then during receiving, user want receive item as online. | [5 empty] | Selangor
86 | 18483213C | I-PhIS039461118S | 2018-06-13 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive Inter Facility - request to show item pending | User request at screen receive inter facility have section show item which is pending or show in status for item issuer not issue. According to user example he indent 10 item but when he receive only 8 item. For balance item he not receive he didnt know either this item will receive or not. He inform he need to check back again at indent screen he made to verify which item already indent. | [5 empty] | Selangor
87 | 18493393C | I-PhIS040187118S | 2018-06-21 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for Modul Desiminate for three stage | User request for Modul Desiminate Inter facility to distribute within three stage.User request the Desiminate should go thru first stage within PKD, second stage within stated and third stage within whole facility in malaysia. | [5 empty] | Selangor
88 | 18493633C | I-PhIS040197118S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive item - Request to allow to key in decimal number for UOM PKU | Pengguna memohon pilihan UOM PKU dibenarkan memasukkan nombor perpulahan. Merujuk kepada perkara di atas, saya ingin merujuk satu contoh yang saya sedang lakukan sekarang iaitu modul 'receive intra fasiliti'. 'Default Setting' untuk UOM ialah 'PKU'. Apabila telah dipilih UOM PKU maka sistem tidak membenarkan kuantiti dimasukkan dengan baki kurang dari 'SATU' Disini saya ingin memohon, bukan hanya untuk modul ini tetapi untuk modul modul lain yang semestinya pihak tuan tahu, apabila UOM PKU maka benarkanlah jika ada baki kurang dari satu maka bolelah juga nilai ini dimasukkan. | [5 empty] | Selangor
89 | 18494293C | I-PhIS040249118S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase Order/Receive From Supplier - Notification Credit Note after complete payment at eP | Encik Omar request got Notification Credit Note at Receive from Supplier & Purchase Order Screen after payment complete at eP. Currently user did not notice either got credit note or not and LPO still appear at receiving screen until payment done by IWP. User also request payment at eP updated directly to IWP without thru payment screen manually. | [5 empty] | Selangor
90 | 18494613C | I-PhIS040269318S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase order(APPL[non-drug]) - Request popup alert information which unit need that item to order | Encik Omar request popup alert information which unit need that item to order. System able to detect stock each unit before proceed purchase order | [5 empty] | Selangor
91 | 18481133C | I-PhIS039319118S | 2018-06-12 | Hospital Tengku Ampuan Jemaah (Sabak Bernam) | Report/Enquiry | PF 5.5(b) - data untuk pre MTAC kaunseling adalah tinggi berbanding dengan PF manual | Pn Tee reported through email to inform that when report generated from PF5.5(b) are showing incorrect statstic for column 'PRE' for MTAC patient. Please refer to excerpt from her email below and attachment given in file upload: untuk menjana laporan untuk indikator 'Bil kaunseling MTAC DM yang dilakukan (Pre*) , melalui cara penjanaan laporan [Menu Report/Enquiry>Pharmacy>Clinical>PF 5.5(b)], didapati data untuk pre adalah tinggi, iaitu 37 berbanding dengan PF manual, iaitu 10 pre kaunseling. didapati data untuk pre yang tinggi daripada PF 5.5(b) adalah kerana sistem PhIS telah mengambil kira mtac visit no untuk data pre kaunseling. untuk makluman pihak puan, walaupun mtac visit no adalah 1 tetapi pesakit tersebut adalah pesakit MTAC lama yang menerima post kaunseling. ini adalah kerana data untuk pesakit MTAC lama tidak dimasukkan ke dalam PhIS untuk tahun sebelumnya. untuk fasility HTAJ, kita akan mengambil kira appointment type 'new' untuk pre kaunseling. | [5 empty] | Selangor
92 | 18494474C | I-PhIS040259118S | 2018-06-22 | Hospital Selayang | Special Drug Request | Special Drug Request - Request repeat patient able key in if patient not existing in special drug | Puan Nurah request repeat patient able key in if patient not existing in special drug request. Patient able to find in patient details. Situation: Patient might be repeat use special drug but not recorded in special drug request. User only recorded as manual Current situation: Special drug request not allow to find repeat/existing patient if not recorded in special drug request | [5 empty] | Selangor
93 | 18499115C | I-PhIS040597218S | 2018-06-26 | Jabatan Kesihatan Negeri Selangor | Special Drug Request | Cadangan mengambil kira bilangan permohonan KPK | Cadangan untuk Pasukan Projek KKM : a) Jika Petunjuk Prestasi Utama (KPI) mengambil kira bilangan permohonan KPK yang dihantar menggunakan PhIS, pandangan saya patut menggunakan bilangan permohonan di screen Special Drug Request kerana semua permohonan yang dibuat tercatit di situ. b) Jika Petunjuk Prestasi Utama (KPI) mengambil kira bilangan permohonan KPK yang diterima oleh Bhgn Formulari KKM menggunakan PhIS, gunakanlah nominator bil permohonan yang diterima oleh Bhgn Formulari KKM dan denominator adalah bil permohonan Manual + PhIS dari fasiliti. | [5 empty] | Selangor
94 | 18476153C | I-PhIS039001118S | 2018-06-11 | Klinik Kesihatan Permaisuri | General Module | Request to extend time for system auto logout | En Wan Sulaiman request to extend time for system auto logout. He inform system will auto logout if he not use less than 10 minutes. User request to extend the time for system logout until 20 minutes. | [5 empty] | Terengganu
95 | 18482333C | I-PhIS039401118S | 2018-06-13 | Klinik Kesihatan Bukit Payong | Pharmacy Inventory | Borang terima barang(BTB) - Request to add column total for price (RM) | En Ruswi request to add column total for price (RM) item in Borang terima barang(BTB). Due to currently no total for item. Refer file upload. 18482333C | [5 empty] | Terengganu
96 | 18484114C | I-PhIS039533118S | 2018-06-14 | Klinik Kesihatan Bukit Payong | Pharmacy Inventory | Receive From Supplier (AP) - Request to show total amount of items purchase | En Ruswi request system shows total amount of items purchase at Received from Supplier screen (receiving details list's section) and also at report KEW.PS 1. Currently, system only show total amount of purchase per items. | [5 empty] | Terengganu
97 | 18464852C | I-PhIS038441218S | 2018-06-06 | Hospital Labuan | Adverse Drug Reaction (ADR) | ADR Report Listing - Memohon mengasingkan data tahun 2017 dan 2018. | Pengguna memohon mengasingkan data tahun 2017 dan 2018. Mewujudkan pemilihan tarikh untuk outcome Untuk makuman, laporan ADR BERNOMBOR 180000152 adalah kes 2017 tetapi dilaporkan pada 2018. jadi data dicapture sebagai laporan 2018. terdapat lagi laporan 2017 yang lain yang dicapture dalam laporan 2018. dilampirkan screenshot ADR listing yang diperlukan | [5 empty] | W. Labuan
98 | 18456353C | I-PhIS037879118S | 2018-06-01 | Hospital Rehabilitasi Cheras | Adverse Drug Reaction (ADR) | ADR Reporting - Naranjo Algorithm missing when select WHO Causality Categories | Pn Yumi explain as below: 1. User click WHO Causality Categories/Naranjo Algorithm hyperlinks 2. Answering all the question at section 'Option 2: Naranjo Algorithm' to get the score 3. Click radio button (e.g 3=(Possible)) at section 'Option 1: WHO Causality Categories' 4. All the answered question at section 'Option 2: Naranjo Algorithm' automatically cleared. | [5 empty] | W. Persekutuan
99 | 18464633C | I-PhIS038425218S | 2018-06-06 | Hospital Rehabilitasi Cheras | Inpatient Pharmacy | Transcribe Order Request to able allocate as half, quater beside 1 | User request to do allocate by set as half, quater beside 1. Purpose: User has acknowledged the request rejected previously but she being advised by the auditor to request again since it affected to quantity stock become not tally. | [5 empty] | W. Persekutuan
100 | 18465873C | I-PhIS038495118S | 2018-06-06 | Hospital Rehabilitasi Cheras | Manufacturing - Extemporaneous | Medication Return - Request drug extemperonous able to return after dispensed | User request to able do medication return for extemperonous item after dispensed. Scenario:- User informed she used Omeprazol Capsule to do extemperonous item Omeprazol Syrup. User already dispense the item but patient didn't come to collect the medication. When she want to do Medication Return, the drug display as Omeprazol Capsule instead of Syrup. User want the Omeprazole Syrup since the medication still valid until 1 month which user want to use it for patient in ward. | [5 empty] | W. Persekutuan
101 | 18458533C | I-PhIS038041118S | 2018-06-04 | Klinik Kesihatan Bandar Tun Razak | Order Management - Web | Record Prescription - Request cursor default on Original Prescription Serial Number | Ms Nandini request cursor default on Original Prescription Serial Number. This is due to current, cursor default on column drug and it take time for user to key in data patient. | [5 empty] | W. Persekutuan
102 | 18472975C | I-PhIS038841118S | 2018-06-08 | Hospital Putrajaya | Pharmacy Inventory | Item Product buffer level - Request to sync changes on default vote code | Ms Sanggeta request to sync changes on default vote code once new vote code is created instead of user need to do manually by changes it self in PHIS. | [5 empty] | W. Persekutuan
103 | 18483576C | I-PhIS039485118S | 2018-06-14 | Pejabat Kesihatan Titiwangsa | Pharmacy Inventory | Purchase Order/Stock Balance by Item - Request to have filter option ALL for Item Purchase Type | User request to have filter option ALL for Item Purchase Type. As user noticed in module Purchase Order and Stock Balance by Item, filter of Item Purchase Type only have APPL, LP and Contract. User suggest to have option as ALL to make generate data more easier. Note: If any module that have function filtering Item Purchase Type besides this two module, kindly add on also. | [5 empty] | W. Persekutuan

## HQ(BPF)
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18472413C | I-PhIS038817218S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools(Medicines Utilisation Report) - Request to add additional tab for Receive Category | Request to add additional tab for Receive Category: drop down 1. Blank/Online Procurement 2. Free of Charge (FOC) 3. Replacement 4. Bonus (PASC) 5. Offline Procurement
2 | 18472474C | I-PhIS038821118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools - Request to add additional column for Receive Category in the Medicines Utilisation Report | Request to add additional column for Receive Category in the Medicines Utilisation Report
3 | 18480713C | I-PhIS039289118S | 2018-06-12 | Bahagian Perkhidmatan Farmasi (BPF) | Data Mining - PhARM | BI Tools-Kemaskini format application usage KPI Indication report | Request to update format for Report of application usage KPI Indication in BI Tools. Refer user attachment at format reference. From Email:- format terbaru bagi laporan application usage KPI Indication untuk dikemaskini dalam BI Tools dengan kadar segera kerana pihak negeri akan mula menghantar pelaporan KPI bagi tempoh Jan-Jun 2018 bermula bulan Julai berdasarkan kepada laporan application usage KPI Indication ini.
4 | 18472293C | I-PhIS038799118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(LP) - Request to add drop down menu for Item Scheme | Request to add drop down menu for Item Scheme: 1. Normal/Non PASC 2. PASC
5 | 18472319C | I-PhIS038803118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(Contract) - Request to add drop down menu for Item Scheme | Request to add drop down menu for Item Scheme: 1. Normal/Non PASC 2. PASC
6 | 18472334C | I-PhIS038805218S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order(AP) - Request to add drop down menu for Item Scheme | To add radio button Offline Procurement and Online Procurement (Mandatory) in AP Purchase Order
7 | 18472341C | I-PhIS038807118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Receive From Supplier - Request to add additional drop down menu for Receive Category | Request to add additional drop down menu for Receive Category: 1. Bonus (PASC) 2. Offline Procurement
8 | 18472355C | I-PhIS038809118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Receive From Supplier - Request to indicate as mandatory fields for Receive Category : Bonus (PASC) | Request to indicate as mandatory fields for Receive Category : Bonus (PASC) 1. Receive Item Against 2. LPO No. 3. Supplier Name 4. Item Group 5. DO No. 6. Goods Received Date & Time
9 | 18477455C | I-PhIS039093118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Pharmacy Inventory | Purchase Order - Request for date range as LPO approved date instead of created date | User request filter date range change to LPO approved date instead of created date. But, user still want the created date remain at listing record.
10 | 18472377C | I-PhIS038811118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Report/Enquiry - Request to add new report for item received including Bonus PASC | Request to add new report for item received including Bonus PASC Menu >>> Report/Enquiry >>> Inventory >>> Procurement >>> YTD Received Item Supplier
11 | 18472632C | I-PhIS038825118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Drug Utilisation Report - Request to add a tab for Indication | Request to add a tab for Indication: - drop down ALL - drop down Specific Indication
12 | 18472653C | I-PhIS038827118S | 2018-06-08 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | Drug Utilisation Report - Request to add information on: Total Number of Patients per Indication | Request to add information on: Total Number of Patients per Indication
13 | 18476872C | I-PhIS039039318S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | PF5.5b - Request to change specification from PhIS and BI Tools | Mohon untuk tukar spesifikasi teknikal bagi PF 5.5(b) dalam PhIS dan BI Tools seperti berikut: Bagi semua kolum pre , mohon guna appointment type=new sebagai formula kepada kolum tersebut bagi menggantikan formula visit number=1
14 | 18477693C | I-PhIS039089118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | CDR Registry - Request to add new field/filtering | User request to add new field/filtering for CDR Registry Future Column and Filtering: 1. Prepare admixture: Yes/No 2. Dispensed status: All 3. Age group: Adult or paediatric At CDR order screen, to identify order for adult or paediatric
15 | 18477732C | I-PhIS039091118S | 2018-06-11 | Bahagian Perkhidmatan Farmasi (BPF) | Report/Enquiry | PN Registry - Request to add new field/filtering | User request to add new field/filtering for PN Registry Future Column and Filtering: 1. Dispensed Status: All

## Johor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18480974C | I-PhIS039307118S | 2018-06-12 | Hospital Pontian | General Module | Unit Catalogue List - Request to add one column for item type in stock available | User request to add one column for item type in stock available. User want to know stock available under which category of item. Kindly refer attachment for reference.
2 | 18482193C | I-PhIS039397118S | 2018-06-13 | Hospital Sultanah Aminah | Manufacturing - IV | IV ad - ROA on label to be in full sentence | User request ROA on label to be in full sentence. ROA on label is in short form eg IVF, IVB as seen which can cause confusion for nurses while doing administration. Possible to label in full sentences eg ' IV Infusion' , 'IV Push' or 'IV Bolus', 'Intraventricular' , 'Intrathecal'. Please add in 'Intraventricular' and 'Intrathecal', only for Vancomycin and Polymycin B.
3 | 18482453C | I-PhIS039409118S | 2018-06-13 | Hospital Sultanah Aminah | Manufacturing - IV | IV Admixture - Preset expiry date and final concentration | In order to prevent medication error, user hope that the expiry date can be preset according to our formulary CIVAS (as attached). Other than that, user's preparations are all done in standardized final concentration as shown in 'Drug Description' in formulary CIVAS (as attached). User are suggesting that once user key in the drug dose, the system can automatically calculate the drug volume and final volume according to this preset final concentration instead of key in the final volume ourselves. This can reduce workload and reduce medication error.
4
5
6
7
8
9
10
11
12

## Kedah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10

## Kelantan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18505494C | I-PhIS041031218S | 2018-06-28 | Hospital Tanah Merah | Drug Information & Consumer Education | Drug Info : Request to allowed for Edit Enquiry Date & Time | User request to allowed for Edit Enquiry Date & Time .
2 | 18480433C | I-PhIS039279118S | 2018-06-12 | Klinik Kesihatan Labok | Order Management - Web | Record Prescription - Request cursor default on Original Prescription Serial Number | Pn Hidayah request cursor default on Original Prescription Serial Number. This is due to current v1716, cursor default on drug and it take time for user to key in data patient.
3 | 18491313C | I-PhIS040039118S | 2018-06-21 | Klinik Kesihatan Kuala Balah | Order Management - Web | Allergy - Request pop up allergy base on active ingredients | Encik Mohd Azwan request pop up allergy base on active ingredients and request to revise back the substance class for active ingredients. Current Situation- Please refer remarks & File Upload : User attachment Additional : Some active ingredients got substances class that not related. Example Amlodipine : As confirmed by user the substances class for Amlodipine suppose only : Calcium channel blocking agents - dihydropyridines Currently in system, got 3 substance appear when select Active Ingredients Amlodipine.
4 | 18465454C | I-PhIS038473318S | 2018-06-06 | Hospital Tumpat | Pharmacy Inventory | Penalty - Expected Delivery Date shows wrong | Pn Fatimah reported Expected Delivery Date shows wrong in penalty screen. She informed eP approved Date and Time is on 14/5 but for Expected Delivery Date state 16/5. User already received stock on 20/5. Delay days shows 4 days. She claim supposedly Expected Delivery Date is 22/5/18. Kindly refer attachment.
5 | 18480533C | I-PhIS039283118S | 2018-06-12 | Klinik Kesihatan Wakaf Bharu | Pharmacy Inventory | issue RIQ - preferred item that requester unit select during indenting not appear | user request supplying unit able to see preferred item that requester unit select during indenting as user inform user need to supply same as user request at preferred item. user inform currently when user checked at RIQ, system not display preferred item that requester unit select during indenting. kindly refer file upload
6 | 18495495C | I-PhIS040343218S | 2018-06-24 | Hospital Tanah Merah | Ward Pharmacy | Ward Pharmacy - Request enhancement for Ward Pharmacy | Miss Lee Wan Nee request able to key in daily review and C&S without need to complete CP2 first. Current Situation : User unable to key in daily review and C&S without complete CP2 first. Related Report : 18495333C
7
8
9
10
11
12

## Melaka
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10
11
12

## N_Sembilan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18494274C | I-PhIS040245118S | 2018-06-22 | Klinik Kesihatan Seremban (TPC) | Data Mining - PhARM | BI Tools [Farmakokinetik (TDM)] - Don't have specific report in BI Tools | Email: Pengguna melaporkan data BI Tools Farmakokinetik (TDM), hanya ada bil kes.Tiada bil jenis ubat dipantau, bil.permohonan yg diterima dan bil. pemantauan kes dijalankan oleh makmal.
2
3
4
5
6
7
8
9

## Pahang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18474034C | I-PhIS038893118S | 2018-06-09 | Klinik Kesihatan Bandar Tun Abdul Razak | General Module | Setting current date in system | User inform date(calender) setting in system PhIS always default to 1 January. So when user would like to set date user would have to scroll the calender untill met the latest date and save. Sometimes if user would like to ammend data in system, system will auto change to 1st January back before able to save. User request to easily set the current date.
2 | 18480793C | I-PhIS039301118S | 2018-06-12 | Hospital Tengku Ampuan Afzan | General Module | Request to add number of counter from 10 to 15 | Puan Elina request to add number of counter from 10 to 15. Number of counter in login page.
3 | 18477656C | I-PhIS039085118S | 2018-06-11 | Hospital Jerantut | Outpatient Pharmacy | Request to add column select check box at screen dispensing | User request to add column select check box at screen dispensing to allow user select few patient for dispensing in one time. user inform if there have 1000 record of patient, user have to enter one by one to clear patient name at screen dispensing.
4 | 18471335C | I-PhIS038747118S | 2018-06-08 | Hospital Kuala Lipis | Pharmacy Inventory | Returned Item - Request able to return item to inter facility | Miss Tan request have a module to able to return item to inter facility.
5 | 18456953C | I-PhIS037925118S | 2018-06-01 | Hospital Tengku Ampuan Afzan | Ward Pharmacy | Ward Pharmacy(CP2) - Request to change name for transcribe by | En Nasri request to change name for transcribe by to created by at screen ward pharmacy CP 2 and CP1. Due to currently system show who login the system. Refer file upload. step by user : clinical summary>click CP1/CP2>click link at CP1/CP2
6
7
8
9
10

## Perak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18462152C | I-PhIS038241118S | 2018-06-05 | Hospital Sg Siput | Adverse Drug Reaction (ADR) | ADR Reporting (Drug Details) - Request to rename Total daily dosage given | Ms Fong request to rename 'Total daily dosage given' to 'Dosage given' due to it really confusing to user. Situation: Supply drug to patient for frequency TDS (three times a day) with dosage 275 mg. User key in Total daily dosage given as 825 mg which is 275 mg*3. However when print the reporting, it supposed means user to key in 275 mg only (not total).
2 | 18498854C | I-PhIS040563318S | 2018-06-26 | Hospital Seri Manjung | Data Mining - PhARM | Bi Tools - Request able to filter data by range of month for all report in Bi Tools | User request able to filter report by range of month. Example : Jan 2018 until June 2018 Currently only able to filter by monthly or all.
3 | 18466213C | I-PhIS038511218S | 2018-06-06 | Hospital Seri Manjung | General Module | Order Routing - Request to enable set more than 1 unit | Pn Zuraidah inform that during working hours, satelite pharmacy is under Inpatient. But after working hours, satelite pharmacy can be both inpatient and outpatient (ED). However Order Routing screen only allow user to select one unit only.
4 | 18471833C | I-PhIS038777118S | 2018-06-08 | Hospital Bahagia Ulu Kinta | Inpatient Pharmacy | Inpatient drug label - Request to know the purpose of box date supply | En Hilmi request to know the purpose/function of box date supply at inpatient drug label. As per inform by user, he want to know the right purpose by module owner since facility don't use the box. If follow the 'Carta Ubat' at facility that they can sign or check who transcribe the drug and only have 1 box. User query why have 7 box of date supply in the inpatient drug label. User request to remove the box of date supply and make all the details in drug label become bigger IF APPLICABLE. Related report: 16075640C, 17156176C Updated: User request to remove the box date supply since it is not necessary at his hospital and request to make other details font become bigger.
5 | 18463596C | I-PhIS038345118S | 2018-06-05 | Klinik Kesihatan Manong | Order Management - Web | Record Prescription - Request to display confirmation popup | Saya ingin mengemukan beberapa cadangan penambahbaikan bagi versi berikutnya. A. Mencadangkan diwujudkan semula conformation pop up semasa Medication Order setelah menekan butang Conform. Hal ini bagi membolehkan ubat yang tertinggal atau tersilap order boleh dibuat pembetulan.
6 | 18466673C | I-PhIS038537118S | 2018-06-06 | Hospital Raja Permaisuri Bainun | Order Management - Web | Request to have print prescription button/link at Medication Profile page | Request to have print prescription button/link at Medication Profile. Sometimes doctor may not print immediately after order but they can print PS later when the visit patient medication profile.
7 | 18503813C | I-PhIS040913118S | 2018-06-27 | Klinik Kesihatan Buntong | Order Management - Web | Medication Order (SPUB) - Request to allow multiple prescription with same patient | User request to allow multiple prescription with same patient without proceed until verification screen. Currently, user need to verify the prescription in verification screen before user transcribe new offline SPUB from others facility. User claimed one patient can have many prescription from different facility. This purpose is to make sure user not confused to check one by one screen when user has complete until verification.
8 | 18456793C | I-PhIS037915118S | 2018-06-01 | Hospital Tapah | Outpatient Pharmacy | Preparation - Extemporaneous - Request to auto allocate X-Tempt | Based on report no: 18454873C. User reported there is no item batch and expiry date for X-Tempt item. User was advise to do Issue-Consumption to deduct stock from Unit Catalog List to tally stock. Therefore, user request to auto allocate X-Tempt item.
9 | 18471496C | I-PhIS038751118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | SPUB - Request proceed offline SPUB without proceed online SPUB | User request to allow proceed offline SPUB without proceed with online SPUB to confirm order. Currently he unable to add item at Medication Order . User do request since he refuse to proceed online SPUB before proceed Offline SPUB. User claimed patient came to facility not to collect Online SPUB.
10 | 18471535C | I-PhIS038753118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | Indent SPUB - request to allow indent for item standard and non standard | User request to allow indent for all item standard and non standard. Currently user able to indent for item non standard only.
11 | 18471578C | I-PhIS038755118S | 2018-06-08 | Klinik Kesihatan Bidor | Outpatient Pharmacy | Record Prescription - Request cursor mouse auto appear at empty column | User request cursor mouse auto appear at empty column for screen record prescription, so that pharmacist not required to move the mouse cursor to the empty column when type patient ID . Currently cursor auto appear at Select Registration Patient All not at empty column.
12 | 18485213C | I-PhIS039623518S | 2018-06-18 | Hospital Tapah | Pharmacy Inventory | report / inquiry -request to add new column search by drug/ non code at item movement | user request to add new column search by drug/ non code at screen item movement to make user select drug/non drug code before select item code.as current version user have to select specific item code for same item.
13 | 18490073C | I-PhIS039959118S | 2018-06-20 | Hospital Sg Siput | Pharmacy Inventory | Stock transfer - Able to add more than 1 item | User Miss Tan request able to add more than 1 item when do stock transfer.Purpose user request due to user need to create more than 1 transaction if user want to stock transfer more than 1 item.
14 | 18501933C | I-PhIS040791118S | 2018-06-27 | Hospital Teluk Intan | Pharmacy Inventory | KEWPS 10 - Request for amend SKU or PKU column | En Amir request amend SKU or PKU column on KEWPS10 beside Issue Quantity column. So that user will be not confused either he will issue in SKU or PKU quantity.
15
16
17
18
19
20

## P.Pinang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18458974C | I-PhIS038069218S | 2018-06-04 | Klinik Kesihatan Kepala Batas | Order Management - Web | Medication order - Request to move search listing | Cik Farah request search listing do not cover the Original Prescriber Name column during typing . Refer file upload.
2 | 18483134C | I-PhIS039455318S | 2018-06-13 | Hospital Bukit Mertajam | Order Management - Web | Record Prescription (Med Order) - Request starting cursor default at queue no | Ms Tan request starting cursor default at queue no. User inform for current system, cursor default at drug. User claim they have to key in all mandatory field before proceed. If starting cursor start from queue no, supposedly there is no left field required to fill in.
3 | 18483152C | I-PhIS039455418S | 2018-06-13 | Hospital Bukit Mertajam | Order Management - Web | Record Prescription (Med Order) - Request to extend running time of drug selection | Ms Tan request to extend running time of drug selection. She inform when she select drug to transcribing, for example user choose simvastatin, system appear selection different strength but when user try to use arrow down at keyboard, the running time is too fast. Sometimes, user want to select 40 mg but system auto select 20 mg after user press down arrow keyboard. She inform pharmacist usually use keyboard and not always use mouse for fast transcribing.
4 | 18483633C | I-PhIS039499118S | 2018-06-14 | Hospital Seberang Jaya | Pharmacy Inventory | Task List-Unable to reject status pending to receive | User reported there has transaction receive internal with status pending to receive exist in task list. When user double click the transaction there has no reject button. User want to reject the transaction due main store did not receive the physical item. RT17000021 RT17000024 RT18000003 RT18000014
5
6
7
8
9
10
11
12

## Perlis
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18486433C | I-PhIS039697118S | 2018-06-18 | Hospital Tuanku Fauziah | Report/Enquiry | report/inquiry - request to add column Total number of item dispensed at Prescription Management IP | user request at screen report/ inquiry - Inpatient Prescription to show report for Total number of item dispensed as user inform user need to collect data that user already dispense for each unit
2
3
4
5
6
7
8
9
10

## Sabah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18484673C | I-PhIS039581118S | 2018-06-16 | Hospital Beluran | Adverse Drug Reaction (ADR) | NPRA- Request to have Notification Message once NPRA Send | Mr.Quah request to have Notification Message once NPRA Send. This is due user did not know if NPRA has been send or not.
2 | 18507853C | I-PhIS041187118S | 2018-06-29 | Hospital Queen Elizabeth | MTAC | Request to allow selected users to view the MTAC RVD | User Miss Melinda request to allow only certain users to use the MTAC RVD module in PhIS to maintain patient's privacy and confidentiality.
3 | 18493733C | I-PhIS040205118S | 2018-06-22 | Hospital Dutchess of Kent | Order Management - Web | Record Prescription - Request to add brand name column at allergy details | Ms Lam request to add new column as 'Brand name' at allergy details. She inform for example patient have allergy to a Specific Brand only, user had key in the specific brand that patient allergy. After that when user want to view details back, the brand is not appear. User also unable to double click to view the allergy details. Example: Record prescription > search patient IC > click down arrow at allergy > click details > brand name not appear. User inform it difficult if patient admit ward and want to prescribe drug to that patient. If pharmacist unable to see correct details, they don't give the drug to patient at all. Besides patient just allergy to specific brand only.
4 | 18501912C | I-PhIS040793118S | 2018-06-27 | Klinik Kesihatan Suan Lamba | Order Management - Web | Transcribe order - Request to proceed verified,prepare and dispense without closed page | Mr Joey request to proceed verified,prepare and dispense without closed page. Current system : After click verify page close and user need to click module preparation to proceed other screen. User need to use more time to proceed dispense and also the waiting time is higher. User inform facility only have 1 pc and user not have many times to do many step.
5 | 18464133C | I-PhIS038383218S | 2018-06-06 | Hospital Tawau | Pharmacy Inventory | Purchase Order (Contract) - request to allow eP approved even delivery due date already past | User reported unable to proceed eP approved due to delivery due date already past. She inform if want to proceed eP approved need to adjust the date for delivery. According to user if she adjust the date, it will affect the delivery lead period. Then it also effect for penalty. Therefore she request to allow eP approved even delivery due date already past.
6 | 18489893C | I-PhIS039945118S | 2018-06-20 | Cawangan Farmasi Logistik Negeri | Pharmacy Inventory | Issuing - Request system not auto issue for Purchase Order : Quotation and Request type: Indent | En Humam reported when proceed receiving for LP Purchase Order : Quotation and Request Type : Indent system will auto issuing. Therefore he request system not auto issuing when proceed receiving by same person. According to user in his facility procedure there have their own person in change for receiving and issuing.
7 | 18495753C | I-PhIS040369118S | 2018-06-25 | Hospital Beluran | Pharmacy Inventory | Label prepacking - Request to center the label | Mr Quah request to center the label when print due currently label not center and have more space empty. Refer attachment.
8 | 18505313C | I-PhIS041021118S | 2018-06-28 | Hospital Queen Elizabeth | Pharmacy Inventory | Purchase order - Request to add in the packaging description when search item | Mdm Tee Swee Pin request to add in the packaging description when search item. Email user: Is it possible to add in the packaging description in item purchase order for purchase order like the one product search in quotation? The problem user are facing are: need to guest packaging (Kindly refer attachment)
9 | 18475853C | I-PhIS038975218S | 2018-06-11 | Hospital Dutchess of Kent | Report/Enquiry | Drug Utilisation - Request to add new column - Identification Card | Ms Tham request to add new column (identification card) in Drug Utilization report. It will easier for user to filter or search patient using IC number.
10 | 18491694C | I-PhIS040063118S | 2018-06-21 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Stock Balance By Drug/Non-Drug - Add column last transaction issue out | User Mr Human request to add column last transaction issue out for the item.Purpose user request due user unable to find item that not been issue out more than 6 month.If user search using module slow processing,only item have slow moving within 6 month.
11 | 18498233C | I-PhIS040517118S | 2018-06-25 | Hospital Dutchess of Kent | Report/Enquiry | Extemporaneous Registry - Request to add patient name and IC No | Ms Tham request to add patient name and patient IC No on extemporaneous registry report.
12 | 18488052C | I-PhIS039813118S | 2018-06-19 | Cawangan Farmasi Logistik Negeri | Special Drug Request | Special Drug Request - Unable to Recomended request | User Ms Pamela reported she unable to recommend any Special Drug Request due to when user click on Recommend button, nothing happen. The status still appear new request. Facility Request No.: PKDSB130002/2018 User ID: 830225125588 V1.7.1.6
13 | 18503293C | I-PhIS040879118S | 2018-06-27 | Hospital Tawau | Special Drug Request | Special Drug Request - Cannot enter Strength in Decimal Value | Ms Diana informed user want to enter strength in decimal value since strength this drug in decimal but system shows You must specify a number . User informed it should be strength in value decimal due to not accurate if user round number to into Even Number. Drug: Sodium Dihydrogen Phosphate Dihydrate & Disodium Phospate Dodecahydrate Strength: 24.4, 10.8
14 | 18477553C | I-PhIS039075318S | 2018-06-11 | Hospital Beaufort | Ward Pharmacy | Ward Pharmacy CP2 - CP1 - Request to add new column for Pharmacist recommendation | User request to add column Pharmacist note for pharmacist able to remark general recommendation. Refer user attachment as further reference.
15
16
17
18

## Sarawak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18491753C | I-PhIS040065218S | 2018-06-21 | Hospital Umum Sarawak | Adverse Drug Reaction (ADR) | ADR Reporting (Drug Details) - Request to rename Total daily dosage given | Miss Phang Lie Jin request to rename 'Total daily dosage given' to 'Dose' due to it really confusing to user. Situation: Supply drug to patient for frequency TDS (three times a day) with dosage 500 mg. User key in Total daily dosage given as 1500 mg which is 500 mg*3. However when print the reporting, it supposed means user to key in 500 only (not total).
2 | 18501438C | I-PhIS040751318S | 2018-06-26 | Hospital Sibu | Data Mining - PhARM | BI Tools - No Report to be compare with PhIS | Mr Ting Su Hock reported no report in BI Tools to be compare with PhIS. He inform he generate Purchase Order by Drug/Item report in PhIS. He notice that BI Tools has no report that enable him to compare with.
3 | 18505933C | I-PhIS041057118S | 2018-06-28 | Makmal Ubat dan Stor Bahagian Sibu | General Module | Change Password - Request to extend password expiry validity | Mr Francis request to extend password expiry date due to he inform have to change the password always. She inform it can disturb their work if every time popup appear to change password. Currently maximum password expiry validity is only 90 days. He request if can extend the password expiry date as 2 years in phis.
4 | 18465633C | I-PhIS038483118S | 2018-06-06 | Hospital Miri | Pharmacy Inventory | REQUEST TO ENABLE USER ABLE TO INDENT SPUB TO LOCATION BESIDE OUTPATIENT | Email: User reported current PHIS system only enable user to indent SPUB items to Outpatient Pharmacy. Actually, some SPUB is refer out by satellite pharmacy, and means the indent need send to satellite pharmacy because satellite pharmacy will supply the items to facility request the items. Temporarily all indent and supply process manually without go through PHIS.
5 | 18493532C | I-PhIS040193218S | 2018-06-22 | Hospital Saratok | Pharmacy Inventory | RIQ (Intra) - Request able to change supplying unit after save | Ms Karen request able to change supplying unit after save transaction. Example situation: User must select supplying unit as IPD nut wrongly select as Substore unit. She inform the transaction already save. User unable to change back the supplying unit to the correct unit. Also there is no reject button to reject the transaction.
6 | 18467773C | I-PhIS038611118S | 2018-06-07 | Hospital Umum Sarawak | Report/Enquiry | Generator Elution Record - Request to change last 6 digit Elution Batch No. to as Measured Date | User request to change last 6 digit of Elution Batch No. to as Measured Date instead of Date. Refer user attachment as reference.
7 | 18499122C | I-PhIS040593118S | 2018-06-26 | Hospital Kanowit | Report/Enquiry | PF 6.3(b) - Report not tally | Ms Ngo reported that PF 6.3(b) not tally. She informed that she had dispensed prescription for 1 patient today (26/6/2018). When she check on Prescription Management IP have recorded 1 data for that patient. She check on Inpatient Prescription report also have recorded 1 data for that patient on column No of Rx Generated. But when she check on PF 6.3(b), shows 0 record for that patient. IC No: 700906135778
8 | 18499154C | I-PhIS040597418S | 2018-06-26 | Hospital Kanowit | Report/Enquiry | Inpatient Prescription - Report not tally | Ms Ngo reported that report for Prescription Management IP not tally. She mention she have dispensed 2 prescription today (26/6/2018). Total drug for both prescription is 12. But when she check on No of Rx Generated column shows as 12, while on No of Rx Dispensed also shows as 12. She mention supposedly both column shows 2 prescription only even the total number of item prescribed is 12. Ms Ngo also inform on Prescription Received column at PF 6.3(b) also shows as 12. MRN No: 1) 780527135500 - 4 drug order for 1 prescription 2) 620119135170 - 8 drug order for 1 prescription
9 | 18504953C | I-PhIS040997118S | 2018-06-28 | Hospital Kanowit | Report/Enquiry | Inpatient Prescription - Request to follow report PF 6.1 | Ms Ngo request for Inpatient Prescription report for number of supplied for daily follow the calculation UDS on PF 6.1 report. Kindly refer calculation UDS provided by Ms Ngo.
10
11
12
13
14
15
16
17
18

## Selangor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18459454C | I-PhIS038097118S | 2018-06-04 | Jabatan Kesihatan Negeri Selangor | Data Mining - PhARM | BI Tools - Inventory not follow Manual KPI 2018 | Puan Anis reported Inventory not follow Manual KPI 2018. According to Manual KPI 2018 from Program Perkhidmatan Farmasi , the column No. of item issued should be Bil Pesanan Kerajaan (LPO) dikeluarkan . Kindly refer attachment
2 | 18464554C | I-PhIS038417118S | 2018-06-06 | Jabatan Kesihatan Negeri Selangor | Data Mining - PhARM | Change Request untuk BI Tools | Cadangan penambaikan ini telah dibuat dalam Mesyuarat Teknikal Farmasi Informatik pada 1-2 Mac yang lalu. Tak pasti samada dah masuk jadi CR atau tidak. Saya lihat tiada perubahan as of today jadi saya log cadangan ini semula. 1. KPI Indication Report dalam BI Tools - mohon tambahkan pilihan bulan untuk data dijana (rujuk lampiran) 2. Laporan PF 5.1 dalam BI Tools - mohon tambahkan pilihan bulan untuk data dijana (rujuk lampiran)
3 | 18503254C | I-PhIS040875118S | 2018-06-27 | Hospital Kuala Kubu Bharu | Drug Information & Consumer Education | Drug information - Request Question not been default to relevant or irrelevant | User Miss Suraya request to no not been default to relevant or irrelevant.Purpose due user sometimes not aware question not been default to Irrelevant.
4 | 18477613C | I-PhIS039079118S | 2018-06-11 | Klinik Kesihatan Kalumpang | General Module | Request to add a few info in Maintenance-item batch screen. | En Omar requested to add info below in item batch screen: 1.No Pendaftaran produk(Product registration number) 2.Tarikh Pengilangan(Manufactured date) 3. Jenis Pembekalan(Type of supply eg.: APPL) This info needed when user need to fill up Borang aduan produk berdaftar dengan pihakberkuasa kawalan dadah No Siri Borang : NPRA418.5
5 | 18479912C | I-PhIS039235218S | 2018-06-12 | Hospital Tengku Ampuan Rahimah | General Module | Change Password - Request no need to change password | Pn Asmahani request no need to change password for phis password. She inform staff have to change password every 3 month and if staff forgot the password, she have to reset back. User also inform unable to renew password to the old one. She find out this only disturb her work since she not see any significant reason to every time to change password.
6 | 18470135C | I-PhIS038727118S | 2018-06-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Profile - Request to add remarks in additional info | User request to add remarks in additional info. User claimed currently when user put remarks, it will not appear in additional info. Kindly refer attachment for reference. Remarks typed when dispensing medicines not appeared at Medication Profile patient. Purpose of request: to notify next staff about specific patient Example: MRN KKE10002500079518
7 | 18461612C | I-PhIS038209118S | 2018-06-05 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Prescriber - Request to remove column Prescriber Type & Category | En Omar request to remove column Prescriber Type & Category in Prescriber screen due to for both column user already enter in User Profile screen. User informed no need to enter same details in different screen. V1.7.1.6
8 | 18475812C | I-PhIS038973318S | 2018-06-11 | Hospital Kajang | Pharmacy Inventory | Purchase Order (LP) - Unit price unable to insert more than 2 decimal point | Ms Kelly reported unable to insert unit price more than 2 decimal point. Issue happen since facility upgrade v1716. She inform able to insert unit price more than 2 decimal point for previous version. She seek an advice the solution since if she proceed, the total amount become greater and effect her budget. The status for this PO is still Open. As of now, user will proceed with manual purchasing since she urgent to purchase that item. PO no: PO18001231 Non-drug code: L2120580014
9 | 18478115C | I-PhIS039121218S | 2018-06-11 | Klinik Kesihatan Ampang | Pharmacy Inventory | Issue (Inter Facility) - Request to exclude indent transaction | User request to exclude indent transaction in issue (inter facility) due to this record can make her confused. User claimed there is same transaction in 3 screen which are indent (inter), issue (inter) and receive (inter). For example, user indent to others facility then she has create indent (inter), but transaction shows in issue (inter).
10 | 18481635C | I-PhIS039357218S | 2018-06-13 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive Item (APPL) - Request to receive online even though user Purchase Order manually | User request to receive online even though user purchase order manual. Example: User purchase order manual through 1GFMAS/EP, then during receiving, user want receive item as online.
11 | 18483213C | I-PhIS039461118S | 2018-06-13 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive Inter Facility - request to show item pending | User request at screen receive inter facility have section show item which is pending or show in status for item issuer not issue. According to user example he indent 10 item but when he receive only 8 item. For balance item he not receive he didnt know either this item will receive or not. He inform he need to check back again at indent screen he made to verify which item already indent.
12 | 18493393C | I-PhIS040187118S | 2018-06-21 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for Modul Desiminate for three stage | User request for Modul Desiminate Inter facility to distribute within three stage.User request the Desiminate should go thru first stage within PKD, second stage within stated and third stage within whole facility in malaysia.
13 | 18493633C | I-PhIS040197118S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive item - Request to allow to key in decimal number for UOM PKU | Pengguna memohon pilihan UOM PKU dibenarkan memasukkan nombor perpulahan. Merujuk kepada perkara di atas, saya ingin merujuk satu contoh yang saya sedang lakukan sekarang iaitu modul 'receive intra fasiliti'. 'Default Setting' untuk UOM ialah 'PKU'. Apabila telah dipilih UOM PKU maka sistem tidak membenarkan kuantiti dimasukkan dengan baki kurang dari 'SATU' Disini saya ingin memohon, bukan hanya untuk modul ini tetapi untuk modul modul lain yang semestinya pihak tuan tahu, apabila UOM PKU maka benarkanlah jika ada baki kurang dari satu maka bolelah juga nilai ini dimasukkan.
14 | 18494293C | I-PhIS040249118S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase Order/Receive From Supplier - Notification Credit Note after complete payment at eP | Encik Omar request got Notification Credit Note at Receive from Supplier & Purchase Order Screen after payment complete at eP. Currently user did not notice either got credit note or not and LPO still appear at receiving screen until payment done by IWP. User also request payment at eP updated directly to IWP without thru payment screen manually.
15 | 18494613C | I-PhIS040269318S | 2018-06-22 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase order(APPL[non-drug]) - Request popup alert information which unit need that item to order | Encik Omar request popup alert information which unit need that item to order. System able to detect stock each unit before proceed purchase order
16 | 18481133C | I-PhIS039319118S | 2018-06-12 | Hospital Tengku Ampuan Jemaah (Sabak Bernam) | Report/Enquiry | PF 5.5(b) - data untuk pre MTAC kaunseling adalah tinggi berbanding dengan PF manual | Pn Tee reported through email to inform that when report generated from PF5.5(b) are showing incorrect statstic for column 'PRE' for MTAC patient. Please refer to excerpt from her email below and attachment given in file upload: untuk menjana laporan untuk indikator 'Bil kaunseling MTAC DM yang dilakukan (Pre*) , melalui cara penjanaan laporan [Menu Report/Enquiry>Pharmacy>Clinical>PF 5.5(b)], didapati data untuk pre adalah tinggi, iaitu 37 berbanding dengan PF manual, iaitu 10 pre kaunseling. didapati data untuk pre yang tinggi daripada PF 5.5(b) adalah kerana sistem PhIS telah mengambil kira mtac visit no untuk data pre kaunseling. untuk makluman pihak puan, walaupun mtac visit no adalah 1 tetapi pesakit tersebut adalah pesakit MTAC lama yang menerima post kaunseling. ini adalah kerana data untuk pesakit MTAC lama tidak dimasukkan ke dalam PhIS untuk tahun sebelumnya. untuk fasility HTAJ, kita akan mengambil kira appointment type 'new' untuk pre kaunseling.
17 | 18494474C | I-PhIS040259118S | 2018-06-22 | Hospital Selayang | Special Drug Request | Special Drug Request - Request repeat patient able key in if patient not existing in special drug | Puan Nurah request repeat patient able key in if patient not existing in special drug request. Patient able to find in patient details. Situation: Patient might be repeat use special drug but not recorded in special drug request. User only recorded as manual Current situation: Special drug request not allow to find repeat/existing patient if not recorded in special drug request
18 | 18499115C | I-PhIS040597218S | 2018-06-26 | Jabatan Kesihatan Negeri Selangor | Special Drug Request | Cadangan mengambil kira bilangan permohonan KPK | Cadangan untuk Pasukan Projek KKM : a) Jika Petunjuk Prestasi Utama (KPI) mengambil kira bilangan permohonan KPK yang dihantar menggunakan PhIS, pandangan saya patut menggunakan bilangan permohonan di screen Special Drug Request kerana semua permohonan yang dibuat tercatit di situ. b) Jika Petunjuk Prestasi Utama (KPI) mengambil kira bilangan permohonan KPK yang diterima oleh Bhgn Formulari KKM menggunakan PhIS, gunakanlah nominator bil permohonan yang diterima oleh Bhgn Formulari KKM dan denominator adalah bil permohonan Manual + PhIS dari fasiliti.
19
20
21
22
23
24

## Terengganu
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18476153C | I-PhIS039001118S | 2018-06-11 | Klinik Kesihatan Permaisuri | General Module | Request to extend time for system auto logout | En Wan Sulaiman request to extend time for system auto logout. He inform system will auto logout if he not use less than 10 minutes. User request to extend the time for system logout until 20 minutes.
2 | 18482333C | I-PhIS039401118S | 2018-06-13 | Klinik Kesihatan Bukit Payong | Pharmacy Inventory | Borang terima barang(BTB) - Request to add column total for price (RM) | En Ruswi request to add column total for price (RM) item in Borang terima barang(BTB). Due to currently no total for item. Refer file upload. 18482333C
3 | 18484114C | I-PhIS039533118S | 2018-06-14 | Klinik Kesihatan Bukit Payong | Pharmacy Inventory | Receive From Supplier (AP) - Request to show total amount of items purchase | En Ruswi request system shows total amount of items purchase at Received from Supplier screen (receiving details list's section) and also at report KEW.PS 1. Currently, system only show total amount of purchase per items.
4
5
6

## HKL
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18456493C | I-PhIS037889118S | 2018-06-01 | Hospital Kuala Lumpur | Inpatient Pharmacy | Fill list - Request to remove Refresh Option | User request to remove Message stock has been modified as he need to click refresh button. Once click refresh button he need to start all over again.
2 | 18484295C | I-PhIS039551218S | 2018-06-14 | Hospital Kuala Lumpur | Report/Enquiry | Drug Supply Registry - Request on Discharge Referred | Miss Chia request on discharge referred 1) Sent To need to auto popup according facility on referred facility that user choose 2) Able to add multiple drug name at prescription details. Current situation, if one patient have two drugs need to do one by one drug supply transaction. 3) Cost need to auto calculate base on drug price in PhIS
3 | 18486373C | I-PhIS039693118S | 2018-06-18 | Hospital Kuala Lumpur | Report/Enquiry | report / inquiry - request to add new column Counselling by unit at Medication Counselling | user request to add new column Counselling by unit at Medication Counselling Reporting specific by unit that given the Medication Counselling as user inform at HKL few unit will give Medication Counselling to patient as user unable to identify which unit give the Medication Counselling.
4
5
6
7
8
9
10
11
12

## WLabuan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18464852C | I-PhIS038441218S | 2018-06-06 | Hospital Labuan | Adverse Drug Reaction (ADR) | ADR Report Listing - Memohon mengasingkan data tahun 2017 dan 2018. | Pengguna memohon mengasingkan data tahun 2017 dan 2018. Mewujudkan pemilihan tarikh untuk outcome Untuk makuman, laporan ADR BERNOMBOR 180000152 adalah kes 2017 tetapi dilaporkan pada 2018. jadi data dicapture sebagai laporan 2018. terdapat lagi laporan 2017 yang lain yang dicapture dalam laporan 2018. dilampirkan screenshot ADR listing yang diperlukan
2
3
4
5
6

## WP
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18456353C | I-PhIS037879118S | 2018-06-01 | Hospital Rehabilitasi Cheras | Adverse Drug Reaction (ADR) | ADR Reporting - Naranjo Algorithm missing when select WHO Causality Categories | Pn Yumi explain as below: 1. User click WHO Causality Categories/Naranjo Algorithm hyperlinks 2. Answering all the question at section 'Option 2: Naranjo Algorithm' to get the score 3. Click radio button (e.g 3=(Possible)) at section 'Option 1: WHO Causality Categories' 4. All the answered question at section 'Option 2: Naranjo Algorithm' automatically cleared.
2 | 18464633C | I-PhIS038425218S | 2018-06-06 | Hospital Rehabilitasi Cheras | Inpatient Pharmacy | Transcribe Order Request to able allocate as half, quater beside 1 | User request to do allocate by set as half, quater beside 1. Purpose: User has acknowledged the request rejected previously but she being advised by the auditor to request again since it affected to quantity stock become not tally.
3 | 18465873C | I-PhIS038495118S | 2018-06-06 | Hospital Rehabilitasi Cheras | Manufacturing - Extemporaneous | Medication Return - Request drug extemperonous able to return after dispensed | User request to able do medication return for extemperonous item after dispensed. Scenario:- User informed she used Omeprazol Capsule to do extemperonous item Omeprazol Syrup. User already dispense the item but patient didn't come to collect the medication. When she want to do Medication Return, the drug display as Omeprazol Capsule instead of Syrup. User want the Omeprazole Syrup since the medication still valid until 1 month which user want to use it for patient in ward.
4 | 18458533C | I-PhIS038041118S | 2018-06-04 | Klinik Kesihatan Bandar Tun Razak | Order Management - Web | Record Prescription - Request cursor default on Original Prescription Serial Number | Ms Nandini request cursor default on Original Prescription Serial Number. This is due to current, cursor default on column drug and it take time for user to key in data patient.
5 | 18472975C | I-PhIS038841118S | 2018-06-08 | Hospital Putrajaya | Pharmacy Inventory | Item Product buffer level - Request to sync changes on default vote code | Ms Sanggeta request to sync changes on default vote code once new vote code is created instead of user need to do manually by changes it self in PHIS.
6 | 18483576C | I-PhIS039485118S | 2018-06-14 | Pejabat Kesihatan Titiwangsa | Pharmacy Inventory | Purchase Order/Stock Balance by Item - Request to have filter option ALL for Item Purchase Type | User request to have filter option ALL for Item Purchase Type. As user noticed in module Purchase Order and Stock Balance by Item, filter of Item Purchase Type only have APPL, LP and Contract. User suggest to have option as ALL to make generate data more easier. Note: If any module that have function filtering Item Purchase Type besides this two module, kindly add on also.

## Institut
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10