## Summ_Module
Summary by Status
No | Issue Type | Request
1 | Pharmacy Inventory | 31
2 | Patient Management | 1
3 | Order Management - Web | 8
4 | Order Management - Mobile | 0
5 | Special Drug Request | 1
6 | Outpatient Pharmacy | 8
7 | Inpatient Pharmacy | 2
8 | MAR - Web | 0
9 | MAR - Mobile | 0
10 | MTAC | 2
11 | Ward Pharmacy | 1
12 | Ward Pharmacy - Mobile | 0
13 | Medication Counseling | 0
14 | Adverse Drug Reaction (ADR) | 6
15 | Clinical Pharmacokinetic Services (CPS) & TDM | 1
16 | Drug Information & Consumer Education | 5
17 | PhIS Portal | 1
18 | Manufacturing - CDR | 0
19 | Manufacturing - Extemporaneous | 1
20 | Manufacturing - Galenical | 0
21 | Manufacturing - IV | 0
22 | Manufacturing - PN | 0
23 | Manufacturing - Radiopharmaceutical | 1
24 | Data Mining - PhARM | 0
25 | Report/Enquiry | 19
26 | IWP | 0
27 | General Module | 8
28 | BCP | 0
| Total | 96

## Summ_State
No | Issue Type | Request
1 | BPF | 1
2 | Johor | 7
3 | Kedah | 3
4 | Kelantan | 5
5 | Melaka | 3
6 | Pahang | 2
7 | Perak | 11
8 | Pulau Pinang | 18
9 | Sabah | 5
10 | Sarawak | 6
11 | Selangor | 28
12 | Terengganu | 0
13 | W. Persekutuan | 0
14 | Negeri Sembilan | 3
15 | Perlis | 0
16 | HKL | 4
17 | W. Labuan | 0
18 | Institut | 0
| Total | 96

## Total
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks | State
1 | 18586018C | I-PhIS046589618S | 2018-11-05 | Bahagian Perkhidmatan Farmasi (BPF) | PhIS Portal | To create new section for PM Report | To create new section for PM Report to upload PM report by facility (Sample Attached) | [5 empty] | BPF
2 | 18592306C | I-PhIS047119618S | 2018-11-23 | Hospital Kuala Lumpur | Manufacturing - Radiopharmaceutical | Stock Verification(Radiopharma): Request to add column to lock data | Miss Rachel request request to add column to lock data once activity has been measured and received for the first time, and then for subsequent updates to be listed as a list and recorded, instead of overwriting the data. Please see as attached. This request has been discussed with SA Ilya Syarah | [5 empty] | HKL
3 | 18591408C | I-PhIS047051118S | 2018-11-21 | Hospital Kuala Lumpur | Order Management - Web | Record prescription - Patient name wrongly appear after enter IC patient no. | User Ms Yong reported patient name auto appear with incorrect patient details after user enter correct IC no. at screen Record prescription. User informed she already enter IC No.: 020326102188. But system auto appear for patient for IC No.: 921024105680. User realize patient name wrongly appear after she confirm order. User informed issue happen intermittently. Date Happen: 7/11/2018 (10.35am) Patient IC No.: 020326102188 Wrong patient IC No.: 921024105680 | [5 empty] | HKL
4 | 18586816C | I-PhIS046677518S | 2018-11-07 | Hospital Kuala Lumpur | Report/Enquiry | MTAC Registry - Request to provide Patient name | Ms Ho Chia Chia request to provide detail of patient name. She informed the patient name column is also important. | [5 empty] | HKL
5 | 18586821C | I-PhIS046677718S | 2018-11-07 | Hospital Kuala Lumpur | Report/Enquiry | MTAC Registry - Request to provide total MTAC Record after print | Ms Ho Chia Chia request to provide total MTAC Record after print. User informed the total record is needed when print. | [5 empty] | HKL
6 | 18588302C | I-PhIS046801318S | 2018-11-12 | Hospital Enche Besar Hajjah Kalsom, Kluang | General Module | Drug/Non Drug Catalogue - Unable to change item default | Email: Seperti dalam lampiran, terdapat 3 item default dalam non drug catalogues phis tidak boleh ditukar kepada yang terkini, di mana item default yang diingini (item LP) tidak muncul dalam product search . Item APPL sahaja yang boleh dipilih sebagai default item walaopun ketiga-tiga item tersebut bukan lagi item APPL sekarang. Drug code: B1200160005 B1200160006 B1200160007 | [5 empty] | Johor
7 | 18595241C | I-PhIS047287418S | 2018-11-27 | Hospital Pakar Sultanah Fatimah | Inpatient Pharmacy | Fill List - Request enhancement | Request raised by Pn Aisyah through En Adam (BPF) via email. Kindly refer attachment for further details. | [5 empty] | Johor
8 | 18586225C | I-PhIS046611418S | 2018-11-05 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Record Prescription - Renew RX with diff duration- Request data auto appear | Puan Azween request Original Presciption No & End Date appear base on data already fill in at Record prescription screen before click at Medication profile for Renew RX with diff duration. Original Presciption No : appear base on Original Prescription Serial Number End Date : appear base on Clinic TCA | [5 empty] | Johor
9 | 18587159C | I-PhIS046703718S | 2018-11-08 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Medication profile - Add button intervention for missed medication | Receive email from user Tan Pei Ling request : Cadangkan tambah satu buton untuk tujuan intervensi dose tertinggal (missed medication) di page medication order dan boleh tambahkan ubat yang tertinggal itu melalui medication profile. Untuk masa sekarang, dalam PhIS , intervensi hanya boleh dibuat untuk dos , frekuensi dan durasi sahaja. Hal ini kerana pada masa sekarang, untuk ptj bukan full-based, apabila doctor tertinggal preskrib ubat, pihak farmasi perlu transkrip semula ubat yang tertinggal itu (ambil lebih masa) dan statistic itu tidak dicapture sebagai intervensi dalam PhIS. (statistic intervensi missed medication perlu dicatat secara manual) | [5 empty] | Johor
10 | 18588979C | I-PhIS046859218S | 2018-11-13 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Record Prescription - Request able to change dosage schedule for BD HD and Non BD HD | Puan Azween request able to change dosage schedule for BD HD and Non BD HD. Reason User acknowledge about the system limitation but user insist to request for system at least able to appear the correct dose. User acknowledge they need to make manual calculation again for the allocation. | [5 empty] | Johor
11 | 18591587C | I-PhIS047075118S | 2018-11-21 | Hospital Permai | Outpatient Pharmacy | Request able to print label direct | Miss Tan request for print drug label without view Module open one by one detail patient. Example ,user select detail patient and click print. | [5 empty] | Johor
12 | 18596421C | I-PhIS047365118S | 2018-11-29 | Hospital Pakar Sultanah Fatimah | Pharmacy Inventory | Receive internal - Request to have button reject or cancelled | User Mr Fauzan request to add button reject or cancelled when receive internal. Current situation user need to approve and do adjustment. | [5 empty] | Johor
13 | 18586074C | I-PhIS046593118S | 2018-11-05 | Hospital Baling | General Module | Unit Catalogue List - All item missing | Encik Ikhwan reported all item missing in Unit Lelaki 2. User cannot remember the step. | [5 empty] | Kedah
14 | 18589474C | I-PhIS046901118S | 2018-11-14 | Hospital Kulim | Pharmacy Inventory | Issue - Own Consumption - Unable to cancel transaction | Encik Rosli reported unable to cancel transaction for own consumption issue Unit : Jabatan Kecemasan & Trauma Manual Issue No : M02U.ANE-0031738 Status : Draft User informed no button reject, user delete item but unable to save due to pop up msg please add item. | [5 empty] | Kedah
15 | 18591590C | I-PhIS047065118S | 2018-11-21 | Hospital Kulim | Pharmacy Inventory | KEWPS10 (issue offline): Request column Dikeluarkan & Direkodkan oleh to be blank | Puan Husna request column Dikeluarkan & Direkodkan oleh to be blank. This is because, person who issue the physical item might be different person for Hospital Kulim and all store in Kedah state. | [5 empty] | Kedah
16 | 18590759C | I-PhIS046991318S | 2018-11-18 | Hospital Pasir Mas | Manufacturing - Extemporaneous | ROA in Extemporaneous Glycopyrolate and in label become Intravenous | Email: Pengguna melaporkan:- 1) ROA di label dan worksheet Glycopyrolate 100mcg/ml Syrup jadi Intraveneous apabila di generate melaui Extemporaneus di modul OPD. 2) Arahan extemporaneous Glycopyrolate 100mcg/ml Syrup untuk dibuat oleh pesakit tidak betul. MRN: 75507 | [5 empty] | Kelantan
17 | 18589118C | I-PhIS046873418S | 2018-11-14 | Hospital Tumpat | Pharmacy Inventory | Receive Interfacility - Request able to receive manual | Encik Mohd Salehudin request Level 3 able to receive manual(Unit not involve for indent SPUB & Manufacturing) Reason User receive item from level 3 (HRPZ) manually | [5 empty] | Kelantan
18 | 18596036C | I-PhIS047335318S | 2018-11-28 | Klinik Kesihatan Lundang Paku | Report/Enquiry | Request enhancement for Issue report | Report/Enquiry-Inventory-Store Transaction- Transaction Summary- Issue report Mohon di asingkan maklumat di dalam issue report pada bahagian (Item Group ) DRUG, NON-DRUG & VACCINE. (rujuk lampiran 1) jUSTIFIKASI: 1) LAPORAN/RETEN DARI KKM perlu di asingkan antara 3 jenis ini 2) Praktis sekarang, nilai VAKSIN di tolak dari DRUG kerena ia di campur bersama (sedangkan Duit pembelian adalah berasingan) Jadi kenapa tidak di asingkan sedangkan maklumat yang di kehendaki oleh KKM adalah Berasingan? | [5 empty] | Kelantan
19 | 18596040C | I-PhIS047335418S | 2018-11-28 | Klinik Kesihatan Lundang Paku | Report/Enquiry | Request enhancement for Issue report Receive Item Report | Report/Enquiry-Inventory-Store Transaction- Transaction Summary- Receive Item Report Mohon di asingkan maklumat di dalam Receive Item Report pada bahagian (Item Group) DRUG, NON-DRUG & VACCINE. (rujuk lampiran 2) jUSTIFIKASI: 1) LAPORAN/RETEN DARI KKM perlu di asingkan antara 3 jenis ini 2) Praktis sekarang, nilai VAKSIN di tolak dari DRUG kerena ia di campur bersama (sedangkan Duit pembelian adalah berasingan) Jadi kenapa tidak di asingkan sedangkan maklumat yang di kehendaki oleh KKM adalah Berasingan? | [5 empty] | Kelantan
20 | 18585723C | I-PhIS046555518S | 2018-11-04 | Hospital Tanah Merah | Special Drug Request | Special Drug Request unable to edit | User unable to edit in module Special Drug Request . She want edit for transaction htmh 0049/2018 .Request type show patient, but she want change request type by batch | [5 empty] | Kelantan
21 | 18589176C | I-PhIS046879318S | 2018-11-14 | Hospital Alor Gajah | Adverse Drug Reaction (ADR) | ADR Reporting - Request listing filtered by ADR no | Ms Lio request listing filtered by ADR no. As of now, system will listing based on suspected drug. If user key in 2 drug for 1 patient, the listing will appear as 2 transaction based on drug even with same ADR no. Reason: Hard for user to calculate manually since facility filter based on ADR no, not based on drug. User inform if have many patient for the date she filtered, user must to view one by one patient based on their ADR no. | [5 empty] | Melaka
22 | 18586829C | I-PhIS046681118S | 2018-11-07 | Hospital Alor Gajah | MTAC | PF5.5b(MTAC) - Request to include based on order date in report | Puan Najwa request to include based on order date MTAC in report PF5.5b as a pre then after complete MTAC reporting appear as post. Based on checking user, if user not complete MTAC patient for MTAC reporting, it will not recorded in PF5.5b. If user complete with reporting it will recorded. As in manual practice, user will count from order date, not reporting date. Example: MRN: 83478 MTAC Order: 8/10/2018 Create visit: 9/10/2018 | [5 empty] | Melaka
23 | 18590275C | I-PhIS046959218S | 2018-11-16 | Hospital Jasin | MTAC | MTAC: Memohon isi kandungan consent form PhIS mengikut isi kandungan form manual KKM | Email: Pengguna memohon isi kandungan consent form PhIS mengikut isi kandungan form manual dari KKM Salam sejahtera, Sehubungan dengan perkara di atas, saya ingin mengemukakan change request untuk bahagian consent form di dalam modul MTAC. Hal ini kerana isi kandungan consent form dalam PhIS adalah tidak sama dengan kandungan yang tertera dalam Protocol Medication Therapy Adherence Clinic: Diabetes 2014 yang diterbit oleh Bahagian Perkhidmatan Farmasi, KKM. Ketidaksamaan ini telah menerima teguran daripada auditor dalaman ISO di fasiliti kami. Saya lampirkan gambar untuk menyokong change request ini. Diharap permohonan ini mendapat pertimbangan daripada pihak tuan/puan | [5 empty] | Melaka
24 | 18596816C | I-PhIS047391518S | 2018-11-30 | Hospital Tampin | Inpatient Pharmacy | Methadone Dispensing - Unable to find patient | Pn Nurul Huda informed she want to dispense for patient methadone for 2nd day but patient not found in Methadone Dispensing. User informed during search Dispensing Location only appear Farmasi Pesakit Luar and Kaunter Outpatient only. This patient should dispense on Kaunter Farmasi Pesakit Dalam. Patient: HTP00037344 | [5 empty] | Negeri Sembilan
25 | 18591997C | I-PhIS047095518S | 2018-11-22 | Klinik Kesihatan Ampangan (TPC) | Outpatient Pharmacy | Single Stage Dispensing(TPC) - Request addition button as per Methadone Dispensing tab. | Suggest addition of Record Prescription or Medication Order button as per Methadone Dispensing tab. Suggested flow Medication order (new button on Single Stage Dispensing) Single Stage Dispensing we would like to proceed with the previous change request to add in an additional button of medication order in the Single Stage Dispensing page which links to Record Prescription screen and had the function of Single Stage in a multiple stage dispensing settings location. The suggestion is as shown in attachment. | [5 empty] | Negeri Sembilan
26 | 18589195C | I-PhIS046881218S | 2018-11-14 | Hospital Tuanku Jaafar | Pharmacy Inventory | Return to supplier - Do number not appear | User reported she unable to perform return to supplier due to Do number not appear. User claimed she has received FOC for this PO. User select to return as others and PO is appear in system. Details as below: Receipt No: PO180000465 | [5 empty] | Negeri Sembilan
27 | 18587590C | I-PhIS046741118S | 2018-11-09 | Hospital Tengku Ampuan Afzan | Adverse Drug Reaction (ADR) | ADR Reporting - request is to add edit button in the allergy history | user request as below user need to fill the ADR reporting first, then we will need to fill in the allergy section which doing double work. I think if the ADR reporting have a specific button for allergy card and update patient's profile automatically during the ADR reporting process this will be very helpful. It's good to have the add allergy button too if patient already have documented allergy profile (such as if patient have allergy card from other KKM facilities), so our ward pharmacist can fill in the documented allergy information in the system. And in any ADR case which need to be confirmed, we can capture this reaction to be reported into the system. Another request is to add edit button in the allergy history. This is because sometimes, the doctor mistakenly informed us wrong medication that the patient allergic to. This eventually notify us during the transcribing process and giving extra concern to the doctors and patients during clarification process. The request is as explained in the PDF attachment. Thank you. | [5 empty] | Pahang
28 | 18596095C | I-PhIS047337318S | 2018-11-28 | Hospital Pekan | Order Management - Web | Record Prescription - Request to remove auto default when insert IC/MRN | User request to remove auto default/capture MRN number when user insert IC/MRN patient due to sometimes user not realize system auto select wrong IC and user has complete the transaction for that patient. User claimed current system, will auto recommend by IC/MRN. | [5 empty] | Pahang
29 | 18584799C | I-PhIS046465118S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request to have function cancel/reject | Encik Zulhilmi request to have function cancel/reject in this module. User request due to sometimes data enter incorrect. | [5 empty] | Perak
30 | 18590185C | I-PhIS046951818S | 2018-11-16 | Hospital Taiping | Adverse Drug Reaction (ADR) | ADR - No sent to integration button | Ms Tan reported regarding button send to integration. User informed there's ADR transaction without button sent to integration . After upgrade version, user aware the existence of the button. But, user wondered there's some transaction not provide that button, therefore she concerns whether that transaction successfully sent or not. User also query about previous ADR transaction which before version upgrade, the button is also provided, is it she need to click on that button or the transaction has been successfully sent. Refer user attachment for reference. Example patient:- HTPG00013249 HTPG00070604 From Email:- Enquiries: Function of button 'Send for integration' Module Adverse Drug Reaction Reports recorded & confirmed before 28/9/2018: YES, there is button to send for integration. Report done & confirmed after 28/9/2018 - NO, the button is missing. 1. Do we need to click to button to send report online to ADR monitoring centre, NPRA? OR just click confirm the report will be send to ADR monitoring centre, NPRA, MOH? 2. For report send before 28/9/2018: there is button for send for integration. Do we need to click on the button now? If we click, will the report be recieved 2x for the ADR monitoring centre? 3. For report send after 28/9/2018: is the report reach NPRA? How do we know if the report reach? Request addition of status update for each ADR report if recieved by ADR monitoring centre NPRA. Date for system update: 11/10/2018 | [5 empty] | Perak
31 | 18592123C | I-PhIS047109118S | 2018-11-22 | Klinik Kesihatan Changkat Jering | Adverse Drug Reaction (ADR) | ADR - Request to add button cancel/delete | Request to add button cancel / delete at Adverse drug Reaction screen. Due to currently no button to cancel and delete the record if status record Recorded. | [5 empty] | Perak
32 | 18590207C | I-PhIS046953918S | 2018-11-16 | Hospital Taiping | Clinical Pharmacokinetic Services (CPS) & TDM | TDM - To Add reject Reason | User request to add another reject reason if drug was not available at facility. Example : Drug Sample not available. | [5 empty] | Perak
33 | 18592142C | I-PhIS047109818S | 2018-11-22 | Hospital Bahagia Ulu Kinta | General Module | Error Factor - Request enhancement on listing page | Encik Hilmi request enhancement on listing page. user request to add column as below -Error detected By : Personnel Name (Pharmacist Name) -Type of Error -Able to sort date (Currently unable to sort date accordingly) -Status : Complete/In progress | [5 empty] | Perak
34 | 18596800C | I-PhIS047390818S | 2018-11-30 | Hospital Bahagia Ulu Kinta | General Module | User Roles-Request filter using IC No | En Hilmi request able to search user using IC No | [5 empty] | Perak
35 | 18592298C | I-PhIS047119418S | 2018-11-23 | Hospital Seri Manjung | Order Management - Web | Request system be able to identify/calculate the time for the medicine to be served auto | Puan Malinisham (BPF) request on behalf Hosp Seri Manjung regarding frequency. Following Mesyuarat PhIS at Hospital Seri Manjung (HSM) on 21st November 2018, prescribers were not happy with solution given for the following request Request to add Serve Todays Dose instead of STAT due to STAT dose policy which required drug to be served within 30minutes. Thus, there is a new request from HSM as follows System should be able to identify/ calculate the time for the medicine to be served AUTOMATICALLY when the doctor prescribe instead of clicking on the '1st dose now' icon . This is to avoid missed dose cases in case prescriber forget to tick the '1st dose now' icon. | [5 empty] | Perak
36 | 18584803C | I-PhIS046465418S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Report/Enquiry | ADR Report Listing - Request to tally with report BI Tools | Encik Zulhilmi request to tally report between PhIS (ADR Report Listing) and BI Tools (PF7). As of now user did not generate from PhIS since report not tally each time he generate. | [5 empty] | Perak
37 | 18584811C | I-PhIS046465618S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Report/Enquiry | ADR Report Listing - Request to generate status Verified and Confirm only | Encik Zulhilmi request when he generate report ADR Report Listing, ADR with status recorded also appear. User request not to included data with status Recorded. Reason: Some of ADR Reporting created hanging with status Recorded because of user wrongly key in data. To Add ADR status Filter and also column in ADR Report Listing. | [5 empty] | Perak
38 | 18588835C | I-PhIS046847418S | 2018-11-13 | Klinik Kesihatan Greentown | Report/Enquiry | Average Issue By Month - Request report enhancement | Request' ini dimajukan oleh En Adam: Mohon lihat semula formula laporan average issue per month 1. Dicadangkan bila dijana nilai yang diambil adalah nilai bulan terakhir. a. Contoh sekiranya laporan dijana pada hari ni, nilai yang dilaporkan adalah dari akhir bulan oktober 2. Average issue qty / month adalah dalam nilai sku bukan RM a. Mohon semak sama ada formula bulan yang dibahagikan adalah dari bulan yang laporan dijana atau ambil 12 bulan secara am walaupun laporan dijana pada bulan november? | [5 empty] | Perak
39 | 18596797C | I-PhIS047391018S | 2018-11-30 | Hospital Bahagia Ulu Kinta | Report/Enquiry | Request enhancement - Medication Error Reporting | En Hilmi request PhIS able to produce report (Medication Error Reporting) from data in Error Factor, QAP & Intervention. This report able to sent thru integration to MOH. (Same as ADR) | [5 empty] | Perak
40 | 18592558C | I-PhIS047134018S | 2018-11-23 | Hospital Seberang Jaya | Adverse Drug Reaction (ADR) | ADR: Request do not include medications that are started after the date of reaction | Email: Mr Goh request do not include medications that are started after the date of reaction Current Situation Currently, when making an ADR Report, PhIS will also automatically include all medications that are still ongoing into the ADR Report Problem Users tend to key in the report only after a week of investigation. This means that the report will contain medications that have started after the ADR event. e.g. ADR180000305 | [5 empty] | Pulau Pinang
41 | 18586520C | I-PhIS046643418S | 2018-11-07 | Hospital Pulau Pinang | Drug Information & Consumer Education | Enquiry Analysis : Request to Enhance Report | User request for Enquiry analysis can be filter by Department. Also user request to add search Criteria by Enquirer Name. | [5 empty] | Pulau Pinang
42 | 18587774C | I-PhIS046753418S | 2018-11-09 | Hospital Bukit Mertajam | Outpatient Pharmacy | request - label of ORS show in mls for pediatric | user found out the dose information as in the Phis label is not complete especially for the pediatric patient. Dose of ORS for pediatric patient should be customized according to their body weight. With this, i would like to make a recommendation regarding the ORS label information as in the Phis system while at the transcribing stage to add in choice of milliliter (ML) to make it to either choose packet or ML. This is to ease the job of customizing dose for pediatric patients. At the same time, kindly retain the dilution of the ORS by 1 packet of ORS to dilute in 250ML of water in the label. | [5 empty] | Pulau Pinang
43 | 18589975C | I-PhIS046935118S | 2018-11-15 | Hospital Bukit Mertajam | Outpatient Pharmacy | Screening & Verification - System wrongly allocate | Based on previous report no.: 17127920C. She informed system wrongly allocate. Example Scenario: User informed if she click allocate button for duration 1 month, system auto allocate 2 bottle. Confirmed by user, she want to allocate 1 bottle/month instead of 2 bottle/month. User already set dispense quantity as 1 bottle/month, but system still allocate as 2. User inform she don't want to proceed with Manual allocation. Example : Drug Name : Hypromellose 0.3% Eye Drops (with preservative) Drug Code : S01XA20000D2002XX | [5 empty] | Pulau Pinang
44 | 18592575C | I-PhIS047134718S | 2018-11-23 | Hospital Seberang Jaya | Outpatient Pharmacy | Request to allow tapered dose to be dispensed as part supply without having to hold any medication | Mr Goh request to allow tapered dose to be dispensed as part supply without having to hold any medication Current Situation If a prescription has tapered dose and is dispensed as a pert supply, error Unable to dispense! Please do allocation for all drugs or hold the drug if there is no drug stock will appear, so we have to hold the part supply Problem: This has made us unable to process tapered dose prescriptions correctly | [5 empty] | Pulau Pinang
45 | 18594574C | I-PhIS047251418S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Request Enhancement on Methadone Dispensing | Miss Eng request enhancement on Methadone Dispensing Currently able to tick : Dose Checking(intervention) Adverse Drug Reaction Monitoring Drug Information Drug Interaction Monitoring Methadone Dose Modification Type of side effect but no place to fill in detail. User request after tick the dose checking, got column for user to explain further regarding the intervention Reason Pharmacy acknowledge doctor regarding the intervention Example Tick : Drug Interaction Notes/remarks Column : Detail regarding interaction Produce report from data for statistic record in the end of the month. | [5 empty] | Pulau Pinang
46 | 18594594C | I-PhIS047252118S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Methadone Dispensing - Request enhancement on Listing Page | Miss Eng request enhancement on Methadone Dispensing Listing Page. User request to differentiate detail patient that already dispense for the same day to avoid duplicate dispensing. Suggestion. 1. Add Column with remarks done dispensed or 2. Notification appear when user double click for patient that already done dispense for that day - Are you confirm to proceed with 2nd dispense? or 3. After complete dispense patient, the patient name will disappear from listing page or 4. Got different colour for patient detail that already complete dispense. | [5 empty] | Pulau Pinang
47 | 18594717C | I-PhIS047257118S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Methadone Dispensing - Print out label for each date | Ms Eng request to print out label for each date. For example, - supply duration is from 26/11/2018 until 28/11/2018, - currently PhIS label will printed as 26/11/2018-28/11/2018. User request to can print each label for each date. Example: 1 label shows as 26/11/2018, 1 label shows as 27/11/2018, 1 label shows as 28/11/2018 | [5 empty] | Pulau Pinang
48 | 18592569C | I-PhIS047134418S | 2018-11-23 | Hospital Seberang Jaya | Patient Management | Patient Registration:Request in the Patient Registration List also show who registered patient | Mr Goh request in the Patient Registration List also show who registered patient Current Situation All patients registered in PhIS will appear in the Patient Registration List Problem Often we find possible mistakes in the patients details that we need to find the user to keyed the data to confirm the error. PhIS does not show who registered the patient. | [5 empty] | Pulau Pinang
49 | 18588819C | I-PhIS046845318S | 2018-11-13 | Hospital Seberang Jaya | Pharmacy Inventory | Indent Intra facility - Request add indent item appear all item in unit catalogue indenter & issuer | Refer to previous report: 16103425C User Mr Goh request add indent item in Indent Intra Facility screen, will appear all item in unit catalogue indenter & issuer (unit that has been select at Send Indent To). This is to avoid user (indenter) wrongly indent item and avoid mistakes in the indent process. | [5 empty] | Pulau Pinang
50 | 18592567C | I-PhIS047134318S | 2018-11-23 | Hospital Seberang Jaya | Pharmacy Inventory | KEWP 11 - Request to change format | Mr Goh request to Change the Item Issue Lists format so that the quantity issued will not confuse the reader. We recommend: (Refer attachment) Problem This is a repeat of ticket 17222806C, it was rejected but we strongly insist that the request be reconsidered. Current Situation The report shows the issue number more than once if more than 1 batch is issued for a particular drug/non-drug | [5 empty] | Pulau Pinang
51 | 18592571C | I-PhIS047134518S | 2018-11-23 | Hospital Seberang Jaya | Pharmacy Inventory | Recommend SPUB Indent List:Request only include prescriptions indented supply has been dispensed | Mr Goh request when generating a Recommend SPUB Indent List (in addition to the criteria in 18513613C) also only include prescriptions the indented supply has been dispensed Problem. The SPUB indent is often done weekly, but will still indent for a 1 month supply. Current Situation This request is an amendment to the change request 18513613C | [5 empty] | Pulau Pinang
52 | 18596737C | I-PhIS047387318S | 2018-11-30 | Hospital Balik Pulau | Pharmacy Inventory | Unit Catalogue List - All existing drug missing | Mr Fong reported all existing drug in unit Ward Lelaki suddenly missing. User realize item missing when user at Ward Lelaki unable to perform indent. Unit: Wad Lelaki | [5 empty] | Pulau Pinang
53 | 18592562C | I-PhIS047134218S | 2018-11-23 | Hospital Seberang Jaya | Report/Enquiry | Ward Pharmacy Registry:Request count CP1, CP2,and CP4, according to date that document generated | Mr Goh request to count the CP1, CP2, and CP4, according to the date that the documents were generated. Current Situation Currently, the report Ward Pharmacy Registry counts CP1, CP2, CP4 based on the date of admission. Problem In out PF report, we count based on the date the CP1, CP2, and CP4 is created. | [5 empty] | Pulau Pinang
54 | 18594662C | I-PhIS047255218S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage by Patient - Insert patient's address into PDF or Excel | Ms Eng request to insert details of patient's adress into PDF and Excel only. | [5 empty] | Pulau Pinang
55 | 18594674C | I-PhIS047255518S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage By Patient - Insert total of Qty Dispense | Ms Eng request to insert total of Qty Dispense into report. | [5 empty] | Pulau Pinang
56 | 18594682C | I-PhIS047255718S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage By Patient - Insert Title report, Printed by and Printed Date into Excel | MS Eng request to insert Title report, Printed By name of user and Printed Date into excel also. Kindly refer to example screen. | [5 empty] | Pulau Pinang
57 | 18594748C | I-PhIS047258418S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Report/Enquiry - Request to provide Methadone Report | Ms Eng request to provide Methadone Report specifically only for methadone record. Details include Patient Details (Name, MRN patient, ID patient) - SPUB - M1M - DBB - Counselling Kindly refer file upload for more details. | [5 empty] | Pulau Pinang
58 | 18586698C | I-PhIS046667418S | 2018-11-07 | Klinik Kesihatan Tandek | Pharmacy Inventory | request - RIQ inter facility maintain at current page if indent have more than 1 page | user request for RIQ inter facility, system to maintain at current page if indent have more than 1 page. as example. if user received 2 page of indent and edit quantity at page 2, after user save for the item, system will auto back at 1st page of RIQ screen, | [5 empty] | Sabah
59 | 18595182C | I-PhIS047281218S | 2018-11-27 | Hospital Tawau | Pharmacy Inventory | Return to supplying unit - Request able to reject transaction | User Pn Shahirul request able to reject transaction return to supplying unit or able to select other unit to receive the transaction. Situation: Ward (level 3) already perform return to supplying unit to substore inpatient pharmacy (level 2). But user at Sub Store inpatient pharmacy do not want to receive the item. That is why user request able to reject the transaction or able to select other unit to receive the transaction. | [5 empty] | Sabah
60 | 18596442C | I-PhIS047369318S | 2018-11-29 | Cawangan Farmasi Logistik Negeri Sabah | Pharmacy Inventory | RPL - Price appear as unit price not average price | Receive email from user : mohon pihak phis letak real price terutama bagi item quotation sbb harga sudah ditetapkan dari kontrak sebutharga PTJ. kebanyakkan harga item semakin mahal dan mengambil average price menyebabkan anggaran keseluruhan harga tidak tepat. Example item : Clindamycin 300mg/2ml Injection | [5 empty] | Sabah
61 | 18586771C | I-PhIS046673518S | 2018-11-07 | Hospital Dutchess of Kent | Report/Enquiry | Below Buffer - Request report print as per screen. | User Ms Tham informed already generate report Below Buffer and already sort by Available Quantity. But when user print report, item appear originally before user sort the data. Ms Tham request report print as per screen. Step: - Open screen report Below Buffer. - User select : Item Group = All, Quantity Available =All, Item Sub Class =All, Standard Item = All - Click search and report will generate. - Originally, item will appear as sort by Drug/ Non Drug name (from Alphabet A-Z). - User change sort by Quantity Available (from 0 until Max value). - When user click print report, it appear originally which is sort by Drug/ Non Drug name (from Alphabet A-Z). - User request report print as per screen which is after user change sort by Quantity Available (from 0 until Max value). V1823 | [5 empty] | Sabah
62 | 18587508C | I-PhIS046733418S | 2018-11-09 | Hospital Queen Elizabeth | Ward Pharmacy | Ward Pharmacy (CP2) - Missing CP1 and CP2 entry in PhIS | Email: I would like to log in complaint for the following entry (CP1 & CP2) which are missing in PhIs after one of our pharmacists key in. Timothy cleophas - 780212-12-5623 - CP 1 & CP 2 Soimon Gurad - 550311-12-5131- CP 2 Jalu Padar - 541231-65-5155 - CP 1 & CP 2 Chok Shun Jin - 3010102-12-5178 - CP 1 & CP 2 Ricky Julius - 650710-12-5807 CP 2 | [5 empty] | Sabah
63 | 18585034C | I-PhIS046491118S | 2018-11-01 | Hospital Sibu | Drug Information & Consumer Education | Drug Information - Request to Add Category of Enquiry | Mr Lau request to add category of enquiry as below. The existing category Drug not accurate. - Drug Interaction - Efficacy | [5 empty] | Sarawak
64 | 18586599C | I-PhIS046657318S | 2018-11-07 | Hospital Sibu | General Module | Item Master - Request provide print function | User request to able print record from item master. Purpose: User want to refer drug code by print the record since user informed after item code change to new code, the drug code also being changed. It makes user confused and user need to check one by one from item master. User informed currently user need to make comparison in Item Master to check new drug code (When HQ make changes for drug code), so can add the new drug code in Unit Catalogue List. | [5 empty] | Sarawak
65 | 18587338C | I-PhIS046717318S | 2018-11-08 | Hospital Umum Sarawak | General Module | Patient Registration: Enable to find patient detail that had been merge | Miss Julie request to enable to find patient detail that had been merge (IC & Other identification number). This is because, to avoid registration many times if patient come to provide other identification details. Currently PhIS allow to register many time by using other identification number. Example police that use IC and Police ID. | [5 empty] | Sarawak
66 | 18590624C | I-PhIS046981118S | 2018-11-17 | Hospital Miri | General Module | User Roles- Request able to edit CDR Regimen | Mr Ong request for Pharmacist in charge CDR able to edit CDR Regimen. Currently only roles facility admin able to edit CDR Regimen. | [5 empty] | Sarawak
67 | 18585492C | I-PhIS046531318S | 2018-11-02 | MUSN Kuching | Pharmacy Inventory | issue report - quantity issued appear as 0 | user reported at screen issue report appear even though user have closed the indent and did not issue any item to requester .user inform actually no need to appear in the report . Why need to show in the report. all the while doesn't have. kindly refer file upload | [5 empty] | Sarawak
68 | 18595078C | I-PhIS047276318S | 2018-11-27 | Hospital Betong | Pharmacy Inventory | Physical checking - Appear message when save | Mr Lau reported appear message when click save button at physical checking. duplicate item batch and combination . At screen appear 2 item ,same brand, difference batch and expire date. item : 13.4400.01 step : | [5 empty] | Sarawak
69 | 18585159C | I-PhIS046507118S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Penambahbaikan - Drug Information - Bahagian Enquiry Date & Time | En Omar memberitahu penambaikan perlu dilakukan bagi modul 'Drug Information' pada bahagian Enquiry Date & Time. En Omar memberitahu bahawa bahagian Enquiry Date & Time hendaklah boleh di backdated. Buat masa sekarang ini, bahagian ini tidak boleh di backdated. | [5 empty] | Selangor
70 | 18585161C | I-PhIS046507218S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Penambaikan - Drug Information - Enquiry From | En Omar memberitahu apabila beliau membuat pilihan bahagian Enquirer Category : Public, pada bahagian Enquiry From Within facility / Department; tiada pilihan yang sesuai yang perlu dipilih untuk dipadan dengan Enquirer Category : Public. En Omar memberitahu situasi berlaku apabila seorang mak telah menelifon beliau untuk bertanyakan berkenaan ubat yang diberikan kepada anaknya. En Omar memberitahu senarai yang perlu ditambah pada bahagian Enquiry From Within facility / Department adalah Others supaya apabila membuat pilihan bahagian Enquirer Category : Public, pada bahagian Enquiry From Within facility / Department boleh dipilih sebagi Others. | [5 empty] | Selangor
71 | 18585262C | I-PhIS046511618S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Drug Information - Request to have function delete after save record | Encik Omar request to have function delete/cancel/reject in this module if user wrongly key in, after saved. | [5 empty] | Selangor
72 | 18591654C | I-PhIS047073418S | 2018-11-21 | Hospital Selayang | General Module | Unit Catalogue List - All item missing | Pn Masyitah reported all item been missing in unit catalogue list IPD substore. She informed had click 1 item and want to delete, however when user click dustbin button, all item were missing. When user try to add back the item, popup appear 'Item already exist'. As of now when user enter unit catalogue back, appear no record found. Unit catalogue: IPD substore Unit code: PS007 | [5 empty] | Selangor
73 | 18586755C | I-PhIS046673118S | 2018-11-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Profile (Renew Rx with different duration) - Request enhancement | Ms Goh request Original Prescriber Name and Original Prescription No is auto filled at Renew Rx with different duration in medication profile screen. She inform already fill in both field earlier and have to fill in once again in this screen. | [5 empty] | Selangor
74 | 18586760C | I-PhIS046673218S | 2018-11-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Order - Request cursor to default at queue no | Ms Goh request cursor to default at queue no at medication order screen. She claim as of current version, cursor is default at Original Prescription Serial Number. | [5 empty] | Selangor
75 | 18587384C | I-PhIS046723318S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase order - Mohon diletakkan bersebelahan Kuantiti Order dan Packaging Description | Receive email from Mr Omar: Saya ingin merujuk kepada 'Packaging description' vs 'Order Quantity' yang berada bersebelahan, agak jauh. Masalah akan berlaku apabila 'pack size' berubah dari eg botol kepada pack 72 botol. Buat order selang 3 bulan sekali. bermula dari 'pack size' eg botol beberapa kali sehingga lah pihak pembekal menukarnya kepada 'pack size' eg pack of 72 bottle. Di sini oleh kerana terbiasa mengira sebagai 'pack size' eg bootle , maka kesilapan hendak kuantiti 100 botol menjadi 100 x 72's. Oleh kerana hendak cepat selesai dan item yang di order bukan satu ke dua jenis item tetapi banyak maka terlepas pandang untuk melihat 'packing description' boleh berlaku. Di dalam tempuh 3 bulan ini saya telah tersilap sebanyak 2 kali kerana perkara ini. Kedua-dua mata saya hanya boleh melihat searah dan tidak mencapah kiri dan kanan . Maka apalah kiranya, pihak tuan dapat menukar posisi 'Quantity Order' dan 'Packing Description' di bawah atau di atasnya. Seterusnya saya hendak tahu 'Buffer Level', Min/Max storage adakah masih perlu dibuat secara manual ? Tidak bolehkah sistem default sebagai 'auto calculate' dan boleh diedit jika mahu, berdasarkan simpanan dan pembelian/inden item tersebut ? Alangkah baiknya jika sistem ini cerdik daripada kaku sahaja. | [5 empty] | Selangor
76 | 18587454C | I-PhIS046729118S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for button create new record | User request for (+) create new record button in inter facility indent after user done do indent. User inform right now user need to go to main screen to click create new record button, but user request the button appear after user done do the indent like purchase order. | [5 empty] | Selangor
77 | 18587457C | I-PhIS046729218S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for pop up window in inter facility indent | User request for Back Order Quantity column in inter facility indent user can click and show pop up window in detail for which indent number the back order come from. | [5 empty] | Selangor
78 | 18587459C | I-PhIS046729318S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Desiminate Slow Moving Item & Near Expired Item | User memohon agar item yang telah di buat tawaran 'slow moving item' atau near expired item', boleh diedit dan diguna semula datanya dan bukan perlu diulang semula kesemua proses ini. 1. Item yang di tawar, boleh di edit apabila ada yang berminat. 2. Senarai item boleh kitar semula untuk yang masih tiada permintaan. Ini akan membolehkan tempoh tawaran dipendekkan dan tidak berlaku sehingga setahun senarai ditawar tetapi di dalam senarai yang lama. | [5 empty] | Selangor
79 | 18589073C | I-PhIS046871118S | 2018-11-14 | Klinik Kesihatan Kelana Jaya | Pharmacy Inventory | Receive (Inter) - No record to received | Email: Tiada rekod untuk disimpan pada receive inter facality dari KK SEKSYEN 7 SHAH ALAM. Bersama ini saya lampirkan issue note R18000278, R800184 dan R17001042 untuk tindakan pembetulan dalam sistem Phis. | [5 empty] | Selangor
80 | 18589365C | I-PhIS046895418S | 2018-11-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive from Supplier - Request to know why Goods Received Date And Time included time in seconds | En Omar insist to know why good receive time included 'seconds' as well in receiving from supplier screen. Refer attachment. | [5 empty] | Selangor
81 | 18589637C | I-PhIS046915318S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Stock Adjustment: Request to remain character in field of item description and add button refresh | Encik Omar request to remain the searching character in field of item description. For example: user search item Gliclazide and user double click one item out of 10. User check the item batch, then user decide want to check other item code with same character item description, current system it will refresh the searching. User request to remain and add button refresh. If user want to search another item, user able to click on refresh button to clear the character. | [5 empty] | Selangor
82 | 18589821C | I-PhIS046927318S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent: Memohon notifikasi back order untuk stok telah dipesan | email: Pengguna ingin tahu jika APPL, apabila inden telah dibuat dan 'eP Approve', dan semasa proses 'receiving' jika ada item belum dibekal oleh APPL, maka boleh dipantau di modul 'Back order'. Tidak berlaku untuk inden Interfasiliti. Maka di sini pengguna ingin memohon agar 1. Apabila inden di buat dan telah 'Save' maka semasa membuat inden seterusnya, maka sistem akan memberitahu inden telah dibuat sama ada hendak diteruskan dengan tambahan inden atau membatalnya. 2. Ini akan mengelakkan kesilapan membuat inden atau pembelian berganda 3. Sistem akan dapat mengesan sejak sebelum inden 'Approve' lagi. 4. Ini berlaku untuk inden Pembelian atau Interfasiliti. 5. Apabila inden interfasiliti atau pembelian telah dibuat juaga, sistem akan memberitahu jika item berkenaan telah di inden/beli, semasa membuat inden/pembelian baru Diharap permohonan ini mendapat pertimbangan dari pihak tuan. | [5 empty] | Selangor
83 | 18590075C | I-PhIS046943218S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | request - allow system to receive item as purchase for purchasing via eP | email from user : Modul Receive Manual Oleh kerana sehingga ke hari ini, masalah integrasi 'ep' dan PhIS telah hampir satu tahun, yang tidak diketahui bilakah akan berakhir maka saya memohon agar 'Receive Manual' boleh dibuat mengguna 'receive category' yang bukan 'FOC'. Ini kerana jika ada penalti saya tidak dapat membuatnya kerana unit saya tiada borang penalti 'hardcopy' | [5 empty] | Selangor
84 | 18590083C | I-PhIS046943818S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Inquiry Indent inter facility - Usage Quantity Detail | Receive email from user Mr Omar : Merujuk kepada pertanyaan saya perkara ini berlaku di 'Usage Quantity Detail'. di mana - mana modul yang boleh dilihat Usage Quantity Detail'. Contoh di atas ialah di modul 'Interfasiliti Inden' 1. Adakah 'Usage Quantity Detail' termasuk a. kuantiti yang telah saya berikan kepada fasiliti lain b. Kuantiti telah lupus/rosak yang di buat 'Stok Adjustment' atau di kuarantin kerana luput tarikh atau lain-lain sebab ia di kuarantin c. Kuantiti diterima di level 3 dari fasiliti luar. | [5 empty] | Selangor
85 | 18590957C | I-PhIS047007618S | 2018-11-19 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive from supplier (FOC) - Appear message Item brand cannot be blank | En Omar reported,appear message item brand cannot be blank when fill column batch number, user need to fill other column first before fill column batch umber.Refer attachment. example item from user : 02.3015.04 | [5 empty] | Selangor
86 | 18591333C | I-PhIS047041118S | 2018-11-21 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive item (Inter Facility): Selected UOM is PKU but shown in item list is in SKU | Encik Omar reported selected UOM is PKU but shown in item list is in SKU. Indent no.: R18000198 Issue No.: M02PS001-0000724 | [5 empty] | Selangor
87 | 18594079C | I-PhIS047219018S | 2018-11-26 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent detail screen - Request able to edit approve quantity | En Omar request able to edit approve quantity at indent detail screen. Currently system not allow to edit, able to approve and reject only. Refer attachment. | [5 empty] | Selangor
88 | 18595814C | I-PhIS047321118S | 2018-11-28 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | request - request Stock Available (PKU) not show quantity .00 if stock PKU at Physical Checking | user request Stock Available (PKU) not show quantity .00 if stock PKU show as 1 box. at Physical Checking module as user inform stock with quantity available 1.00 will make the report physical checking a bit messy. earlier request is user request System not to show stock with null qty but after explain as per activity 1, user change the request as above | [5 empty] | Selangor
89 | 18596377C | I-PhIS047361218S | 2018-11-29 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive From Supplier (FOC) - Request to able using same DO for new transaction | En Omar informed he received item from supplier which in 1 DO have some item. He informed he has not enough time to insert all item in one receiving transaction due to he need to check on the cost of every item before proceed receiving. Usually he just proceed and approved receiving for certain item first which already checked the cost. On the next free time, he will open new receiving transaction for the rest item. However, system not allow to use the same DO due to system will prompt message the DO already in used . Therefore, user request system to allow using the same DO for new receiving transaction. | [5 empty] | Selangor
90 | 18596735C | I-PhIS047387218S | 2018-11-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Issue - Request to exclude RIQ (Inter) for user level 3 | Encik Omar request to exclude Module RIQ (inter) for user level 3. | [5 empty] | Selangor
91 | 18596739C | I-PhIS047387418S | 2018-11-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Physical Checking - Request to have option filter item prepacking | Encik Omar request to have option filtering of item prepack. User want when he search during add item, user can filter for item prepack. For example: Item prepacking > Set as Yes / No | [5 empty] | Selangor
92 | 18585706C | I-PhIS046553118S | 2018-11-04 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request enhancement for Module Item Movement | Mr Omar request to do enhancement in item movement module. he said after search under transaction below show result from 1/1/2018. User request the result transaction at page 1 must sort by the latest date or current date for easy him to view the report. | [5 empty] | Selangor
93 | 18586673C | I-PhIS046665618S | 2018-11-07 | Klinik Kesihatan Kalumpang | Report/Enquiry | Enquiry Analysis - Request to provide total record for each Category | En Omar request to provide total record for each category. User informed currently, the category of Enquiry have 13 category and user need to select one by one and manual count the total of each category. Purpose:- User want to update/transfer data from PhIS to his manual. | [5 empty] | Selangor
94 | 18587467C | I-PhIS046729618S | 2018-11-09 | Klinik Kesihatan Kalumpang | Report/Enquiry | Drug Information & Item Movement - Request to delete default | Merujuk kepada perkara di atas untuk kesemua data yang melibatkan tarikh. Contoh : 1. Modul Drug Information, apabila dibuka, baris yang pertama yang akan dipaparkan tarikh mula data di isi. 2. Item Movement, data pada baris pertama ialah data awal tahun. Yang terkini ialah di muka terakhir Dan banyak lagi modul bersifat 'DEFAULT'. User beritahu apabila dia hendak tahu maklumat data terakhir dan bukan data terawal sekali. Memanglah user boleh pergi ke muka surat terakhir, tetapi di dalam kesibukkan bekerja user perlu membuat satu langkah iaitu pergi ke muka surat terakhir ? User meminta proses memudah kerja digunapakai di sini. | [5 empty] | Selangor
95 | 18588493C | I-PhIS046821118S | 2018-11-12 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request reason the differential between PF7 in Bi Tools and Enquiry Registry in PhIS | Encik Omar request reason the differential between PF7 in Bi Tools and Enquiry Registry in PhIS. As user's concern, the two report is same format and it confused user. User give example with PF5.5b and PF6.3b. Both report show same name of report between PhIS and Bi Tools. | [5 empty] | Selangor
96 | 18596453C | I-PhIS047369818S | 2018-11-29 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request enhancement on Report (Next Collection Date) | Encik Omar request PhIS able to produce report appear list of patient that can print out base on total patient appear for next collection date in Dispensing Screen. Filter : Next Collection Date Partial Supply | [5 empty] | Selangor

## HQ(BPF)
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18586018C | I-PhIS046589618S | 2018-11-05 | Bahagian Perkhidmatan Farmasi (BPF) | PhIS Portal | To create new section for PM Report | To create new section for PM Report to upload PM report by facility (Sample Attached)
2
3
4
5
6
7
8
9
10

## Johor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18588302C | I-PhIS046801318S | 2018-11-12 | Hospital Enche Besar Hajjah Kalsom, Kluang | General Module | Drug/Non Drug Catalogue - Unable to change item default | Email: Seperti dalam lampiran, terdapat 3 item default dalam non drug catalogues phis tidak boleh ditukar kepada yang terkini, di mana item default yang diingini (item LP) tidak muncul dalam product search . Item APPL sahaja yang boleh dipilih sebagai default item walaopun ketiga-tiga item tersebut bukan lagi item APPL sekarang. Drug code: B1200160005 B1200160006 B1200160007
2 | 18595241C | I-PhIS047287418S | 2018-11-27 | Hospital Pakar Sultanah Fatimah | Inpatient Pharmacy | Fill List - Request enhancement | Request raised by Pn Aisyah through En Adam (BPF) via email. Kindly refer attachment for further details.
3 | 18586225C | I-PhIS046611418S | 2018-11-05 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Record Prescription - Renew RX with diff duration- Request data auto appear | Puan Azween request Original Presciption No & End Date appear base on data already fill in at Record prescription screen before click at Medication profile for Renew RX with diff duration. Original Presciption No : appear base on Original Prescription Serial Number End Date : appear base on Clinic TCA
4 | 18587159C | I-PhIS046703718S | 2018-11-08 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Medication profile - Add button intervention for missed medication | Receive email from user Tan Pei Ling request : Cadangkan tambah satu buton untuk tujuan intervensi dose tertinggal (missed medication) di page medication order dan boleh tambahkan ubat yang tertinggal itu melalui medication profile. Untuk masa sekarang, dalam PhIS , intervensi hanya boleh dibuat untuk dos , frekuensi dan durasi sahaja. Hal ini kerana pada masa sekarang, untuk ptj bukan full-based, apabila doctor tertinggal preskrib ubat, pihak farmasi perlu transkrip semula ubat yang tertinggal itu (ambil lebih masa) dan statistic itu tidak dicapture sebagai intervensi dalam PhIS. (statistic intervensi missed medication perlu dicatat secara manual)
5 | 18588979C | I-PhIS046859218S | 2018-11-13 | Klinik Kesihatan Bandar Maharani | Order Management - Web | Record Prescription - Request able to change dosage schedule for BD HD and Non BD HD | Puan Azween request able to change dosage schedule for BD HD and Non BD HD. Reason User acknowledge about the system limitation but user insist to request for system at least able to appear the correct dose. User acknowledge they need to make manual calculation again for the allocation.
6 | 18591587C | I-PhIS047075118S | 2018-11-21 | Hospital Permai | Outpatient Pharmacy | Request able to print label direct | Miss Tan request for print drug label without view Module open one by one detail patient. Example ,user select detail patient and click print.
7 | 18596421C | I-PhIS047365118S | 2018-11-29 | Hospital Pakar Sultanah Fatimah | Pharmacy Inventory | Receive internal - Request to have button reject or cancelled | User Mr Fauzan request to add button reject or cancelled when receive internal. Current situation user need to approve and do adjustment.
8
9
10
11
12

## Kedah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18586074C | I-PhIS046593118S | 2018-11-05 | Hospital Baling | General Module | Unit Catalogue List - All item missing | Encik Ikhwan reported all item missing in Unit Lelaki 2. User cannot remember the step.
2 | 18589474C | I-PhIS046901118S | 2018-11-14 | Hospital Kulim | Pharmacy Inventory | Issue - Own Consumption - Unable to cancel transaction | Encik Rosli reported unable to cancel transaction for own consumption issue Unit : Jabatan Kecemasan & Trauma Manual Issue No : M02U.ANE-0031738 Status : Draft User informed no button reject, user delete item but unable to save due to pop up msg please add item.
3 | 18591590C | I-PhIS047065118S | 2018-11-21 | Hospital Kulim | Pharmacy Inventory | KEWPS10 (issue offline): Request column Dikeluarkan & Direkodkan oleh to be blank | Puan Husna request column Dikeluarkan & Direkodkan oleh to be blank. This is because, person who issue the physical item might be different person for Hospital Kulim and all store in Kedah state.
4
5
6
7
8
9
10

## Kelantan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18590759C | I-PhIS046991318S | 2018-11-18 | Hospital Pasir Mas | Manufacturing - Extemporaneous | ROA in Extemporaneous Glycopyrolate and in label become Intravenous | Email: Pengguna melaporkan:- 1) ROA di label dan worksheet Glycopyrolate 100mcg/ml Syrup jadi Intraveneous apabila di generate melaui Extemporaneus di modul OPD. 2) Arahan extemporaneous Glycopyrolate 100mcg/ml Syrup untuk dibuat oleh pesakit tidak betul. MRN: 75507
2 | 18589118C | I-PhIS046873418S | 2018-11-14 | Hospital Tumpat | Pharmacy Inventory | Receive Interfacility - Request able to receive manual | Encik Mohd Salehudin request Level 3 able to receive manual(Unit not involve for indent SPUB & Manufacturing) Reason User receive item from level 3 (HRPZ) manually
3 | 18596036C | I-PhIS047335318S | 2018-11-28 | Klinik Kesihatan Lundang Paku | Report/Enquiry | Request enhancement for Issue report | Report/Enquiry-Inventory-Store Transaction- Transaction Summary- Issue report Mohon di asingkan maklumat di dalam issue report pada bahagian (Item Group ) DRUG, NON-DRUG & VACCINE. (rujuk lampiran 1) jUSTIFIKASI: 1) LAPORAN/RETEN DARI KKM perlu di asingkan antara 3 jenis ini 2) Praktis sekarang, nilai VAKSIN di tolak dari DRUG kerena ia di campur bersama (sedangkan Duit pembelian adalah berasingan) Jadi kenapa tidak di asingkan sedangkan maklumat yang di kehendaki oleh KKM adalah Berasingan?
4 | 18596040C | I-PhIS047335418S | 2018-11-28 | Klinik Kesihatan Lundang Paku | Report/Enquiry | Request enhancement for Issue report Receive Item Report | Report/Enquiry-Inventory-Store Transaction- Transaction Summary- Receive Item Report Mohon di asingkan maklumat di dalam Receive Item Report pada bahagian (Item Group) DRUG, NON-DRUG & VACCINE. (rujuk lampiran 2) jUSTIFIKASI: 1) LAPORAN/RETEN DARI KKM perlu di asingkan antara 3 jenis ini 2) Praktis sekarang, nilai VAKSIN di tolak dari DRUG kerena ia di campur bersama (sedangkan Duit pembelian adalah berasingan) Jadi kenapa tidak di asingkan sedangkan maklumat yang di kehendaki oleh KKM adalah Berasingan?
5 | 18585723C | I-PhIS046555518S | 2018-11-04 | Hospital Tanah Merah | Special Drug Request | Special Drug Request unable to edit | User unable to edit in module Special Drug Request . She want edit for transaction htmh 0049/2018 .Request type show patient, but she want change request type by batch
6
7
8
9
10
11
12

## Melaka
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18589176C | I-PhIS046879318S | 2018-11-14 | Hospital Alor Gajah | Adverse Drug Reaction (ADR) | ADR Reporting - Request listing filtered by ADR no | Ms Lio request listing filtered by ADR no. As of now, system will listing based on suspected drug. If user key in 2 drug for 1 patient, the listing will appear as 2 transaction based on drug even with same ADR no. Reason: Hard for user to calculate manually since facility filter based on ADR no, not based on drug. User inform if have many patient for the date she filtered, user must to view one by one patient based on their ADR no.
2 | 18586829C | I-PhIS046681118S | 2018-11-07 | Hospital Alor Gajah | MTAC | PF5.5b(MTAC) - Request to include based on order date in report | Puan Najwa request to include based on order date MTAC in report PF5.5b as a pre then after complete MTAC reporting appear as post. Based on checking user, if user not complete MTAC patient for MTAC reporting, it will not recorded in PF5.5b. If user complete with reporting it will recorded. As in manual practice, user will count from order date, not reporting date. Example: MRN: 83478 MTAC Order: 8/10/2018 Create visit: 9/10/2018
3 | 18590275C | I-PhIS046959218S | 2018-11-16 | Hospital Jasin | MTAC | MTAC: Memohon isi kandungan consent form PhIS mengikut isi kandungan form manual KKM | Email: Pengguna memohon isi kandungan consent form PhIS mengikut isi kandungan form manual dari KKM Salam sejahtera, Sehubungan dengan perkara di atas, saya ingin mengemukakan change request untuk bahagian consent form di dalam modul MTAC. Hal ini kerana isi kandungan consent form dalam PhIS adalah tidak sama dengan kandungan yang tertera dalam Protocol Medication Therapy Adherence Clinic: Diabetes 2014 yang diterbit oleh Bahagian Perkhidmatan Farmasi, KKM. Ketidaksamaan ini telah menerima teguran daripada auditor dalaman ISO di fasiliti kami. Saya lampirkan gambar untuk menyokong change request ini. Diharap permohonan ini mendapat pertimbangan daripada pihak tuan/puan
4
5
6
7
8
9
10
11
12

## N_Sembilan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18596816C | I-PhIS047391518S | 2018-11-30 | Hospital Tampin | Inpatient Pharmacy | Methadone Dispensing - Unable to find patient | Pn Nurul Huda informed she want to dispense for patient methadone for 2nd day but patient not found in Methadone Dispensing. User informed during search Dispensing Location only appear Farmasi Pesakit Luar and Kaunter Outpatient only. This patient should dispense on Kaunter Farmasi Pesakit Dalam. Patient: HTP00037344
2 | 18591997C | I-PhIS047095518S | 2018-11-22 | Klinik Kesihatan Ampangan (TPC) | Outpatient Pharmacy | Single Stage Dispensing(TPC) - Request addition button as per Methadone Dispensing tab. | Suggest addition of Record Prescription or Medication Order button as per Methadone Dispensing tab. Suggested flow Medication order (new button on Single Stage Dispensing) Single Stage Dispensing we would like to proceed with the previous change request to add in an additional button of medication order in the Single Stage Dispensing page which links to Record Prescription screen and had the function of Single Stage in a multiple stage dispensing settings location. The suggestion is as shown in attachment.
3 | 18589195C | I-PhIS046881218S | 2018-11-14 | Hospital Tuanku Jaafar | Pharmacy Inventory | Return to supplier - Do number not appear | User reported she unable to perform return to supplier due to Do number not appear. User claimed she has received FOC for this PO. User select to return as others and PO is appear in system. Details as below: Receipt No: PO180000465
4
5
6
7
8
9

## Pahang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18587590C | I-PhIS046741118S | 2018-11-09 | Hospital Tengku Ampuan Afzan | Adverse Drug Reaction (ADR) | ADR Reporting - request is to add edit button in the allergy history | user request as below user need to fill the ADR reporting first, then we will need to fill in the allergy section which doing double work. I think if the ADR reporting have a specific button for allergy card and update patient's profile automatically during the ADR reporting process this will be very helpful. It's good to have the add allergy button too if patient already have documented allergy profile (such as if patient have allergy card from other KKM facilities), so our ward pharmacist can fill in the documented allergy information in the system. And in any ADR case which need to be confirmed, we can capture this reaction to be reported into the system. Another request is to add edit button in the allergy history. This is because sometimes, the doctor mistakenly informed us wrong medication that the patient allergic to. This eventually notify us during the transcribing process and giving extra concern to the doctors and patients during clarification process. The request is as explained in the PDF attachment. Thank you.
2 | 18596095C | I-PhIS047337318S | 2018-11-28 | Hospital Pekan | Order Management - Web | Record Prescription - Request to remove auto default when insert IC/MRN | User request to remove auto default/capture MRN number when user insert IC/MRN patient due to sometimes user not realize system auto select wrong IC and user has complete the transaction for that patient. User claimed current system, will auto recommend by IC/MRN.
3
4
5
6
7
8
9
10

## Perak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18584799C | I-PhIS046465118S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request to have function cancel/reject | Encik Zulhilmi request to have function cancel/reject in this module. User request due to sometimes data enter incorrect.
2 | 18590185C | I-PhIS046951818S | 2018-11-16 | Hospital Taiping | Adverse Drug Reaction (ADR) | ADR - No sent to integration button | Ms Tan reported regarding button send to integration. User informed there's ADR transaction without button sent to integration . After upgrade version, user aware the existence of the button. But, user wondered there's some transaction not provide that button, therefore she concerns whether that transaction successfully sent or not. User also query about previous ADR transaction which before version upgrade, the button is also provided, is it she need to click on that button or the transaction has been successfully sent. Refer user attachment for reference. Example patient:- HTPG00013249 HTPG00070604 From Email:- Enquiries: Function of button 'Send for integration' Module Adverse Drug Reaction Reports recorded & confirmed before 28/9/2018: YES, there is button to send for integration. Report done & confirmed after 28/9/2018 - NO, the button is missing. 1. Do we need to click to button to send report online to ADR monitoring centre, NPRA? OR just click confirm the report will be send to ADR monitoring centre, NPRA, MOH? 2. For report send before 28/9/2018: there is button for send for integration. Do we need to click on the button now? If we click, will the report be recieved 2x for the ADR monitoring centre? 3. For report send after 28/9/2018: is the report reach NPRA? How do we know if the report reach? Request addition of status update for each ADR report if recieved by ADR monitoring centre NPRA. Date for system update: 11/10/2018
3 | 18592123C | I-PhIS047109118S | 2018-11-22 | Klinik Kesihatan Changkat Jering | Adverse Drug Reaction (ADR) | ADR - Request to add button cancel/delete | Request to add button cancel / delete at Adverse drug Reaction screen. Due to currently no button to cancel and delete the record if status record Recorded.
4 | 18590207C | I-PhIS046953918S | 2018-11-16 | Hospital Taiping | Clinical Pharmacokinetic Services (CPS) & TDM | TDM - To Add reject Reason | User request to add another reject reason if drug was not available at facility. Example : Drug Sample not available.
5 | 18592142C | I-PhIS047109818S | 2018-11-22 | Hospital Bahagia Ulu Kinta | General Module | Error Factor - Request enhancement on listing page | Encik Hilmi request enhancement on listing page. user request to add column as below -Error detected By : Personnel Name (Pharmacist Name) -Type of Error -Able to sort date (Currently unable to sort date accordingly) -Status : Complete/In progress
6 | 18596800C | I-PhIS047390818S | 2018-11-30 | Hospital Bahagia Ulu Kinta | General Module | User Roles-Request filter using IC No | En Hilmi request able to search user using IC No
7 | 18592298C | I-PhIS047119418S | 2018-11-23 | Hospital Seri Manjung | Order Management - Web | Request system be able to identify/calculate the time for the medicine to be served auto | Puan Malinisham (BPF) request on behalf Hosp Seri Manjung regarding frequency. Following Mesyuarat PhIS at Hospital Seri Manjung (HSM) on 21st November 2018, prescribers were not happy with solution given for the following request Request to add Serve Todays Dose instead of STAT due to STAT dose policy which required drug to be served within 30minutes. Thus, there is a new request from HSM as follows System should be able to identify/ calculate the time for the medicine to be served AUTOMATICALLY when the doctor prescribe instead of clicking on the '1st dose now' icon . This is to avoid missed dose cases in case prescriber forget to tick the '1st dose now' icon.
8 | 18584803C | I-PhIS046465418S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Report/Enquiry | ADR Report Listing - Request to tally with report BI Tools | Encik Zulhilmi request to tally report between PhIS (ADR Report Listing) and BI Tools (PF7). As of now user did not generate from PhIS since report not tally each time he generate.
9 | 18584811C | I-PhIS046465618S | 2018-11-01 | Hospital Bahagia Ulu Kinta | Report/Enquiry | ADR Report Listing - Request to generate status Verified and Confirm only | Encik Zulhilmi request when he generate report ADR Report Listing, ADR with status recorded also appear. User request not to included data with status Recorded. Reason: Some of ADR Reporting created hanging with status Recorded because of user wrongly key in data. To Add ADR status Filter and also column in ADR Report Listing.
10 | 18588835C | I-PhIS046847418S | 2018-11-13 | Klinik Kesihatan Greentown | Report/Enquiry | Average Issue By Month - Request report enhancement | Request' ini dimajukan oleh En Adam: Mohon lihat semula formula laporan average issue per month 1. Dicadangkan bila dijana nilai yang diambil adalah nilai bulan terakhir. a. Contoh sekiranya laporan dijana pada hari ni, nilai yang dilaporkan adalah dari akhir bulan oktober 2. Average issue qty / month adalah dalam nilai sku bukan RM a. Mohon semak sama ada formula bulan yang dibahagikan adalah dari bulan yang laporan dijana atau ambil 12 bulan secara am walaupun laporan dijana pada bulan november?
11 | 18596797C | I-PhIS047391018S | 2018-11-30 | Hospital Bahagia Ulu Kinta | Report/Enquiry | Request enhancement - Medication Error Reporting | En Hilmi request PhIS able to produce report (Medication Error Reporting) from data in Error Factor, QAP & Intervention. This report able to sent thru integration to MOH. (Same as ADR)
12
13
14
15
16
17
18
19
20

## P.Pinang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18592558C | I-PhIS047134018S | 2018-11-23 | Hospital Seberang Jaya | Adverse Drug Reaction (ADR) | ADR: Request do not include medications that are started after the date of reaction | Email: Mr Goh request do not include medications that are started after the date of reaction Current Situation Currently, when making an ADR Report, PhIS will also automatically include all medications that are still ongoing into the ADR Report Problem Users tend to key in the report only after a week of investigation. This means that the report will contain medications that have started after the ADR event. e.g. ADR180000305
2 | 18586520C | I-PhIS046643418S | 2018-11-07 | Hospital Pulau Pinang | Drug Information & Consumer Education | Enquiry Analysis : Request to Enhance Report | User request for Enquiry analysis can be filter by Department. Also user request to add search Criteria by Enquirer Name.
3 | 18587774C | I-PhIS046753418S | 2018-11-09 | Hospital Bukit Mertajam | Outpatient Pharmacy | request - label of ORS show in mls for pediatric | user found out the dose information as in the Phis label is not complete especially for the pediatric patient. Dose of ORS for pediatric patient should be customized according to their body weight. With this, i would like to make a recommendation regarding the ORS label information as in the Phis system while at the transcribing stage to add in choice of milliliter (ML) to make it to either choose packet or ML. This is to ease the job of customizing dose for pediatric patients. At the same time, kindly retain the dilution of the ORS by 1 packet of ORS to dilute in 250ML of water in the label.
4 | 18589975C | I-PhIS046935118S | 2018-11-15 | Hospital Bukit Mertajam | Outpatient Pharmacy | Screening & Verification - System wrongly allocate | Based on previous report no.: 17127920C. She informed system wrongly allocate. Example Scenario: User informed if she click allocate button for duration 1 month, system auto allocate 2 bottle. Confirmed by user, she want to allocate 1 bottle/month instead of 2 bottle/month. User already set dispense quantity as 1 bottle/month, but system still allocate as 2. User inform she don't want to proceed with Manual allocation. Example : Drug Name : Hypromellose 0.3% Eye Drops (with preservative) Drug Code : S01XA20000D2002XX
5 | 18592575C | I-PhIS047134718S | 2018-11-23 | Hospital Seberang Jaya | Outpatient Pharmacy | Request to allow tapered dose to be dispensed as part supply without having to hold any medication | Mr Goh request to allow tapered dose to be dispensed as part supply without having to hold any medication Current Situation If a prescription has tapered dose and is dispensed as a pert supply, error Unable to dispense! Please do allocation for all drugs or hold the drug if there is no drug stock will appear, so we have to hold the part supply Problem: This has made us unable to process tapered dose prescriptions correctly
6 | 18594574C | I-PhIS047251418S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Request Enhancement on Methadone Dispensing | Miss Eng request enhancement on Methadone Dispensing Currently able to tick : Dose Checking(intervention) Adverse Drug Reaction Monitoring Drug Information Drug Interaction Monitoring Methadone Dose Modification Type of side effect but no place to fill in detail. User request after tick the dose checking, got column for user to explain further regarding the intervention Reason Pharmacy acknowledge doctor regarding the intervention Example Tick : Drug Interaction Notes/remarks Column : Detail regarding interaction Produce report from data for statistic record in the end of the month.
7 | 18594594C | I-PhIS047252118S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Methadone Dispensing - Request enhancement on Listing Page | Miss Eng request enhancement on Methadone Dispensing Listing Page. User request to differentiate detail patient that already dispense for the same day to avoid duplicate dispensing. Suggestion. 1. Add Column with remarks done dispensed or 2. Notification appear when user double click for patient that already done dispense for that day - Are you confirm to proceed with 2nd dispense? or 3. After complete dispense patient, the patient name will disappear from listing page or 4. Got different colour for patient detail that already complete dispense.
8 | 18594717C | I-PhIS047257118S | 2018-11-26 | Klinik Kesihatan Butterworth | Outpatient Pharmacy | Methadone Dispensing - Print out label for each date | Ms Eng request to print out label for each date. For example, - supply duration is from 26/11/2018 until 28/11/2018, - currently PhIS label will printed as 26/11/2018-28/11/2018. User request to can print each label for each date. Example: 1 label shows as 26/11/2018, 1 label shows as 27/11/2018, 1 label shows as 28/11/2018
9 | 18592569C | I-PhIS047134418S | 2018-11-23 | Hospital Seberang Jaya | Patient Management | Patient Registration:Request in the Patient Registration List also show who registered patient | Mr Goh request in the Patient Registration List also show who registered patient Current Situation All patients registered in PhIS will appear in the Patient Registration List Problem Often we find possible mistakes in the patients details that we need to find the user to keyed the data to confirm the error. PhIS does not show who registered the patient.
10 | 18588819C | I-PhIS046845318S | 2018-11-13 | Hospital Seberang Jaya | Pharmacy Inventory | Indent Intra facility - Request add indent item appear all item in unit catalogue indenter & issuer | Refer to previous report: 16103425C User Mr Goh request add indent item in Indent Intra Facility screen, will appear all item in unit catalogue indenter & issuer (unit that has been select at Send Indent To). This is to avoid user (indenter) wrongly indent item and avoid mistakes in the indent process.
11 | 18592567C | I-PhIS047134318S | 2018-11-23 | Hospital Seberang Jaya | Pharmacy Inventory | KEWP 11 - Request to change format | Mr Goh request to Change the Item Issue Lists format so that the quantity issued will not confuse the reader. We recommend: (Refer attachment) Problem This is a repeat of ticket 17222806C, it was rejected but we strongly insist that the request be reconsidered. Current Situation The report shows the issue number more than once if more than 1 batch is issued for a particular drug/non-drug
12 | 18592571C | I-PhIS047134518S | 2018-11-23 | Hospital Seberang Jaya | Pharmacy Inventory | Recommend SPUB Indent List:Request only include prescriptions indented supply has been dispensed | Mr Goh request when generating a Recommend SPUB Indent List (in addition to the criteria in 18513613C) also only include prescriptions the indented supply has been dispensed Problem. The SPUB indent is often done weekly, but will still indent for a 1 month supply. Current Situation This request is an amendment to the change request 18513613C
13 | 18596737C | I-PhIS047387318S | 2018-11-30 | Hospital Balik Pulau | Pharmacy Inventory | Unit Catalogue List - All existing drug missing | Mr Fong reported all existing drug in unit Ward Lelaki suddenly missing. User realize item missing when user at Ward Lelaki unable to perform indent. Unit: Wad Lelaki
14 | 18592562C | I-PhIS047134218S | 2018-11-23 | Hospital Seberang Jaya | Report/Enquiry | Ward Pharmacy Registry:Request count CP1, CP2,and CP4, according to date that document generated | Mr Goh request to count the CP1, CP2, and CP4, according to the date that the documents were generated. Current Situation Currently, the report Ward Pharmacy Registry counts CP1, CP2, CP4 based on the date of admission. Problem In out PF report, we count based on the date the CP1, CP2, and CP4 is created.
15 | 18594662C | I-PhIS047255218S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage by Patient - Insert patient's address into PDF or Excel | Ms Eng request to insert details of patient's adress into PDF and Excel only.
16 | 18594674C | I-PhIS047255518S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage By Patient - Insert total of Qty Dispense | Ms Eng request to insert total of Qty Dispense into report.
17 | 18594682C | I-PhIS047255718S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Drug Usage By Patient - Insert Title report, Printed by and Printed Date into Excel | MS Eng request to insert Title report, Printed By name of user and Printed Date into excel also. Kindly refer to example screen.
18 | 18594748C | I-PhIS047258418S | 2018-11-26 | Klinik Kesihatan Butterworth | Report/Enquiry | Report/Enquiry - Request to provide Methadone Report | Ms Eng request to provide Methadone Report specifically only for methadone record. Details include Patient Details (Name, MRN patient, ID patient) - SPUB - M1M - DBB - Counselling Kindly refer file upload for more details.
19
20

## Perlis
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10

## Sabah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18586698C | I-PhIS046667418S | 2018-11-07 | Klinik Kesihatan Tandek | Pharmacy Inventory | request - RIQ inter facility maintain at current page if indent have more than 1 page | user request for RIQ inter facility, system to maintain at current page if indent have more than 1 page. as example. if user received 2 page of indent and edit quantity at page 2, after user save for the item, system will auto back at 1st page of RIQ screen,
2 | 18595182C | I-PhIS047281218S | 2018-11-27 | Hospital Tawau | Pharmacy Inventory | Return to supplying unit - Request able to reject transaction | User Pn Shahirul request able to reject transaction return to supplying unit or able to select other unit to receive the transaction. Situation: Ward (level 3) already perform return to supplying unit to substore inpatient pharmacy (level 2). But user at Sub Store inpatient pharmacy do not want to receive the item. That is why user request able to reject the transaction or able to select other unit to receive the transaction.
3 | 18596442C | I-PhIS047369318S | 2018-11-29 | Cawangan Farmasi Logistik Negeri Sabah | Pharmacy Inventory | RPL - Price appear as unit price not average price | Receive email from user : mohon pihak phis letak real price terutama bagi item quotation sbb harga sudah ditetapkan dari kontrak sebutharga PTJ. kebanyakkan harga item semakin mahal dan mengambil average price menyebabkan anggaran keseluruhan harga tidak tepat. Example item : Clindamycin 300mg/2ml Injection
4 | 18586771C | I-PhIS046673518S | 2018-11-07 | Hospital Dutchess of Kent | Report/Enquiry | Below Buffer - Request report print as per screen. | User Ms Tham informed already generate report Below Buffer and already sort by Available Quantity. But when user print report, item appear originally before user sort the data. Ms Tham request report print as per screen. Step: - Open screen report Below Buffer. - User select : Item Group = All, Quantity Available =All, Item Sub Class =All, Standard Item = All - Click search and report will generate. - Originally, item will appear as sort by Drug/ Non Drug name (from Alphabet A-Z). - User change sort by Quantity Available (from 0 until Max value). - When user click print report, it appear originally which is sort by Drug/ Non Drug name (from Alphabet A-Z). - User request report print as per screen which is after user change sort by Quantity Available (from 0 until Max value). V1823
5 | 18587508C | I-PhIS046733418S | 2018-11-09 | Hospital Queen Elizabeth | Ward Pharmacy | Ward Pharmacy (CP2) - Missing CP1 and CP2 entry in PhIS | Email: I would like to log in complaint for the following entry (CP1 & CP2) which are missing in PhIs after one of our pharmacists key in. Timothy cleophas - 780212-12-5623 - CP 1 & CP 2 Soimon Gurad - 550311-12-5131- CP 2 Jalu Padar - 541231-65-5155 - CP 1 & CP 2 Chok Shun Jin - 3010102-12-5178 - CP 1 & CP 2 Ricky Julius - 650710-12-5807 CP 2
6
7
8
9
10
11
12
13
14
15

## Sarawak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18585034C | I-PhIS046491118S | 2018-11-01 | Hospital Sibu | Drug Information & Consumer Education | Drug Information - Request to Add Category of Enquiry | Mr Lau request to add category of enquiry as below. The existing category Drug not accurate. - Drug Interaction - Efficacy
2 | 18586599C | I-PhIS046657318S | 2018-11-07 | Hospital Sibu | General Module | Item Master - Request provide print function | User request to able print record from item master. Purpose: User want to refer drug code by print the record since user informed after item code change to new code, the drug code also being changed. It makes user confused and user need to check one by one from item master. User informed currently user need to make comparison in Item Master to check new drug code (When HQ make changes for drug code), so can add the new drug code in Unit Catalogue List.
3 | 18587338C | I-PhIS046717318S | 2018-11-08 | Hospital Umum Sarawak | General Module | Patient Registration: Enable to find patient detail that had been merge | Miss Julie request to enable to find patient detail that had been merge (IC & Other identification number). This is because, to avoid registration many times if patient come to provide other identification details. Currently PhIS allow to register many time by using other identification number. Example police that use IC and Police ID.
4 | 18590624C | I-PhIS046981118S | 2018-11-17 | Hospital Miri | General Module | User Roles- Request able to edit CDR Regimen | Mr Ong request for Pharmacist in charge CDR able to edit CDR Regimen. Currently only roles facility admin able to edit CDR Regimen.
5 | 18585492C | I-PhIS046531318S | 2018-11-02 | MUSN Kuching | Pharmacy Inventory | issue report - quantity issued appear as 0 | user reported at screen issue report appear even though user have closed the indent and did not issue any item to requester .user inform actually no need to appear in the report . Why need to show in the report. all the while doesn't have. kindly refer file upload
6 | 18595078C | I-PhIS047276318S | 2018-11-27 | Hospital Betong | Pharmacy Inventory | Physical checking - Appear message when save | Mr Lau reported appear message when click save button at physical checking. duplicate item batch and combination . At screen appear 2 item ,same brand, difference batch and expire date. item : 13.4400.01 step :
7
8
9
10
11
12
13
14
15
16
17
18

## Selangor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18585159C | I-PhIS046507118S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Penambahbaikan - Drug Information - Bahagian Enquiry Date & Time | En Omar memberitahu penambaikan perlu dilakukan bagi modul 'Drug Information' pada bahagian Enquiry Date & Time. En Omar memberitahu bahawa bahagian Enquiry Date & Time hendaklah boleh di backdated. Buat masa sekarang ini, bahagian ini tidak boleh di backdated.
2 | 18585161C | I-PhIS046507218S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Penambaikan - Drug Information - Enquiry From | En Omar memberitahu apabila beliau membuat pilihan bahagian Enquirer Category : Public, pada bahagian Enquiry From Within facility / Department; tiada pilihan yang sesuai yang perlu dipilih untuk dipadan dengan Enquirer Category : Public. En Omar memberitahu situasi berlaku apabila seorang mak telah menelifon beliau untuk bertanyakan berkenaan ubat yang diberikan kepada anaknya. En Omar memberitahu senarai yang perlu ditambah pada bahagian Enquiry From Within facility / Department adalah Others supaya apabila membuat pilihan bahagian Enquirer Category : Public, pada bahagian Enquiry From Within facility / Department boleh dipilih sebagi Others.
3 | 18585262C | I-PhIS046511618S | 2018-11-02 | Klinik Kesihatan Kalumpang | Drug Information & Consumer Education | Drug Information - Request to have function delete after save record | Encik Omar request to have function delete/cancel/reject in this module if user wrongly key in, after saved.
4 | 18591654C | I-PhIS047073418S | 2018-11-21 | Hospital Selayang | General Module | Unit Catalogue List - All item missing | Pn Masyitah reported all item been missing in unit catalogue list IPD substore. She informed had click 1 item and want to delete, however when user click dustbin button, all item were missing. When user try to add back the item, popup appear 'Item already exist'. As of now when user enter unit catalogue back, appear no record found. Unit catalogue: IPD substore Unit code: PS007
5 | 18586755C | I-PhIS046673118S | 2018-11-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Profile (Renew Rx with different duration) - Request enhancement | Ms Goh request Original Prescriber Name and Original Prescription No is auto filled at Renew Rx with different duration in medication profile screen. She inform already fill in both field earlier and have to fill in once again in this screen.
6 | 18586760C | I-PhIS046673218S | 2018-11-07 | Klinik Kesihatan Ampang | Order Management - Web | Medication Order - Request cursor to default at queue no | Ms Goh request cursor to default at queue no at medication order screen. She claim as of current version, cursor is default at Original Prescription Serial Number.
7 | 18587384C | I-PhIS046723318S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Purchase order - Mohon diletakkan bersebelahan Kuantiti Order dan Packaging Description | Receive email from Mr Omar: Saya ingin merujuk kepada 'Packaging description' vs 'Order Quantity' yang berada bersebelahan, agak jauh. Masalah akan berlaku apabila 'pack size' berubah dari eg botol kepada pack 72 botol. Buat order selang 3 bulan sekali. bermula dari 'pack size' eg botol beberapa kali sehingga lah pihak pembekal menukarnya kepada 'pack size' eg pack of 72 bottle. Di sini oleh kerana terbiasa mengira sebagai 'pack size' eg bootle , maka kesilapan hendak kuantiti 100 botol menjadi 100 x 72's. Oleh kerana hendak cepat selesai dan item yang di order bukan satu ke dua jenis item tetapi banyak maka terlepas pandang untuk melihat 'packing description' boleh berlaku. Di dalam tempuh 3 bulan ini saya telah tersilap sebanyak 2 kali kerana perkara ini. Kedua-dua mata saya hanya boleh melihat searah dan tidak mencapah kiri dan kanan . Maka apalah kiranya, pihak tuan dapat menukar posisi 'Quantity Order' dan 'Packing Description' di bawah atau di atasnya. Seterusnya saya hendak tahu 'Buffer Level', Min/Max storage adakah masih perlu dibuat secara manual ? Tidak bolehkah sistem default sebagai 'auto calculate' dan boleh diedit jika mahu, berdasarkan simpanan dan pembelian/inden item tersebut ? Alangkah baiknya jika sistem ini cerdik daripada kaku sahaja.
8 | 18587454C | I-PhIS046729118S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for button create new record | User request for (+) create new record button in inter facility indent after user done do indent. User inform right now user need to go to main screen to click create new record button, but user request the button appear after user done do the indent like purchase order.
9 | 18587457C | I-PhIS046729218S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request for pop up window in inter facility indent | User request for Back Order Quantity column in inter facility indent user can click and show pop up window in detail for which indent number the back order come from.
10 | 18587459C | I-PhIS046729318S | 2018-11-08 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Desiminate Slow Moving Item & Near Expired Item | User memohon agar item yang telah di buat tawaran 'slow moving item' atau near expired item', boleh diedit dan diguna semula datanya dan bukan perlu diulang semula kesemua proses ini. 1. Item yang di tawar, boleh di edit apabila ada yang berminat. 2. Senarai item boleh kitar semula untuk yang masih tiada permintaan. Ini akan membolehkan tempoh tawaran dipendekkan dan tidak berlaku sehingga setahun senarai ditawar tetapi di dalam senarai yang lama.
11 | 18589073C | I-PhIS046871118S | 2018-11-14 | Klinik Kesihatan Kelana Jaya | Pharmacy Inventory | Receive (Inter) - No record to received | Email: Tiada rekod untuk disimpan pada receive inter facality dari KK SEKSYEN 7 SHAH ALAM. Bersama ini saya lampirkan issue note R18000278, R800184 dan R17001042 untuk tindakan pembetulan dalam sistem Phis.
12 | 18589365C | I-PhIS046895418S | 2018-11-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive from Supplier - Request to know why Goods Received Date And Time included time in seconds | En Omar insist to know why good receive time included 'seconds' as well in receiving from supplier screen. Refer attachment.
13 | 18589637C | I-PhIS046915318S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Stock Adjustment: Request to remain character in field of item description and add button refresh | Encik Omar request to remain the searching character in field of item description. For example: user search item Gliclazide and user double click one item out of 10. User check the item batch, then user decide want to check other item code with same character item description, current system it will refresh the searching. User request to remain and add button refresh. If user want to search another item, user able to click on refresh button to clear the character.
14 | 18589821C | I-PhIS046927318S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent: Memohon notifikasi back order untuk stok telah dipesan | email: Pengguna ingin tahu jika APPL, apabila inden telah dibuat dan 'eP Approve', dan semasa proses 'receiving' jika ada item belum dibekal oleh APPL, maka boleh dipantau di modul 'Back order'. Tidak berlaku untuk inden Interfasiliti. Maka di sini pengguna ingin memohon agar 1. Apabila inden di buat dan telah 'Save' maka semasa membuat inden seterusnya, maka sistem akan memberitahu inden telah dibuat sama ada hendak diteruskan dengan tambahan inden atau membatalnya. 2. Ini akan mengelakkan kesilapan membuat inden atau pembelian berganda 3. Sistem akan dapat mengesan sejak sebelum inden 'Approve' lagi. 4. Ini berlaku untuk inden Pembelian atau Interfasiliti. 5. Apabila inden interfasiliti atau pembelian telah dibuat juaga, sistem akan memberitahu jika item berkenaan telah di inden/beli, semasa membuat inden/pembelian baru Diharap permohonan ini mendapat pertimbangan dari pihak tuan.
15 | 18590075C | I-PhIS046943218S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | request - allow system to receive item as purchase for purchasing via eP | email from user : Modul Receive Manual Oleh kerana sehingga ke hari ini, masalah integrasi 'ep' dan PhIS telah hampir satu tahun, yang tidak diketahui bilakah akan berakhir maka saya memohon agar 'Receive Manual' boleh dibuat mengguna 'receive category' yang bukan 'FOC'. Ini kerana jika ada penalti saya tidak dapat membuatnya kerana unit saya tiada borang penalti 'hardcopy'
16 | 18590083C | I-PhIS046943818S | 2018-11-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Inquiry Indent inter facility - Usage Quantity Detail | Receive email from user Mr Omar : Merujuk kepada pertanyaan saya perkara ini berlaku di 'Usage Quantity Detail'. di mana - mana modul yang boleh dilihat Usage Quantity Detail'. Contoh di atas ialah di modul 'Interfasiliti Inden' 1. Adakah 'Usage Quantity Detail' termasuk a. kuantiti yang telah saya berikan kepada fasiliti lain b. Kuantiti telah lupus/rosak yang di buat 'Stok Adjustment' atau di kuarantin kerana luput tarikh atau lain-lain sebab ia di kuarantin c. Kuantiti diterima di level 3 dari fasiliti luar.
17 | 18590957C | I-PhIS047007618S | 2018-11-19 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive from supplier (FOC) - Appear message Item brand cannot be blank | En Omar reported,appear message item brand cannot be blank when fill column batch number, user need to fill other column first before fill column batch umber.Refer attachment. example item from user : 02.3015.04
18 | 18591333C | I-PhIS047041118S | 2018-11-21 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive item (Inter Facility): Selected UOM is PKU but shown in item list is in SKU | Encik Omar reported selected UOM is PKU but shown in item list is in SKU. Indent no.: R18000198 Issue No.: M02PS001-0000724
19 | 18594079C | I-PhIS047219018S | 2018-11-26 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent detail screen - Request able to edit approve quantity | En Omar request able to edit approve quantity at indent detail screen. Currently system not allow to edit, able to approve and reject only. Refer attachment.
20 | 18595814C | I-PhIS047321118S | 2018-11-28 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | request - request Stock Available (PKU) not show quantity .00 if stock PKU at Physical Checking | user request Stock Available (PKU) not show quantity .00 if stock PKU show as 1 box. at Physical Checking module as user inform stock with quantity available 1.00 will make the report physical checking a bit messy. earlier request is user request System not to show stock with null qty but after explain as per activity 1, user change the request as above
21 | 18596377C | I-PhIS047361218S | 2018-11-29 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Receive From Supplier (FOC) - Request to able using same DO for new transaction | En Omar informed he received item from supplier which in 1 DO have some item. He informed he has not enough time to insert all item in one receiving transaction due to he need to check on the cost of every item before proceed receiving. Usually he just proceed and approved receiving for certain item first which already checked the cost. On the next free time, he will open new receiving transaction for the rest item. However, system not allow to use the same DO due to system will prompt message the DO already in used . Therefore, user request system to allow using the same DO for new receiving transaction.
22 | 18596735C | I-PhIS047387218S | 2018-11-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Issue - Request to exclude RIQ (Inter) for user level 3 | Encik Omar request to exclude Module RIQ (inter) for user level 3.
23 | 18596739C | I-PhIS047387418S | 2018-11-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Physical Checking - Request to have option filter item prepacking | Encik Omar request to have option filtering of item prepack. User want when he search during add item, user can filter for item prepack. For example: Item prepacking > Set as Yes / No
24 | 18585706C | I-PhIS046553118S | 2018-11-04 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request enhancement for Module Item Movement | Mr Omar request to do enhancement in item movement module. he said after search under transaction below show result from 1/1/2018. User request the result transaction at page 1 must sort by the latest date or current date for easy him to view the report.
25 | 18586673C | I-PhIS046665618S | 2018-11-07 | Klinik Kesihatan Kalumpang | Report/Enquiry | Enquiry Analysis - Request to provide total record for each Category | En Omar request to provide total record for each category. User informed currently, the category of Enquiry have 13 category and user need to select one by one and manual count the total of each category. Purpose:- User want to update/transfer data from PhIS to his manual.
26 | 18587467C | I-PhIS046729618S | 2018-11-09 | Klinik Kesihatan Kalumpang | Report/Enquiry | Drug Information & Item Movement - Request to delete default | Merujuk kepada perkara di atas untuk kesemua data yang melibatkan tarikh. Contoh : 1. Modul Drug Information, apabila dibuka, baris yang pertama yang akan dipaparkan tarikh mula data di isi. 2. Item Movement, data pada baris pertama ialah data awal tahun. Yang terkini ialah di muka terakhir Dan banyak lagi modul bersifat 'DEFAULT'. User beritahu apabila dia hendak tahu maklumat data terakhir dan bukan data terawal sekali. Memanglah user boleh pergi ke muka surat terakhir, tetapi di dalam kesibukkan bekerja user perlu membuat satu langkah iaitu pergi ke muka surat terakhir ? User meminta proses memudah kerja digunapakai di sini.
27 | 18588493C | I-PhIS046821118S | 2018-11-12 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request reason the differential between PF7 in Bi Tools and Enquiry Registry in PhIS | Encik Omar request reason the differential between PF7 in Bi Tools and Enquiry Registry in PhIS. As user's concern, the two report is same format and it confused user. User give example with PF5.5b and PF6.3b. Both report show same name of report between PhIS and Bi Tools.
28 | 18596453C | I-PhIS047369818S | 2018-11-29 | Klinik Kesihatan Kalumpang | Report/Enquiry | Request enhancement on Report (Next Collection Date) | Encik Omar request PhIS able to produce report appear list of patient that can print out base on total patient appear for next collection date in Dispensing Screen. Filter : Next Collection Date Partial Supply

## Terengganu
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6

## HKL
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18592306C | I-PhIS047119618S | 2018-11-23 | Hospital Kuala Lumpur | Manufacturing - Radiopharmaceutical | Stock Verification(Radiopharma): Request to add column to lock data | Miss Rachel request request to add column to lock data once activity has been measured and received for the first time, and then for subsequent updates to be listed as a list and recorded, instead of overwriting the data. Please see as attached. This request has been discussed with SA Ilya Syarah
2 | 18591408C | I-PhIS047051118S | 2018-11-21 | Hospital Kuala Lumpur | Order Management - Web | Record prescription - Patient name wrongly appear after enter IC patient no. | User Ms Yong reported patient name auto appear with incorrect patient details after user enter correct IC no. at screen Record prescription. User informed she already enter IC No.: 020326102188. But system auto appear for patient for IC No.: 921024105680. User realize patient name wrongly appear after she confirm order. User informed issue happen intermittently. Date Happen: 7/11/2018 (10.35am) Patient IC No.: 020326102188 Wrong patient IC No.: 921024105680
3 | 18586816C | I-PhIS046677518S | 2018-11-07 | Hospital Kuala Lumpur | Report/Enquiry | MTAC Registry - Request to provide Patient name | Ms Ho Chia Chia request to provide detail of patient name. She informed the patient name column is also important.
4 | 18586821C | I-PhIS046677718S | 2018-11-07 | Hospital Kuala Lumpur | Report/Enquiry | MTAC Registry - Request to provide total MTAC Record after print | Ms Ho Chia Chia request to provide total MTAC Record after print. User informed the total record is needed when print.
5
6
7
8
9
10
11
12

## WLabuan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6

## WP
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6

## Institut
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10