## Summ_Module
Summary by Status
No | Issue Type | Request
1 | Pharmacy Inventory | 31
2 | Patient Management | 4
3 | Order Management - Web | 8
4 | Order Management - Mobile | 1
5 | Special Drug Request | 2
6 | Outpatient Pharmacy | 12
7 | Inpatient Pharmacy | 3
8 | MAR - Web | 0
9 | MAR - Mobile | 0
10 | MTAC | 8
11 | Ward Pharmacy | 1
12 | Medication Counseling | 3
13 | Adverse Drug Reaction (ADR) | 6
14 | Clinical Pharmacokinetic Services (CPS) & TDM | 7
15 | Drug Information & Consumer Education | 1
16 | PhIS Portal | 0
17 | Manufacturing - CDR | 1
18 | Manufacturing - Extemporaneous | 0
19 | Manufacturing - Galenical | 0
20 | Manufacturing - IV | 0
21 | Manufacturing - PN | 0
22 | Manufacturing - Radiopharmaceutical | 2
23 | Data Mining - PhARM | 0
24 | Report/Enquiry | 17
25 | IWP | 0
26 | General Module | 3
27 | BCP | 0
| Total | 110

## Summ_State
No | Issue Type | Request
1 | BPF | 0
2 | Johor | 10
3 | Kedah | 2
4 | Kelantan | 4
5 | Melaka | 6
6 | Pahang | 4
7 | Perak | 19
8 | Pulau Pinang | 7
9 | Sabah | 10
10 | Sarawak | 11
11 | Selangor | 24
12 | Terengganu | 1
13 | W. Persekutuan | 2
14 | Negeri Sembilan | 8
15 | Perlis | 1
16 | HKL | 1
17 | W. Labuan | 0
18 | Institut | 0
| Total | 110

## Total
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks | State
1 | 18306774C | I-PhIS027261118S | 2018-03-08 | Hospital Kuala Lumpur | Pharmacy Inventory | Purchase Order (Appl) - Request to create one screen for manual purchase order | User request to create one screen for manual purchase order (Appl). User claimed she want insert manual order like Lp item & Contract. User consent regarding integration issue in eP. When order not enter to eP and user need receive manually. | [5 empty] | HKL
2 | 18322416C | I-PhIS028393218S | 2018-03-19 | Klinik Kesihatan Sultan Ismail | General Module | Login PhIS - Request to extend expiry date of password | En Faiz request to extend expiry date of password. He inform that current requirement which is password will be inactive after 3 months is too short. Therefore, he want to extend it for at least 5 months. | [5 empty] | Johor
3 | 18303133C | I-PhIS027047118S | 2018-03-07 | Hospital Pakar Sultanah Fatimah | Inpatient Pharmacy | Fill List - Unable to proceed fill list - double click, display button | User reported no stock available for this item. We need to untick or hold the medication. But when we double click, the prescription opens at the preparation screen. However, we are unable to hold because all the buttons are missing at preparation screen. Refer user attachment for further reference. Drug effected: Insulin regular Actrapid. Patient Name: Rozihana bt Abdullah | [5 empty] | Johor
4 | 18313256C | I-PhIS027721118S | 2018-03-13 | Hospital Pakar Sultanah Fatimah | Outpatient Pharmacy | Screening & Verification - Wrong allocation qty | System calculates wrongly the allocation qty of warfarin weekly dose. MRN: HPSF00031746 | [5 empty] | Johor
5 | 18315174C | I-PhIS027865318S | 2018-03-14 | Klinik Kesihatan Paya Mas | Outpatient Pharmacy | request to add column select check box at screen dispensing | user request to add column select check box at screen dispensing to allow user select few patient for dispensing in one time. user inform if there have 1000 record of patient, user have to enter one by one to clear patient name at screen dispensing. | [5 empty] | Johor
6 | 18325253C | I-PhIS028617118S | 2018-03-20 | Hospital Permai | Outpatient Pharmacy | SPUB R1 form - Request to add column TCA appointment with doctor | Ms Li Hun Tan request to add new column as TCA appointment with doctor date in SPUB R1 form. She inform it can make easier for user and patient to view when patient TCA with doctor even she send spub out to other facility. | [5 empty] | Johor
7 | 18300333C | I-PhIS026841118S | 2018-03-06 | Hospital Pakar Sultanah Fatimah | Patient Management | Medication Profile - Additional Info - Request to add column 'updated by' for drug remark history | User request to add column 'updated by' for drug remark history at Additional Info (Medication Profile). Refer user attachment for further reference. | [5 empty] | Johor
8 | 18302140C | I-PhIS026969118S | 2018-03-07 | Klinik Kesihatan Sri Gading | Report/Enquiry | KPI2(b) and Prescription Dispense not tally | User Miss Syarifah reported Bilangan Perkara Diproses in KPI29b) not tally with Prescription Dispense for Average dispense. Update: User filter date from 21/12/2018 until 18/1/2018. For jumlah Jumlah Preskripsi Diterima in KPI2b is 2287 and Bilangan Perkara Diproses in KPI2b is 7368 | [5 empty] | Johor
9 | 18318633C | I-PhIS028107118S | 2018-03-15 | Hospital Permai | Report/Enquiry | Request to have report PF 5.1a 'Aktiviti pengurusan perskripsi farmasi pesakit luar in PhIS | Request to have report PF 5.1a Aktiviti pengurusan perskripsi farmasi pesakit luar in PhIS. Currently, the report is only available in BI tools. User request to make this report in PhIS so that they can compare the report between both BI Tools ans PhIS. | [5 empty] | Johor
10 | 18328438C | I-PhIS028835218S | 2018-03-21 | Hospital Sultanah Aminah | Report/Enquiry | KEWPS 5 - Request to edit card no | User request system allowed to edit card no in KEWPS 5 report. | [5 empty] | Johor
11 | 18338675C | I-PhIS029565418S | 2018-03-28 | Klinik Kesihatan Batu Pahat | Report/Enquiry | Request to have report for Prescription by Doctor. | En.Zafifi request to have a report to view record prescription by Doctor Name. The record will list total of prescription specifically by Doctor. | [5 empty] | Johor
12 | 18303713C | I-PhIS027085118S | 2018-03-07 | Pejabat Kesihatan Daerah Kuala Muda | Pharmacy Inventory | Receive item from supplier - Request to remove statement For Non-Drug Item batch is not applicable | Puan Azilawani request to remove statement For Non-Drug Item batch is not applicable at receive item from supplier module. It will confuse user. Reason: Even user not key in the batch no, phis still generate batch not applicable . User not sure that statement is information or instruction for user no need to key in the batch number. Steps: Receive item from supplier (AP/LP/Contract DO) Create new record fill up all requirement Add item Remove statement For Non-Drug Item batch is no applicable | [5 empty] | Kedah
13 | 18293035C | I-PhIS026299218S | 2018-03-01 | Hospital Jitra | Report/Enquiry | Patient Discharge - Request to add filter column by Discharge Date | User request to add filter column by Discharge Date. User want to know the total of Discharge date when she generate the date. Currently, system only shows date by Visit Date not Discharge Date. | [5 empty] | Kedah
14 | 18324933C | I-PhIS028589118S | 2018-03-20 | Hospital Tanah Merah | Clinical Pharmacokinetic Services (CPS) & TDM | TDM - Request to have at least one mandatory section after sample accepted stage | Base on report number 18314612C got TDM record which her staff only proceed until sample accepted but at the system the record already as result viewed. After checking one of her staff already proceed it until result viewed and without proper detail/report. This happens due to after sample accepted stage the is no mandatory section and her staff accidentally proceed until result viewed Pn Nik request to add at least one mandatory section to prevent this issue happen again in future. | [5 empty] | Kelantan
15 | 18336992C | I-PhIS029461118S | 2018-03-27 | Hospital Tanah Merah | Order Management - Mobile | Medication Profile (IPAD) - Request to change next/ previous arrow to be more visible | Pn Nik Ezmiza request to change next/ previous arrow to be more visible. Or put it as 'next' button and 'previous' button in order to acknowledged user for existing function. Based on previous report: 18329633C | [5 empty] | Kelantan
16 | 18307436C | I-PhIS027309118S | 2018-03-09 | Hospital Tanah Merah | Outpatient Pharmacy | Intervention - Dosage column dimmed | Miss Siti reported want to change dosage. But user unable to proceed due to column dosage was dimmed. Already try with another ID,same problem reported. drug name : Ceftazidime 1g Injection RX: ICU0000334147 Patien name : Zarina bt othman Mrn : HTM00023263 | [5 empty] | Kelantan
17 | 18334214C | I-PhIS029237218S | 2018-03-26 | Hospital Machang | Pharmacy Inventory | KEWPS10 (offline) - Dikeluarkan dan Direkod oleh appear detail same with Telah Diluluskan dan Direko | User Mrs Hafizah reported detail for Dikeluarkan dan Direkod oleh same with Telah Diluluskan dan Direkodkan oleh Example No Pegeluaran : M02PS001-0004117 Issue type : Intra-facility | [5 empty] | Kelantan
18 | 18297273C | I-PhIS026607118S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Request remove mandatory for field Status of Intervention * | Cik Asmirah request for Status of Intervention * can be change to not mandatory or provide NA. This is due some work process not direct to Doctor. | [5 empty] | Melaka
19 | 18297293C | I-PhIS026609118S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Request to Increase Character limitation | Cik Asmirah request to increase character Limitation for field Pharmacist Recommendation . | [5 empty] | Melaka
20 | 18297313C | I-PhIS026611218S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Outcome Column not appear at Report | Cik Asmirah reported she had complete for Pharmaceutical Care Issue and key in Outcome Field. However when print the report the Outcome Field was not appear at printed report. Happens to all patient | [5 empty] | Melaka
21 | 18298414C | I-PhIS026687118S | 2018-03-05 | Hospital Alor Gajah | Pharmacy Inventory | Item/Product Buffer Level - Request not mandatory set default vote code | Pn Lai request at screen Item/Product Buffer Level, remove the mandatory to set default vote code. Because, some of the item/drugs are not solely bought under 1 vote only. Instead, they might bought under other vote code depend on situation. If this setting still apply, she worry that user make mistake buying item under wrong vote although in PO screen user still can change to another vote code. She also added, if the mandatory is removed, system should allow user to save the details even the field Default Vote Code is blank at Item/Product Buffer Level screen. | [5 empty] | Melaka
22 | 18298773C | I-PhIS026719118S | 2018-03-05 | Pejabat Kesihatan Daerah Melaka Tengah | Pharmacy Inventory | Penalty Report (DMI) - Report stated name by DMI | En.Wafi reported when view Penalty report he unable to track the report from which Facility. This is due all the list stated DMI instead of user name. He had 10 page for Penalty report to approve but all is stated user DMI. | [5 empty] | Melaka
23 | 18321153C | I-PhIS028291118S | 2018-03-16 | Hospital Alor Gajah | Pharmacy Inventory | Purchase Order - Request unit price into 4 decimal point | User request for unit price can be key in 4 decimal places during purchase order. User mention current system only allowed user to key in unit price only for 2 decimal places and it will affect total of price and report. | [5 empty] | Melaka
24 | 18327593C | I-PhIS028781118S | 2018-03-21 | Klinik Kesihatan Seremban (TPC) | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - TDM Add Result not appear | User reported that TDM Add result not appear in TDM Reporting screen. According to user, sample and result already sent manual to Hospital, then after she receive manual and fill into TDM reporting result not appear. Step by user: TDM Reporting - Search Patient - Click + button - Click Add+ button - TDM Add result not appear. | [5 empty] | Negeri Sembilan
25 | 18332137C | I-PhIS029105118S | 2018-03-23 | Klinik Kesihatan Ampangan (TPC) | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - TDM Add Result not appear | User reported that TDM Add result not appear in TDM Reporting screen. According user she already proceed at TDM order. MRN:950215915048 | [5 empty] | Negeri Sembilan
26 | 18311893C | I-PhIS027607218S | 2018-03-12 | Klinik Kesihatan Port Dickson | Outpatient Pharmacy | Report - VAS Registry: Request to add field advance search | Puan Nadia request to add field advance search just like module (screening&verification,preparation, dispensing). User want the report of partial supply patient based on mode of service and next collection date patient. | [5 empty] | Negeri Sembilan
27 | 18305355C | I-PhIS027197218S | 2018-03-08 | Klinik Kesihatan Sikamat (TPC) | Pharmacy Inventory | Penalty - Request to Ep approve date follow as in PO screen | She request to change Ep approve date in Penalty module same as in PO screen. Tittle: Penalty - Recomended delay days show wrong value Pn Wani reported that the recommended delay day that system show for Penalty PE21-05060206-18300012 is wrong. Should be the recommended delay days is 2, but system show 6 days.User inform she accidently approve it. User want to know is it okay with current record? Penalty no : PE21-05060206-18300012 Manual calculation :2 day system show: 6 | [5 empty] | Negeri Sembilan
28 | 18323173C | I-PhIS028449218S | 2018-03-19 | Hospital Tampin | Pharmacy Inventory | Request created item in HQ set to facility status active | This issue raised in pharmaniaga dialogue. Pn Radznah requested if there are new item created and activated in IWP, it will exist in facility with facility status = active. For example: item Tetanus Toxoid changed from code 07.0004.03 to 07.0004.02. When HQ activated item code 07.0004.02 in IWP, the code will appear in facility with facility status active. So facility do not need to activate the item manually in PHIS. | [5 empty] | Negeri Sembilan
29 | 18323233C | I-PhIS028453118S | 2018-03-19 | Hospital Tampin | Pharmacy Inventory | Request system automatic set default for brand | This issue raised in Pharmaniaga dialogue. En Kamil requested system will automatically set default for item brand if user not set it manually. Current system, user unable to select item that not set brand default. due to this user requested system will automatically set default to any brand if user not set default manually. | [5 empty] | Negeri Sembilan
30 | 18311794C | I-PhIS027603218S | 2018-03-12 | Klinik Kesihatan Ampangan (TPC) | Report/Enquiry | Laporan Kos Per Preskripsi Fasiliti KKM - Enable search by Discipline | User Lim Xinli request to enable search by Discipline in Laporan Kos Per Preskripsi Fasiliti KKM Current Situation: unable to differentiate between medication prescribed by dental/medical officer in 'Laporan Kos Per Preskripsi Fasiliti KKM.' Search by 'Department' returns no results. Request: enable search by Discipline in Laporan Kos Per Preskripsi Fasiliti KKM, as per example shown in Drug Utilisation report. Kindly refer attachment | [5 empty] | Negeri Sembilan
31 | 18315855C | I-PhIS027919118S | 2018-03-14 | Hospital Tuanku Jaafar | Report/Enquiry | Purchase Order by Drug/Item - Filter function for Report | User request option to filter by type exists on report generation page but is non-functional. Kindly enable filtering by type. This request is based on advised at report 18282873C. | [5 empty] | Negeri Sembilan
32 | 18344334C | I-PhIS030039118S | 2018-03-30 | Hospital Tengku Ampuan Afzan | Manufacturing - CDR | CDR Preparation - Enable for Print Worksheet | En.Nasri request to Enable Print Worksheet at CDR Dispensing . As for now only available at CDR Preparation. User concern if user have missed to print at CDR preparation. | [5 empty] | Pahang
33 | 18326234C | I-PhIS028685118S | 2018-03-20 | Hospital Raub | Outpatient Pharmacy | Medication Order - Unable to edit Drug SPUB Online | Miss Young reported unable to edit below patient medication for SPUB online. According to user duration in system show wrong and when want to edit and add drug nothing appear. She confirm no error appear or processing happen but she unable to edit. HRAUB00092964 | [5 empty] | Pahang
34 | 18308512C | I-PhIS027375118S | 2018-03-09 | Hospital Raub | Patient Management | Medication Profile - Allergy - Allergy reaction not appear | User reported already enter allergy reaction during user enter allergy for patient. But when user open medication profile patient, allergy reaction not appear. User inform only appear drug name, severity and identification date. MRN: HRAUB00082376 | [5 empty] | Pahang
35 | 18301533C | I-PhIS026925118S | 2018-03-06 | Hospital Tengku Ampuan Afzan | Report/Enquiry | Receive Item Report - Request to provide filter by drug and vaccine | User request to provide able to filter by item/drug name and able to filter by item vaccine. | [5 empty] | Pahang
36 | 18307814C | I-PhIS027331418S | 2018-03-09 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request able to edit therapy start and end date | En Hilmi request able to edit therapy start and end date in drug details section. According to user currently unable to edit/adjust the therapy start and end date for active medication for patient. Reason: Therapy start date in system will capture when pharmacist transcribe the drug but user inform supposedly pharmacist will enter when patient start take the drug. Therapy end date in system will capture last date of pharmacist transcribe the drug but user inform supposedly pharmacist will enter when patient stop take the drug. Step: ADR Reporting > search pt > click + > drug details section > tick 1 active drug > double click > unable to edit therapy start and end date | [5 empty] | Perak
37 | 18313315C | I-PhIS027727118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request to enhance on ADR Reporting | En Hilmi request to enhance on ADR Reporting where add new option pop up message info example Do You Want to Register Allergic Card for this patient . Example: At Drug Details at ADR Reporting>Save>Pop up New message> | [5 empty] | Perak
38 | 18314615C | I-PhIS027825118S | 2018-03-13 | Klinik Kesihatan Greentown | Adverse Drug Reaction (ADR) | ADR - Drug detail cannot be save | Miss Sherdila reported Drug detail cannot be save when the dose of drug is different than its strength. User give example. Kindly refer File upload Patient taking bisoprolol 1.25mg (half tab of 2.5mg) MRN: KKE08004500003705 LEONG POK@LIANG POK | [5 empty] | Perak
39 | 18338193C | I-PhIS029523118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To change the arrow button to the button with word Add Sample | User reported Doctors need to right click the arrow button then Add Sample will be appear. This will make doctor confuse and cant find where to click as it is not easy to notice. Suggestion/Request: To change the arrow button to the button with word Add Sample as it will be easy to notice. Kindly please refer attachment. | [5 empty] | Perak
40 | 18338213C | I-PhIS029525118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To auto expand the row after add/save the sample. | User reported Doctors need to click + to expand. This is not easy to be noticed by doctors. Therefore she request to auto expand the row after add/save the sample. Kindly please refer attachment. | [5 empty] | Perak
41 | 18338233C | I-PhIS029527118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: Not allow to print prescription of TDM order if not complete confirm. | User reported Doctors can print prescription even not complete confirm the TDM order. This will cause the record not display in TDM Verification screen. Therefore she request not allow to print prescription of TDM order if not complete confirm. Kindly please refer attachment. | [5 empty] | Perak
42 | 18338254C | I-PhIS029529118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To add on / to create / to able the doctors to find back the tdm order for repr | User reported doctors cannot reprint the TDM order form if they had cancel X the screen. This will cause doctors doing multiple order TDM. Therefore she request To add on / to create / to able the doctors to find back the tdm order for reprint.. as a suggestion in TDM History. Kindly please refer attachment. | [5 empty] | Perak
43 | 18307773C | I-PhIS027331318S | 2018-03-09 | Hospital Bahagia Ulu Kinta | Drug Information & Consumer Education | Drug Info - Request to enable Drug Information Request No in printed report | En Hilmi request to enable Drug Information Request No in printed report. He inform have Drug Information Request No when he generate drug info. However, Drug Information Request No not included when he print report. User also inform currently, facility name appear twice at the header of printed report. | [5 empty] | Perak
44 | 18338293C | I-PhIS029533118S | 2018-03-27 | Hospital Seri Manjung | Inpatient Pharmacy | Request patient auto discharge once dispense medication done | Pn. Roshaliza request patient auto discharge once dispense medication done. Justifikasi : Berlaku kekangan di unit hasil(BDM) dan kaunter pendaftaran apabila tidak discharge patient bila keluar wad. Jika berlaku keadaan ini, Staff Kaunter terpaksa discharge patient dahulu, kemudian keyin untuk pendaftaran wad or klinik. Ini menjadikan beban kerja bertambah samaada di kaunter atau pon di wad. Justeru itu, kami mencadangkan agar sistem auto discharge selepas patient ambil ubat di farmasi. | [5 empty] | Perak
45 | 18293753C | I-PhIS026345118S | 2018-03-01 | Hospital Tapah | MTAC | MTAC Reporting - Request able to insert justification in column | User request able to insert justification in column for Lives with Family Members & Nursing Home. Currently system only allow to insert justification for others. Kindly refer attachment for reference. | [5 empty] | Perak
46 | 18337273C | I-PhIS029459118S | 2018-03-27 | Klinik Kesihatan Greentown | MTAC | MTAC Order - Unable to change to cancel status | User reported unable to cancel MTAC reporting in progress eventhough there is an edit button given. During MTAC reporting there is a need to cancel report while at the In Progress stage due to sudden discontinuation of counseling session with patient. Refer user attachment for reference. MRN - KKE08004500077573 Unable to cancel MTAC reporting in progress eventhough there is an edit button given. During MTAC reporting there is a need to cancel report while at the progress stage due to sudden discontinuation of counseling session with patient. Kindly rectify the issue ASAP. Thank you. | [5 empty] | Perak
47 | 18343276C | I-PhIS029957118S | 2018-03-29 | Klinik Kesihatan Jelapang | MTAC | Request to simplify DFIT chart (understanding score) for medication counseling and MTAC reporting | Suggestion: To change the current DFIT chart setting. Instead of allowing Pharmacist to tick (Yes/No) on each individual drug on Dose, frequency, indication, time of administration. Suggest the system to tick on all drugs as Yes on Dose, frequency, indication, time of administration, so that pharmacist only tick NO on wrong dose, frequency, indication or time of administration. Refer user attachment for reference. Reason: To shorten documentation time on each individual drug, pharmacist only tick on drug (Dose, frequency, indication or time of adminstration) that patient taking wrongly. | [5 empty] | Perak
48 | 18344773C | I-PhIS030063418S | 2018-03-30 | Hospital Taiping | MTAC | MTAC Reporting - Request able to cancel appointment for status Scheduled and In Progress | Pn Khor request user able to cancel appointment for MTAC visit with status Scheduled or In progress. Currently, she only able to cancel appointment with status Ordered. | [5 empty] | Perak
49 | 18344473C | I-PhIS030047218S | 2018-03-30 | Hospital Seri Manjung | Order Management - Web | Order Management - Authorisation based on location | User request authorisation based on location and not based on department.The reason as example below:- First scenario OPD MO doing locum in ED during weekend/night, so the prescription should go for ED HOD/specialist talk list not OPD HOD/specialist. This is becasue durgs prescribed in ED not in OPD HOD/specalist liability. second scenario Ophthal MO review medical patient for eye cases and prescribed drugs. Authorisation should go to Ophthal HOD/ Specialist talk list. This scenario shouldn't flow as per first scenario. | [5 empty] | Perak
50 | 18313233C | I-PhIS027717118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Outpatient Pharmacy | Print Allergy Card - Request to print in size as printer label | En Hilmi request to print allergy card in size as printer label due to currently print allergy card in size A4. He inform this not practically and waste time due to user need to print and cut for same as label. | [5 empty] | Perak
51 | 18313258C | I-PhIS027719218S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Outpatient Pharmacy | Print Allergy Card - Request new column for No Siri | En Hilmi request to add new column for No Siri next to column Patient MRN at screen Print Allergic Card. | [5 empty] | Perak
52 | 18334954C | I-PhIS029279118S | 2018-03-26 | Hospital Tapah | Outpatient Pharmacy | SPUB Online - request to view order after click draft | Ms Low reported she already registered patient SPUB online on 26/2/2018. But when patient come today she inform unable to view order. According to user practically she received SPUB online for 7days and need register first. Step User: external notification > Online SPUB R1 Request Received > click register > medication profile > click SPUB online button > click draft . After one month later patient come she unable to view order. Therefore she request able to view order even already click draft without proceed confirm. She inform if she click button confirm it will affect as reserve qty. example pt id: 730614086457 | [5 empty] | Perak
53 | 18313293C | I-PhIS027725118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Patient Management | Clinical Summary - Request to add new column at Allergy | En Hilmi request to add new column at Allergy part at screen Clinical Summary.He inform at Allergy part not show how allergic patient. Therefore he request to add new column Reaction Details next to Allergen. So that he will known more details/summary info reaction for allergy patient. | [5 empty] | Perak
54 | 18313174C | I-PhIS027711118S | 2018-03-13 | Klinik Kesihatan Karai | Pharmacy Inventory | Prepacking - Request to add price in all drug label | User request to add price in all drug label. User claimed currently her facility prepack drug to KK Desa and KK Desa not use the system. Thus, it's easy for KK Desa receive the label with price. | [5 empty] | Perak
55 | 18345993C | I-PhIS030149118S | 2018-03-30 | Hospital Tuanku Fauziah | Report/Enquiry | Report - Prescription Management IP: Request to add order type for filter | User request to add order type for filter in Prescription Management IP. Currently there is no button Order Type to filter as Prescription Management OP. Order type: Discharge, Normal, SPUB | [5 empty] | Perlis
56 | 18314233C | I-PhIS027793118S | 2018-03-13 | Hospital Pulau Pinang | Adverse Drug Reaction (ADR) | ADR Reporting -Request to able edit record even after confirmed | User request to be able to edit record even after it already confirmed. This is due to in future, it will have integration with NPRA, thus they need to ensure that all the details in the report is correct before sent to NPRA | [5 empty] | Pulau Pinang
57 | 18344594C | I-PhIS030053118S | 2018-03-30 | Hospital Pulau Pinang | Adverse Drug Reaction (ADR) | Adverse Drug Reaction - Request to remove (*) for Date End Of Reaction | User request to remove (*) for Date End Of Reaction due some of the reaction still on going. | [5 empty] | Pulau Pinang
58 | 18313952C | I-PhIS027771318S | 2018-03-13 | Klinik Kesihatan Seberang Jaya | Outpatient Pharmacy | SPUB - request to disable selection for facility with Implementation Type indent | user request to disable selection for facility with Implementation Type indent when user select facility for SPUB to prevent user from select wrong facility because some facility did not supply drug to patient example at KK Permatang Pauh | [5 empty] | Pulau Pinang
59 | 18295453C | I-PhIS026463118S | 2018-03-02 | Hospital Seberang Jaya | Pharmacy Inventory | Drug-non drug catalog-Request to add column SPUB | En Shuhaimi requested to add column SPUB in drug non drug catalog to facility. The value might be Yes or No .This function will enable facility to indent / received the item without set buffer level , min/max storage for the item. The item will be allowed to level 2 level 3 user to indent the item automatically. Also SPUB flag might be include in unit catalogue list to allow the facility to do that unit to do SPUB indent for the item and not allow the item to be indent as normal item. If the item set as SPUB YES the item will not appear during purchasing or doing RIL/RPL. This is because the facility will not purchase the item from supplier. facility will indent it from other facility. Example : Hospital seberang Jaya is not specialize in cardio so this facility will only indent the item from other facility that always keep the item. | [5 empty] | Pulau Pinang
60 | 18337594C | I-PhIS029487218S | 2018-03-27 | Hospital Seberang Jaya | Pharmacy Inventory | Indent (intra-facility) - Item not appear | User Mr Goh reported item not appear for C01BB01110P3001XX.01 if user select Item Purchase Type as LP.If user select Item Purchase Type under ALL, item code appear. Item Purchase Type : LP Facility status : Active Unit catalog : Exist | [5 empty] | Pulau Pinang
61 | 18319793C | I-PhIS028193118S | 2018-03-15 | Hospital Pulau Pinang | Special Drug Request | Special Drug Request - Request changes for Request By Batch | Puan Norshazan request changes for Request By : Batch. Current Situation When user print out SDR with status, Sending for KPK Approval. Print KPK Form. Patient Column still appear but blank. User request if tick to Request By Batch, the patient column do not need to be appear and replace with : Stock Hospital | [5 empty] | Pulau Pinang
62 | 18319814C | I-PhIS028195118S | 2018-03-15 | Hospital Pulau Pinang | Special Drug Request | Special Drug Request - Request add UOM strength for injection | Puan Norshazan request for 'Create New Drug' to add UOM strength for injection. Currently user unable to select any suitable UOM for injection. Example : mg/ml | [5 empty] | Pulau Pinang
63 | 18318413C | I-PhIS028087118S | 2018-03-15 | Hospital Pitas | Inpatient Pharmacy | Preparation : Administration Instruction Not appear for Print Preview | Cik Aqilah reported Administration Instruction Not appear for Print Preview. User had enter Administration Instruction bur when print out the Instruction was not appear. Happens to all patient. | [5 empty] | Sabah
64 | 18315494C | I-PhIS027891218S | 2018-03-14 | Klinik Kesihatan Felda Sahabat | Medication Counseling | Medication Counselling - Able to add backdated date more than 5 days | User request for system to allow Counseling to backdated more than 5days for document of their work in PhIS. Problem: In a typical work week, pharmacist will be busy counselling on Monday and Tuesday and will only have time to key in later in the week. Sometimes also it take a month to user key in their work. | [5 empty] | Sabah
65 | 18320153C | I-PhIS028221218S | 2018-03-16 | Hospital Dutchess of Kent | Medication Counseling | Request Group medication counseling able back dated for 7 day | Request Group medication counseling able set back dated for 7 day | [5 empty] | Sabah
66 | 18293973C | I-PhIS026361118S | 2018-03-01 | Hospital Kota Marudu | Order Management - Web | Record Prescription - Kuantiti tidak ikut seperti yang ditetapkan dalam Drug Master | Ms Yew melaporkan bahawa beliau telah menetapkan Paracetamol 500 mg Tablet di Facility Setting (Drug Master) - Quantity per duration adalah 10 tablet per month. Walau bagaimanapun apabila beliau 'prescribe' di dalam sistem PhIS iaitu 2 biji untuk 4 kali sehari, sistem tidak ikut seperti yang telah ditetapkan iaitu 10 biji untuk sebulan, sistem masih kira untuk 2 biji untuk 4 kali sehari untuk sebulan kuantiti akan menjadi beratus biji. | [5 empty] | Sabah
67 | 18342773C | I-PhIS029919118S | 2018-03-29 | Hospital Tawau | Order Management - Web | Medication Order - Request auto display original prescriber name in list | User request auto display original prescriber name in list. User claimed only Visit Type as walk in not appear. If others Visit Type, it auto display to search doctor's name. Details as below: Visit Type: Walk In Location: Farmasi Pesakit Luar Department: Outpatient This order is for TDM Record Prescription > Medication Order > Filter at Visit/Admission > Click TDM > Original Prescriber Name not auto generate in list | [5 empty] | Sabah
68 | 18313434C | I-PhIS027733318S | 2018-03-13 | Hospital Dutchess of Kent | Pharmacy Inventory | Prepacking - Request to add unit price when print label | Miss Saw request to add price when print label at prepacking screen for Label Unit of Dose : 20 mm x 13.3 mm. Refer file upload. User inform price refer item master. | [5 empty] | Sabah
69 | 18337652C | I-PhIS029493118S | 2018-03-27 | Cawangan Farmasi Logistik Negeri | Pharmacy Inventory | RIQ (Inter) - Request to add new column under indenter information (SKU) | Ms Pamela request to add new column under indenter information (SKU) at RIQ (inter) screen. She request if can include new column which is stock balance for indenter. | [5 empty] | Sabah
70 | 18298934C | I-PhIS026723118S | 2018-03-05 | Hospital Tuaran | Report/Enquiry | Issue Report - request new filter | User request to add new filter at Issue Report which indicate the origin the item that she issue. Example, user want to know whether the item that she issue is originally she get from Procurement or from other facility (should state facility name) | [5 empty] | Sabah
71 | 18322633C | I-PhIS028403118S | 2018-03-19 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Stock Balance By Drug/Non-Drug - Inactive item still appear on list | User reported drug still appear in list eventhough has been Inactive for Facility Status at Drug Non Drug Catalogue. User informed that user just new transaction just made yesterday and user already deactivated before that day. It happen to many drug. User can give 1 example of drug happen Drug code: A02AA10912L2101XX Item code: A02AA10912L2101XX.03 & 01.2407.06.074T | [5 empty] | Sabah
72 | 18337632C | I-PhIS029491218S | 2018-03-27 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Report/Enquiry - Request to trace back order qty for indent inter in report | Ms Pamela request to trace back order qty for indent inter that CFLN not supply yet. She request if can include report under report/enquiry so that she able to generate the report by all item. This list is important for user due to she want to refer before make procurement in future. | [5 empty] | Sabah
73 | 18292258C | I-PhIS026255118S | 2018-03-01 | Hospital Serian | General Module | User profile : Password expired date default to 90 days | Miss Chai reported password expired date default to 90 days. User inform already change Password Expiry at facility information but still default to 90 days. No popup appear when save at facility information. Also query why system default to 90 days. | [5 empty] | Sarawak
74 | 18337477C | I-PhIS029477118S | 2018-03-27 | Hospital Umum Sarawak | Manufacturing - Radiopharmaceutical | Kit Preparation - Volume not found | Miss Lucinda reported there is no value in Volume column for reported item. She inform there is no Worksheet ID as she has not save record yet. Kindly refer attachment provided. Item Code: RPH000041.02 | [5 empty] | Sarawak
75 | 18341860C | I-PhIS029845118S | 2018-03-29 | Hospital Umum Sarawak | Manufacturing - Radiopharmaceutical | Radiopharma kit Preparation - unable to allocate quantity to 0 | Radiopharma kit Preparation - unable to allocate quantity to 0 as error show only positive number is allowed as user inform some times user did not use the drug as preparation item code: RPH000041.01 RPH000041.02 | [5 empty] | Sarawak
76 | 18345713C | I-PhIS030129218S | 2018-03-30 | Hospital Miri | Order Management - Web | Transcribe order - unable to add item facility inactive | User Mr Ong request item status facility inactive to not appear when transcribe order | [5 empty] | Sarawak
77 | 18315492C | I-PhIS027893118S | 2018-03-14 | Hospital Kapit | Outpatient Pharmacy | SPUB Patient List - Patient not appear - taper - RX partially dispensed, drug acknowledged | Pn Hamizah reported that patient not appear when she want to make new SPUB patient at screen SPUB Patient List. MRN No: HKPT00099862 Step by user: SPUB Patient List > Key in MRN No patient > click on search button > no record appear | [5 empty] | Sarawak
78 | 18323593C | I-PhIS028479118S | 2018-03-19 | Hospital Umum Sarawak | Outpatient Pharmacy | Screening & Verification - Request to enable view Remarks | Miss Julie inform she key-in Remarks for one of drug in Screening and Verification screen. She already proceed until Dispense. Patient RX still active. By some reason, she want to view the information entered in Remarks but current system has no such function. Therefore, she request to enable user view Remarks for Full Supply patient. Both active and inactive medication. | [5 empty] | Sarawak
79 | 18329652C | I-PhIS028919118S | 2018-03-22 | MUSN Kuching | Pharmacy Inventory | KEWPS10 - Request to remove name at column Dikeluarkan & Direkod Oleh . | User request to remove name at column Dikeluarkan & Direkod Oleh in KEWPS-10 for offline issue. | [5 empty] | Sarawak
80 | 18293853C | I-PhIS026351118S | 2018-03-01 | Hospital Kapit | Report/Enquiry | Inpatient Prescription - Request include Discontinue prescription | Puan Hamizah request include Discontinue prescription in report. Current Situation Puan Hamizah informed data not tally when compare with manual prescription. | [5 empty] | Sarawak
81 | 18306793C | I-PhIS027259118S | 2018-03-08 | Hospital Sibu | Report/Enquiry | Report - Inpatient Prescription: Request to insert Outpatient Dispensing Location | User request to insert Outpatient Dispensing Location into this report so user able to trace back any prescription that officer did. | [5 empty] | Sarawak
82 | 18320854C | I-PhIS028271118S | 2018-03-16 | Klinik Kesihatan Bandar Miri | Report/Enquiry | KPI 2 (b) - 'Preskripsi Diterima' less than Prescription Dispense | Miss Kong reported No of 'Preskripsi Diterima' less than Prescription Dispensed. She inform she check No of 'Preskripsi Diterima' is 933 in KPI 2 (b). But when she check in Prescripsion Dispensed, total show as 1037. Kindly refer attachment provided. | [5 empty] | Sarawak
83 | 18328573C | I-PhIS028841418S | 2018-03-21 | Hospital Kapit | Ward Pharmacy | request - allowed user to access CP2 detail even patient already discharge | user request system allowed user to access CP2 detail even patient already discharge. as per inform by user, user unable to view CP2 detail if patient already discharge. | [5 empty] | Sarawak
84 | 18335933C | I-PhIS029361118S | 2018-03-26 | Klinik Kesihatan Kalumpang | Adverse Drug Reaction (ADR) | ADR - Asterisks Sign | User informed that column that appear to be filled in strictly(asterisks sign ' * ') just 2 which is Product Generic Name & drug Type only . But for drug details to be appeared at ADR, he said user have to fill all column inside drug detail coulmn. User request asterisks (*) sign have to be present at all column inside screen add drug detail. | [5 empty] | Selangor
85 | 18313573C | I-PhIS027743118S | 2018-03-13 | Klinik Kesihatan Kalumpang | General Module | PhIS - System automatically login | Merujuk kepada perkara di atas, saya dapati Cubaan 1: 1. Buka PhIS, ' Log In ' 2. Buka 'Connect Manage' , CM, tanpa perlu 'Log In' 3. Tutup ( Bukan 'Log Out' ) PhIS. Jangan tutup CM 4. Buka semula PhIS. Sistem tidak memerlukan untuk 'Log In' lagi. Skrin akan terus masuk ke dalam PhIS Cubaan 2: 1. Buka 'Connect Manage' , CM, tanpa perlu 'Log In' 2. Buka PhIS, ' Log In ' 3. Tutup ( Bukan 'Log Out' ) PhIS. Jangan tutup CM 4. Buka semula PhIS. Sistem tidak memerlukan untuk 'Log In' lagi. Skrin akan terus masuk ke dalam PhIS Di dalam kedua - dua simulasi ini saya dapati apabila CM dibiarkan dibuka, PhIS hanya perlu sekali sahaja 'Log In', kerana selepas PhIS ditutup (Bukan 'Log Out') dan dibuka semula, PhiS akan terus terbuka tak perlu 'Log In' lagi kepada 'Log In' ID orang yang terakhir menggunakan PhIS. Saya berharap, saya tidak diminta meng 'upload' video simulasi ini, kerana pihak tuan boleh mencuba sendiri menggunakan komputer tuan. | [5 empty] | Selangor
86 | 18295392C | I-PhIS026457218S | 2018-03-02 | Klinik Kesihatan Serendah | Medication Counseling | Medication Counselling order - Unable to change status to cancelled. | User reported unable to cancel medication counselling order for patient due to edit button not appear. But confirmed by user she already proceed with counselling reporting. Counselling Order No: MC1800000404 MRN: KKE10006100090661 | [5 empty] | Selangor
87 | 18312814C | I-PhIS027677218S | 2018-03-13 | Klinik Kesihatan Kalumpang | Order Management - Web | Record Prescription - Request cursor position at Original Prescriber Name field | En Omar request to default cursor position at Original Prescriber Name field. For current version, the default cursor position is at drug name field. | [5 empty] | Selangor
88 | 18323114C | I-PhIS028443318S | 2018-03-19 | Hospital Tanjung Karang | Order Management - Web | Record Prescription - Admission-Visit Type appear Outpatient | Puan Aishah reported Visit Type auto default to Outpatient at Admission even Dispensing Location : Farmasi Pesakit Dalam. Location Setup : Not tick to visit type : Outpatient | [5 empty] | Selangor
89 | 18323153C | I-PhIS028445118S | 2018-03-19 | Hospital Tanjung Karang | Order Management - Web | Record Prescription - Request wardstock not auto tick | Puan Aishah request wardstock drug not auto tick during order. | [5 empty] | Selangor
90 | 18332672C | I-PhIS029123118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Order Management - Web | Transcribe Order - Permohonan penambahbaikan untuk turutan cetakan pada label ubat | En Omar membuat permohonan penambahbaikan untuk turutan cetakan pada label printer. Menurut pengguna, jika pesakit pernah presribe ubat di fasiliti, dan datang lagi sekali untuk prescribe yang baru, pengguna harus mencetak label ubat. contoh: Transcribe order > medication profile > current medication menunjukkan ubat-ubat untuk pesakit. Jika di dalam current medication, senarai ubat yang pertama adalah ubat A, yg kedua adalah ubat B, dan ketiga adalah ubat C, akan tetapi di dalam surat ubat dari doktor menyatakan senarai ubat C adalah ubat yg pertama, ubat A yang kedua, dan ubat B adalah yang ketiga. Pengguna memohon supaya jika pengguna tanda senarai ubat di current medication mengikut senarai surat ubat doktor dan tekan butang 'Save', di cetakan label ubat yang keluar dari mesin cetakan ubat juga begitu. | [5 empty] | Selangor
91 | 18298693C | I-PhIS026707118S | 2018-03-05 | Pejabat Kesihatan Daerah Hulu Langat | Pharmacy Inventory | Request to enable for Update Batch Expiry Date | Cik Afiqah request to enable Edit/Update Batch Expiry when doing Second receiving Scenario : User had enter wrong expiry Date for the first Receiving. After proceed for second receiving with same Batch number it will follow 1st expiry date which is wrong. Therefore user request when proceed for another receiving the Expiry Date also updated. | [5 empty] | Selangor
92 | 18302474C | I-PhIS027013218S | 2018-03-07 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Slow Moving Item - Request to allow save without need to enter Offer Qty | Encik Omar request to allow save without need to enter Offer Qty. He inform sometimes he unable to complete key-in record due to busy with other things. His step as below:- 1. He go to Slow Moving Item 2. Click add button 3. Click List button 4. He select several items (eg: 20 items) 5. He only manage to enter offer qty for 5 items 6. System not allow to save | [5 empty] | Selangor
93 | 18315616C | I-PhIS027903118S | 2018-03-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request to allow level 3 access 'Disseminate' | En Omar request to allow user from level 3 access 'Disseminate' module. Email from user:- Merujuk kepada perkara di atas, saya ingin bertanya penggunaan modul ini di 'level 3'. Oleh kerana saya bertugas di Klinik Kesihatan, maka modul 'Disseminate' di level 3 TIDAK mendatangkan kebaikan dan kemudahan kepada unit saya kerana unit lain di fasiliti saya tidak menggunakan 'PhIS'. | [5 empty] | Selangor
94 | 18317272C | I-PhIS028011118S | 2018-03-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request allow to edit and resend transaction again | User want to continue using 1st disseminate transaction for 2nd disseminate. User request system allow to edit and resend the disseminate without generate list item again. Example: User informed in 1st disseminate still have balance item. So, he request system allow to edit on 1st disseminate transaction and allow to resend for 2nd disseminate. For, current situation user need to generate list item (for slow moving & Near expiration item) if he want to send 2nd disseminate. | [5 empty] | Selangor
95 | 18318933C | I-PhIS028129118S | 2018-03-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent (Inter Facility) - Request to edit at Indent details | Encik Omar request at screen indent details user able to edit and change qty before approve and go to next screen at RIQ (Inter). | [5 empty] | Selangor
96 | 18318972C | I-PhIS028131118S | 2018-03-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request of update stock available | User request that if user sent disseminate to external facility, external facility able to view their stock available and keep update their stock available. So indenter able to indent based on stock that they have only. | [5 empty] | Selangor
97 | 18321413C | I-PhIS028317118S | 2018-03-16 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Inventory - Stock adjustment | User request to change add adjustment item screen different depends on UOM (SKU or PKU) select by user before click add item. User inform if user select PKU at UOM add adjustment item screen show same information as user select SKU at UOM. User request if user select PKU at UOM there no information in SKU show at add adjustment screen. | [5 empty] | Selangor
98 | 18331794C | I-PhIS029085118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | RIQ (Inter) - Request insert details user indenter | User request to insert details indenter before user approve the transaction (At screen Inter Facility Indent) and before issue. Details: Nama: Contact no: Email: | [5 empty] | Selangor
99 | 18331833C | I-PhIS029089118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Issue (Online) - Insert details indenter into Generate Issue Note | User request to insert details indenter into Generate Issue Note. As of now only appear name of indenter but user want add more details such as: 1) Contact no 2) Address Facility 3) Email | [5 empty] | Selangor
100 | 18333915C | I-PhIS029221318S | 2018-03-26 | Pejabat Kesihatan Daerah Hulu Selangor | Pharmacy Inventory | Issue (Offline) - Date not tally item been issue | User Mr Izzat reported order issue been approve on 26/3/2018 but date item been issue is 21/3/2018. Tarikh Pesanan: 21/3/2018 but date in Dilengkapkan Oleh Stor Pemesan appear as 26/3/2018. User also reported date Dikeluarkan dan Direkod oleh: appear as 21/3/2018 but order been approve on 26/3/2018 Issue note no : n02ps001-0000991 Manual issue no : M02PS001-0001172 | [5 empty] | Selangor
101 | 18337234C | I-PhIS029457118S | 2018-03-27 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request enhancement in RIQ(Inter/Intra) | Encik Omar request Stock Available appear as (PKU or SKU). If in PKU, user request able to issue out in quantity decimal point. Current Situation Encik Omar confuse the stock available in SKU or PKU, it takes time to make calculation to reconfirmed the value of PKU. User also request able to issue out using decimal point because user already save using UOM = PKU, but suddenly only 1 item not enough to issue out in PKU. | [5 empty] | Selangor
102 | 18339172C | I-PhIS029605118S | 2018-03-28 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent (Inter Facility) - Request notification for rejected indent | En Omar request notification for rejected indent. Details by user: - He make indent > issuer facility receive the indent but he reject to do issuing due to not enough stock > indenter facility can get notification once the indent was reject by issuer facility. | [5 empty] | Selangor
103 | 18340247C | I-PhIS029709618S | 2018-03-28 | Pejabat Kesihatan Daerah Hulu Selangor | Pharmacy Inventory | KEWPS10 - Tarikh bekalan dikehendaki not appear | User reported Tarikh bekalan dikehendaki not appear in KEWPS10. User query this column is capture from which transaction. User has check in issue report and receiving report but both transaction not appear. Kindly refer attachment for both transaction. Details as below: Issue No: M02PS001-0001165 E02PS001-0001947 | [5 empty] | Selangor
104 | 18342480C | I-PhIS029897118S | 2018-03-29 | Klinik Kesihatan Gombak Setia | Pharmacy Inventory | Generate RCL - Request to enable generate item with HQ inactive | Pn Sabrina request to enable generate item with HQ inactive. She want to make condemn, she go to Generate RCL and click on RCL button, item not found. Check in Item Master, HQ status is Inactive. Inform her that item with HQ status Inactive will not display in RCL screen. She acknowledged and request to proceed with request - enhancement. | [5 empty] | Selangor
105 | 18345453C | I-PhIS030119118S | 2018-03-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent Interfacility (SPUB) -Request for notification | Encik Omar request got notification when user from other facility receive and open the indent SPUB and also got notification after 1 week if user from other facility still not receive and open the indent spub. Reason Since item urgent need to dispense to patient, user need to monitor the item status for further action | [5 empty] | Selangor
106 | 18331716C | I-PhIS029077118S | 2018-03-23 | Klinik Kesihatan Gombak Setia | Report/Enquiry | Report/Enquiry - SPUB Activities no record | Pn Liana reported when she generate SPUB Activites from 1/3/2018 until 23/3/2018 only 1 patient record appear. She dont have a manual record but she confirm have a patient SPUB for this month. She also inform today she has patient SPUB but not include in report SPUB Activites. Example patient SPUB for today. Name Patient:NOR KHAIRIAH IDRIS | [5 empty] | Selangor
107 | 18346455C | I-PhIS030191218S | 2018-03-31 | Hospital Kajang | Report/Enquiry | Stock Balance by Drug/Non Drug - Request to provide filter by date range | User request to provide filter by date range. | [5 empty] | Selangor
108 | 18323474C | I-PhIS028469318S | 2018-03-19 | Hospital Dungun | MTAC | MTAC Reporting(specific details) - Request trace back old record for follow up patient | Miss Adira request to trace back old record for follow up patient in specific details. Type of MTAC: Warfarin Problem: PhIS give option yes/no. If user click yes/no, still need to key in the information. This will duplicate user's work and take lot of time. Request: User request, if click yes, it will auto appear details previous record. It user select no then user have to key in. | [5 empty] | Terengganu
109 | 18324872C | I-PhIS028587118S | 2018-03-20 | Klinik Kesihatan Bandar Tun Razak | Patient Management | Patient Label - Request to increase font size | User request to increase font size for label especially address because it to small and have a more space. This is because user need print label for use for shipping (Poslaju) to patient. Kindly please refer attachment. | [5 empty] | W. Persekutuan
110 | 18323933C | I-PhIS028501318S | 2018-03-19 | Hospital Rehabilitasi Cheras | Pharmacy Inventory | Slow Moving Item - New item receive also generate | User reported new item received also on list of generate in slow moving item. User query on this item still new and no transaction make but appear on list of slow moving item. User just received item today. List item: 10.0800.01 12.3605.10 12.3605.11 12.3651.03 13.2600.01 17.3601.23 25.1001.04 | [5 empty] | W. Persekutuan

## HQ(BPF)
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Johor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18322416C | I-PhIS028393218S | 2018-03-19 | Klinik Kesihatan Sultan Ismail | General Module | Login PhIS - Request to extend expiry date of password | En Faiz request to extend expiry date of password. He inform that current requirement which is password will be inactive after 3 months is too short. Therefore, he want to extend it for at least 5 months.
2 | 18303133C | I-PhIS027047118S | 2018-03-07 | Hospital Pakar Sultanah Fatimah | Inpatient Pharmacy | Fill List - Unable to proceed fill list - double click, display button | User reported no stock available for this item. We need to untick or hold the medication. But when we double click, the prescription opens at the preparation screen. However, we are unable to hold because all the buttons are missing at preparation screen. Refer user attachment for further reference. Drug effected: Insulin regular Actrapid. Patient Name: Rozihana bt Abdullah
3 | 18313256C | I-PhIS027721118S | 2018-03-13 | Hospital Pakar Sultanah Fatimah | Outpatient Pharmacy | Screening & Verification - Wrong allocation qty | System calculates wrongly the allocation qty of warfarin weekly dose. MRN: HPSF00031746
4 | 18315174C | I-PhIS027865318S | 2018-03-14 | Klinik Kesihatan Paya Mas | Outpatient Pharmacy | request to add column select check box at screen dispensing | user request to add column select check box at screen dispensing to allow user select few patient for dispensing in one time. user inform if there have 1000 record of patient, user have to enter one by one to clear patient name at screen dispensing.
5 | 18325253C | I-PhIS028617118S | 2018-03-20 | Hospital Permai | Outpatient Pharmacy | SPUB R1 form - Request to add column TCA appointment with doctor | Ms Li Hun Tan request to add new column as TCA appointment with doctor date in SPUB R1 form. She inform it can make easier for user and patient to view when patient TCA with doctor even she send spub out to other facility.
6 | 18300333C | I-PhIS026841118S | 2018-03-06 | Hospital Pakar Sultanah Fatimah | Patient Management | Medication Profile - Additional Info - Request to add column 'updated by' for drug remark history | User request to add column 'updated by' for drug remark history at Additional Info (Medication Profile). Refer user attachment for further reference.
7 | 18302140C | I-PhIS026969118S | 2018-03-07 | Klinik Kesihatan Sri Gading | Report/Enquiry | KPI2(b) and Prescription Dispense not tally | User Miss Syarifah reported Bilangan Perkara Diproses in KPI29b) not tally with Prescription Dispense for Average dispense. Update: User filter date from 21/12/2018 until 18/1/2018. For jumlah Jumlah Preskripsi Diterima in KPI2b is 2287 and Bilangan Perkara Diproses in KPI2b is 7368
8 | 18318633C | I-PhIS028107118S | 2018-03-15 | Hospital Permai | Report/Enquiry | Request to have report PF 5.1a 'Aktiviti pengurusan perskripsi farmasi pesakit luar in PhIS | Request to have report PF 5.1a Aktiviti pengurusan perskripsi farmasi pesakit luar in PhIS. Currently, the report is only available in BI tools. User request to make this report in PhIS so that they can compare the report between both BI Tools ans PhIS.
9 | 18328438C | I-PhIS028835218S | 2018-03-21 | Hospital Sultanah Aminah | Report/Enquiry | KEWPS 5 - Request to edit card no | User request system allowed to edit card no in KEWPS 5 report.
10 | 18338675C | I-PhIS029565418S | 2018-03-28 | Klinik Kesihatan Batu Pahat | Report/Enquiry | Request to have report for Prescription by Doctor. | En.Zafifi request to have a report to view record prescription by Doctor Name. The record will list total of prescription specifically by Doctor.
11
12
13
14
15
16
17
18
19
20

## Kedah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18303713C | I-PhIS027085118S | 2018-03-07 | Pejabat Kesihatan Daerah Kuala Muda | Pharmacy Inventory | Receive item from supplier - Request to remove statement For Non-Drug Item batch is not applicable | Puan Azilawani request to remove statement For Non-Drug Item batch is not applicable at receive item from supplier module. It will confuse user. Reason: Even user not key in the batch no, phis still generate batch not applicable . User not sure that statement is information or instruction for user no need to key in the batch number. Steps: Receive item from supplier (AP/LP/Contract DO) Create new record fill up all requirement Add item Remove statement For Non-Drug Item batch is no applicable
2 | 18293035C | I-PhIS026299218S | 2018-03-01 | Hospital Jitra | Report/Enquiry | Patient Discharge - Request to add filter column by Discharge Date | User request to add filter column by Discharge Date. User want to know the total of Discharge date when she generate the date. Currently, system only shows date by Visit Date not Discharge Date.
3
4
5
6
7
8
9
10

## Kelantan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18324933C | I-PhIS028589118S | 2018-03-20 | Hospital Tanah Merah | Clinical Pharmacokinetic Services (CPS) & TDM | TDM - Request to have at least one mandatory section after sample accepted stage | Base on report number 18314612C got TDM record which her staff only proceed until sample accepted but at the system the record already as result viewed. After checking one of her staff already proceed it until result viewed and without proper detail/report. This happens due to after sample accepted stage the is no mandatory section and her staff accidentally proceed until result viewed Pn Nik request to add at least one mandatory section to prevent this issue happen again in future.
2 | 18336992C | I-PhIS029461118S | 2018-03-27 | Hospital Tanah Merah | Order Management - Mobile | Medication Profile (IPAD) - Request to change next/ previous arrow to be more visible | Pn Nik Ezmiza request to change next/ previous arrow to be more visible. Or put it as 'next' button and 'previous' button in order to acknowledged user for existing function. Based on previous report: 18329633C
3 | 18307436C | I-PhIS027309118S | 2018-03-09 | Hospital Tanah Merah | Outpatient Pharmacy | Intervention - Dosage column dimmed | Miss Siti reported want to change dosage. But user unable to proceed due to column dosage was dimmed. Already try with another ID,same problem reported. drug name : Ceftazidime 1g Injection RX: ICU0000334147 Patien name : Zarina bt othman Mrn : HTM00023263
4 | 18334214C | I-PhIS029237218S | 2018-03-26 | Hospital Machang | Pharmacy Inventory | KEWPS10 (offline) - Dikeluarkan dan Direkod oleh appear detail same with Telah Diluluskan dan Direko | User Mrs Hafizah reported detail for Dikeluarkan dan Direkod oleh same with Telah Diluluskan dan Direkodkan oleh Example No Pegeluaran : M02PS001-0004117 Issue type : Intra-facility
5
6
7
8
9
10
11
12

## Melaka
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18297273C | I-PhIS026607118S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Request remove mandatory for field Status of Intervention * | Cik Asmirah request for Status of Intervention * can be change to not mandatory or provide NA. This is due some work process not direct to Doctor.
2 | 18297293C | I-PhIS026609118S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Request to Increase Character limitation | Cik Asmirah request to increase character Limitation for field Pharmacist Recommendation .
3 | 18297313C | I-PhIS026611218S | 2018-03-05 | Klinik Kesihatan Peringgit | MTAC | MTAC Reporting - Outcome Column not appear at Report | Cik Asmirah reported she had complete for Pharmaceutical Care Issue and key in Outcome Field. However when print the report the Outcome Field was not appear at printed report. Happens to all patient
4 | 18298414C | I-PhIS026687118S | 2018-03-05 | Hospital Alor Gajah | Pharmacy Inventory | Item/Product Buffer Level - Request not mandatory set default vote code | Pn Lai request at screen Item/Product Buffer Level, remove the mandatory to set default vote code. Because, some of the item/drugs are not solely bought under 1 vote only. Instead, they might bought under other vote code depend on situation. If this setting still apply, she worry that user make mistake buying item under wrong vote although in PO screen user still can change to another vote code. She also added, if the mandatory is removed, system should allow user to save the details even the field Default Vote Code is blank at Item/Product Buffer Level screen.
5 | 18298773C | I-PhIS026719118S | 2018-03-05 | Pejabat Kesihatan Daerah Melaka Tengah | Pharmacy Inventory | Penalty Report (DMI) - Report stated name by DMI | En.Wafi reported when view Penalty report he unable to track the report from which Facility. This is due all the list stated DMI instead of user name. He had 10 page for Penalty report to approve but all is stated user DMI.
6 | 18321153C | I-PhIS028291118S | 2018-03-16 | Hospital Alor Gajah | Pharmacy Inventory | Purchase Order - Request unit price into 4 decimal point | User request for unit price can be key in 4 decimal places during purchase order. User mention current system only allowed user to key in unit price only for 2 decimal places and it will affect total of price and report.
7
8
9
10
11
12

## N_Sembilan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18327593C | I-PhIS028781118S | 2018-03-21 | Klinik Kesihatan Seremban (TPC) | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - TDM Add Result not appear | User reported that TDM Add result not appear in TDM Reporting screen. According to user, sample and result already sent manual to Hospital, then after she receive manual and fill into TDM reporting result not appear. Step by user: TDM Reporting - Search Patient - Click + button - Click Add+ button - TDM Add result not appear.
2 | 18332137C | I-PhIS029105118S | 2018-03-23 | Klinik Kesihatan Ampangan (TPC) | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Reporting - TDM Add Result not appear | User reported that TDM Add result not appear in TDM Reporting screen. According user she already proceed at TDM order. MRN:950215915048
3 | 18311893C | I-PhIS027607218S | 2018-03-12 | Klinik Kesihatan Port Dickson | Outpatient Pharmacy | Report - VAS Registry: Request to add field advance search | Puan Nadia request to add field advance search just like module (screening&verification,preparation, dispensing). User want the report of partial supply patient based on mode of service and next collection date patient.
4 | 18305355C | I-PhIS027197218S | 2018-03-08 | Klinik Kesihatan Sikamat (TPC) | Pharmacy Inventory | Penalty - Request to Ep approve date follow as in PO screen | She request to change Ep approve date in Penalty module same as in PO screen. Tittle: Penalty - Recomended delay days show wrong value Pn Wani reported that the recommended delay day that system show for Penalty PE21-05060206-18300012 is wrong. Should be the recommended delay days is 2, but system show 6 days.User inform she accidently approve it. User want to know is it okay with current record? Penalty no : PE21-05060206-18300012 Manual calculation :2 day system show: 6
5 | 18323173C | I-PhIS028449218S | 2018-03-19 | Hospital Tampin | Pharmacy Inventory | Request created item in HQ set to facility status active | This issue raised in pharmaniaga dialogue. Pn Radznah requested if there are new item created and activated in IWP, it will exist in facility with facility status = active. For example: item Tetanus Toxoid changed from code 07.0004.03 to 07.0004.02. When HQ activated item code 07.0004.02 in IWP, the code will appear in facility with facility status active. So facility do not need to activate the item manually in PHIS.
6 | 18323233C | I-PhIS028453118S | 2018-03-19 | Hospital Tampin | Pharmacy Inventory | Request system automatic set default for brand | This issue raised in Pharmaniaga dialogue. En Kamil requested system will automatically set default for item brand if user not set it manually. Current system, user unable to select item that not set brand default. due to this user requested system will automatically set default to any brand if user not set default manually.
7 | 18311794C | I-PhIS027603218S | 2018-03-12 | Klinik Kesihatan Ampangan (TPC) | Report/Enquiry | Laporan Kos Per Preskripsi Fasiliti KKM - Enable search by Discipline | User Lim Xinli request to enable search by Discipline in Laporan Kos Per Preskripsi Fasiliti KKM Current Situation: unable to differentiate between medication prescribed by dental/medical officer in 'Laporan Kos Per Preskripsi Fasiliti KKM.' Search by 'Department' returns no results. Request: enable search by Discipline in Laporan Kos Per Preskripsi Fasiliti KKM, as per example shown in Drug Utilisation report. Kindly refer attachment
8 | 18315855C | I-PhIS027919118S | 2018-03-14 | Hospital Tuanku Jaafar | Report/Enquiry | Purchase Order by Drug/Item - Filter function for Report | User request option to filter by type exists on report generation page but is non-functional. Kindly enable filtering by type. This request is based on advised at report 18282873C.

## Pahang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18344334C | I-PhIS030039118S | 2018-03-30 | Hospital Tengku Ampuan Afzan | Manufacturing - CDR | CDR Preparation - Enable for Print Worksheet | En.Nasri request to Enable Print Worksheet at CDR Dispensing . As for now only available at CDR Preparation. User concern if user have missed to print at CDR preparation.
2 | 18326234C | I-PhIS028685118S | 2018-03-20 | Hospital Raub | Outpatient Pharmacy | Medication Order - Unable to edit Drug SPUB Online | Miss Young reported unable to edit below patient medication for SPUB online. According to user duration in system show wrong and when want to edit and add drug nothing appear. She confirm no error appear or processing happen but she unable to edit. HRAUB00092964
3 | 18308512C | I-PhIS027375118S | 2018-03-09 | Hospital Raub | Patient Management | Medication Profile - Allergy - Allergy reaction not appear | User reported already enter allergy reaction during user enter allergy for patient. But when user open medication profile patient, allergy reaction not appear. User inform only appear drug name, severity and identification date. MRN: HRAUB00082376
4 | 18301533C | I-PhIS026925118S | 2018-03-06 | Hospital Tengku Ampuan Afzan | Report/Enquiry | Receive Item Report - Request to provide filter by drug and vaccine | User request to provide able to filter by item/drug name and able to filter by item vaccine.
5
6
7
8
9
10
11
12
13
14
15

## Perak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18307814C | I-PhIS027331418S | 2018-03-09 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request able to edit therapy start and end date | En Hilmi request able to edit therapy start and end date in drug details section. According to user currently unable to edit/adjust the therapy start and end date for active medication for patient. Reason: Therapy start date in system will capture when pharmacist transcribe the drug but user inform supposedly pharmacist will enter when patient start take the drug. Therapy end date in system will capture last date of pharmacist transcribe the drug but user inform supposedly pharmacist will enter when patient stop take the drug. Step: ADR Reporting > search pt > click + > drug details section > tick 1 active drug > double click > unable to edit therapy start and end date
2 | 18313315C | I-PhIS027727118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Adverse Drug Reaction (ADR) | ADR Reporting - Request to enhance on ADR Reporting | En Hilmi request to enhance on ADR Reporting where add new option pop up message info example Do You Want to Register Allergic Card for this patient . Example: At Drug Details at ADR Reporting>Save>Pop up New message>
3 | 18314615C | I-PhIS027825118S | 2018-03-13 | Klinik Kesihatan Greentown | Adverse Drug Reaction (ADR) | ADR - Drug detail cannot be save | Miss Sherdila reported Drug detail cannot be save when the dose of drug is different than its strength. User give example. Kindly refer File upload Patient taking bisoprolol 1.25mg (half tab of 2.5mg) MRN: KKE08004500003705 LEONG POK@LIANG POK
4 | 18338193C | I-PhIS029523118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To change the arrow button to the button with word Add Sample | User reported Doctors need to right click the arrow button then Add Sample will be appear. This will make doctor confuse and cant find where to click as it is not easy to notice. Suggestion/Request: To change the arrow button to the button with word Add Sample as it will be easy to notice. Kindly please refer attachment.
5 | 18338213C | I-PhIS029525118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To auto expand the row after add/save the sample. | User reported Doctors need to click + to expand. This is not easy to be noticed by doctors. Therefore she request to auto expand the row after add/save the sample. Kindly please refer attachment.
6 | 18338233C | I-PhIS029527118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: Not allow to print prescription of TDM order if not complete confirm. | User reported Doctors can print prescription even not complete confirm the TDM order. This will cause the record not display in TDM Verification screen. Therefore she request not allow to print prescription of TDM order if not complete confirm. Kindly please refer attachment.
7 | 18338254C | I-PhIS029529118S | 2018-03-27 | Hospital Seri Manjung | Clinical Pharmacokinetic Services (CPS) & TDM | TDM Order - Request: To add on / to create / to able the doctors to find back the tdm order for repr | User reported doctors cannot reprint the TDM order form if they had cancel X the screen. This will cause doctors doing multiple order TDM. Therefore she request To add on / to create / to able the doctors to find back the tdm order for reprint.. as a suggestion in TDM History. Kindly please refer attachment.
8 | 18307773C | I-PhIS027331318S | 2018-03-09 | Hospital Bahagia Ulu Kinta | Drug Information & Consumer Education | Drug Info - Request to enable Drug Information Request No in printed report | En Hilmi request to enable Drug Information Request No in printed report. He inform have Drug Information Request No when he generate drug info. However, Drug Information Request No not included when he print report. User also inform currently, facility name appear twice at the header of printed report.
9 | 18338293C | I-PhIS029533118S | 2018-03-27 | Hospital Seri Manjung | Inpatient Pharmacy | Request patient auto discharge once dispense medication done | Pn. Roshaliza request patient auto discharge once dispense medication done. Justifikasi : Berlaku kekangan di unit hasil(BDM) dan kaunter pendaftaran apabila tidak discharge patient bila keluar wad. Jika berlaku keadaan ini, Staff Kaunter terpaksa discharge patient dahulu, kemudian keyin untuk pendaftaran wad or klinik. Ini menjadikan beban kerja bertambah samaada di kaunter atau pon di wad. Justeru itu, kami mencadangkan agar sistem auto discharge selepas patient ambil ubat di farmasi.
10 | 18293753C | I-PhIS026345118S | 2018-03-01 | Hospital Tapah | MTAC | MTAC Reporting - Request able to insert justification in column | User request able to insert justification in column for Lives with Family Members & Nursing Home. Currently system only allow to insert justification for others. Kindly refer attachment for reference.
11 | 18337273C | I-PhIS029459118S | 2018-03-27 | Klinik Kesihatan Greentown | MTAC | MTAC Order - Unable to change to cancel status | User reported unable to cancel MTAC reporting in progress eventhough there is an edit button given. During MTAC reporting there is a need to cancel report while at the In Progress stage due to sudden discontinuation of counseling session with patient. Refer user attachment for reference. MRN - KKE08004500077573 Unable to cancel MTAC reporting in progress eventhough there is an edit button given. During MTAC reporting there is a need to cancel report while at the progress stage due to sudden discontinuation of counseling session with patient. Kindly rectify the issue ASAP. Thank you.
12 | 18343276C | I-PhIS029957118S | 2018-03-29 | Klinik Kesihatan Jelapang | MTAC | Request to simplify DFIT chart (understanding score) for medication counseling and MTAC reporting | Suggestion: To change the current DFIT chart setting. Instead of allowing Pharmacist to tick (Yes/No) on each individual drug on Dose, frequency, indication, time of administration. Suggest the system to tick on all drugs as Yes on Dose, frequency, indication, time of administration, so that pharmacist only tick NO on wrong dose, frequency, indication or time of administration. Refer user attachment for reference. Reason: To shorten documentation time on each individual drug, pharmacist only tick on drug (Dose, frequency, indication or time of adminstration) that patient taking wrongly.
13 | 18344773C | I-PhIS030063418S | 2018-03-30 | Hospital Taiping | MTAC | MTAC Reporting - Request able to cancel appointment for status Scheduled and In Progress | Pn Khor request user able to cancel appointment for MTAC visit with status Scheduled or In progress. Currently, she only able to cancel appointment with status Ordered.
14 | 18344473C | I-PhIS030047218S | 2018-03-30 | Hospital Seri Manjung | Order Management - Web | Order Management - Authorisation based on location | User request authorisation based on location and not based on department.The reason as example below:- First scenario OPD MO doing locum in ED during weekend/night, so the prescription should go for ED HOD/specialist talk list not OPD HOD/specialist. This is becasue durgs prescribed in ED not in OPD HOD/specalist liability. second scenario Ophthal MO review medical patient for eye cases and prescribed drugs. Authorisation should go to Ophthal HOD/ Specialist talk list. This scenario shouldn't flow as per first scenario.
15 | 18313233C | I-PhIS027717118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Outpatient Pharmacy | Print Allergy Card - Request to print in size as printer label | En Hilmi request to print allergy card in size as printer label due to currently print allergy card in size A4. He inform this not practically and waste time due to user need to print and cut for same as label.
16 | 18313258C | I-PhIS027719218S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Outpatient Pharmacy | Print Allergy Card - Request new column for No Siri | En Hilmi request to add new column for No Siri next to column Patient MRN at screen Print Allergic Card.
17 | 18334954C | I-PhIS029279118S | 2018-03-26 | Hospital Tapah | Outpatient Pharmacy | SPUB Online - request to view order after click draft | Ms Low reported she already registered patient SPUB online on 26/2/2018. But when patient come today she inform unable to view order. According to user practically she received SPUB online for 7days and need register first. Step User: external notification > Online SPUB R1 Request Received > click register > medication profile > click SPUB online button > click draft . After one month later patient come she unable to view order. Therefore she request able to view order even already click draft without proceed confirm. She inform if she click button confirm it will affect as reserve qty. example pt id: 730614086457
18 | 18313293C | I-PhIS027725118S | 2018-03-13 | Hospital Bahagia Ulu Kinta | Patient Management | Clinical Summary - Request to add new column at Allergy | En Hilmi request to add new column at Allergy part at screen Clinical Summary.He inform at Allergy part not show how allergic patient. Therefore he request to add new column Reaction Details next to Allergen. So that he will known more details/summary info reaction for allergy patient.
19 | 18313174C | I-PhIS027711118S | 2018-03-13 | Klinik Kesihatan Karai | Pharmacy Inventory | Prepacking - Request to add price in all drug label | User request to add price in all drug label. User claimed currently her facility prepack drug to KK Desa and KK Desa not use the system. Thus, it's easy for KK Desa receive the label with price.
20 | 18251008C | I-PhIS023105118S | 2018-01-25 | Hospital Taiping | Ward Pharmacy | Ward Pharmacy(CP2) - Request to add pin scoree for patient | User request to add new column PIN SCORE field . This is due user claim for Vital Sign 5 need to attached with PIN Score as advice by MOH. Refer file upload.
21 | 18255375C | I-PhIS023471318S | 2018-01-30 | Klinik Kesihatan Pulau Pangkor | General Module | Item/Product Buffer Level - request able to search by page | User Miss Khadijah request able to search by page.Due it will reduce time for user to search 1 by 1 page. User also request to able to search for another module.
22
23
24

## P.Pinang
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18314233C | I-PhIS027793118S | 2018-03-13 | Hospital Pulau Pinang | Adverse Drug Reaction (ADR) | ADR Reporting -Request to able edit record even after confirmed | User request to be able to edit record even after it already confirmed. This is due to in future, it will have integration with NPRA, thus they need to ensure that all the details in the report is correct before sent to NPRA
2 | 18344594C | I-PhIS030053118S | 2018-03-30 | Hospital Pulau Pinang | Adverse Drug Reaction (ADR) | Adverse Drug Reaction - Request to remove (*) for Date End Of Reaction | User request to remove (*) for Date End Of Reaction due some of the reaction still on going.
3 | 18313952C | I-PhIS027771318S | 2018-03-13 | Klinik Kesihatan Seberang Jaya | Outpatient Pharmacy | SPUB - request to disable selection for facility with Implementation Type indent | user request to disable selection for facility with Implementation Type indent when user select facility for SPUB to prevent user from select wrong facility because some facility did not supply drug to patient example at KK Permatang Pauh
4 | 18295453C | I-PhIS026463118S | 2018-03-02 | Hospital Seberang Jaya | Pharmacy Inventory | Drug-non drug catalog-Request to add column SPUB | En Shuhaimi requested to add column SPUB in drug non drug catalog to facility. The value might be Yes or No .This function will enable facility to indent / received the item without set buffer level , min/max storage for the item. The item will be allowed to level 2 level 3 user to indent the item automatically. Also SPUB flag might be include in unit catalogue list to allow the facility to do that unit to do SPUB indent for the item and not allow the item to be indent as normal item. If the item set as SPUB YES the item will not appear during purchasing or doing RIL/RPL. This is because the facility will not purchase the item from supplier. facility will indent it from other facility. Example : Hospital seberang Jaya is not specialize in cardio so this facility will only indent the item from other facility that always keep the item.
5 | 18337594C | I-PhIS029487218S | 2018-03-27 | Hospital Seberang Jaya | Pharmacy Inventory | Indent (intra-facility) - Item not appear | User Mr Goh reported item not appear for C01BB01110P3001XX.01 if user select Item Purchase Type as LP.If user select Item Purchase Type under ALL, item code appear. Item Purchase Type : LP Facility status : Active Unit catalog : Exist
6 | 18319793C | I-PhIS028193118S | 2018-03-15 | Hospital Pulau Pinang | Special Drug Request | Special Drug Request - Request changes for Request By Batch | Puan Norshazan request changes for Request By : Batch. Current Situation When user print out SDR with status, Sending for KPK Approval. Print KPK Form. Patient Column still appear but blank. User request if tick to Request By Batch, the patient column do not need to be appear and replace with : Stock Hospital
7 | 18319814C | I-PhIS028195118S | 2018-03-15 | Hospital Pulau Pinang | Special Drug Request | Special Drug Request - Request add UOM strength for injection | Puan Norshazan request for 'Create New Drug' to add UOM strength for injection. Currently user unable to select any suitable UOM for injection. Example : mg/ml
8
9
10
11
12
13
14
15

## Perlis
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18345993C | I-PhIS030149118S | 2018-03-30 | Hospital Tuanku Fauziah | Report/Enquiry | Report - Prescription Management IP: Request to add order type for filter | User request to add order type for filter in Prescription Management IP. Currently there is no button Order Type to filter as Prescription Management OP. Order type: Discharge, Normal, SPUB
2
3
4
5
6
7
8
9
10
11
12
13

## Sabah
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18318413C | I-PhIS028087118S | 2018-03-15 | Hospital Pitas | Inpatient Pharmacy | Preparation : Administration Instruction Not appear for Print Preview | Cik Aqilah reported Administration Instruction Not appear for Print Preview. User had enter Administration Instruction bur when print out the Instruction was not appear. Happens to all patient.
2 | 18315494C | I-PhIS027891218S | 2018-03-14 | Klinik Kesihatan Felda Sahabat | Medication Counseling | Medication Counselling - Able to add backdated date more than 5 days | User request for system to allow Counseling to backdated more than 5days for document of their work in PhIS. Problem: In a typical work week, pharmacist will be busy counselling on Monday and Tuesday and will only have time to key in later in the week. Sometimes also it take a month to user key in their work.
3 | 18320153C | I-PhIS028221218S | 2018-03-16 | Hospital Dutchess of Kent | Medication Counseling | Request Group medication counseling able back dated for 7 day | Request Group medication counseling able set back dated for 7 day
4 | 18293973C | I-PhIS026361118S | 2018-03-01 | Hospital Kota Marudu | Order Management - Web | Record Prescription - Kuantiti tidak ikut seperti yang ditetapkan dalam Drug Master | Ms Yew melaporkan bahawa beliau telah menetapkan Paracetamol 500 mg Tablet di Facility Setting (Drug Master) - Quantity per duration adalah 10 tablet per month. Walau bagaimanapun apabila beliau 'prescribe' di dalam sistem PhIS iaitu 2 biji untuk 4 kali sehari, sistem tidak ikut seperti yang telah ditetapkan iaitu 10 biji untuk sebulan, sistem masih kira untuk 2 biji untuk 4 kali sehari untuk sebulan kuantiti akan menjadi beratus biji.
5 | 18342773C | I-PhIS029919118S | 2018-03-29 | Hospital Tawau | Order Management - Web | Medication Order - Request auto display original prescriber name in list | User request auto display original prescriber name in list. User claimed only Visit Type as walk in not appear. If others Visit Type, it auto display to search doctor's name. Details as below: Visit Type: Walk In Location: Farmasi Pesakit Luar Department: Outpatient This order is for TDM Record Prescription > Medication Order > Filter at Visit/Admission > Click TDM > Original Prescriber Name not auto generate in list
6 | 18313434C | I-PhIS027733318S | 2018-03-13 | Hospital Dutchess of Kent | Pharmacy Inventory | Prepacking - Request to add unit price when print label | Miss Saw request to add price when print label at prepacking screen for Label Unit of Dose : 20 mm x 13.3 mm. Refer file upload. User inform price refer item master.
7 | 18337652C | I-PhIS029493118S | 2018-03-27 | Cawangan Farmasi Logistik Negeri | Pharmacy Inventory | RIQ (Inter) - Request to add new column under indenter information (SKU) | Ms Pamela request to add new column under indenter information (SKU) at RIQ (inter) screen. She request if can include new column which is stock balance for indenter.
8 | 18298934C | I-PhIS026723118S | 2018-03-05 | Hospital Tuaran | Report/Enquiry | Issue Report - request new filter | User request to add new filter at Issue Report which indicate the origin the item that she issue. Example, user want to know whether the item that she issue is originally she get from Procurement or from other facility (should state facility name)
9 | 18322633C | I-PhIS028403118S | 2018-03-19 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Stock Balance By Drug/Non-Drug - Inactive item still appear on list | User reported drug still appear in list eventhough has been Inactive for Facility Status at Drug Non Drug Catalogue. User informed that user just new transaction just made yesterday and user already deactivated before that day. It happen to many drug. User can give 1 example of drug happen Drug code: A02AA10912L2101XX Item code: A02AA10912L2101XX.03 & 01.2407.06.074T
10 | 18337632C | I-PhIS029491218S | 2018-03-27 | Cawangan Farmasi Logistik Negeri | Report/Enquiry | Report/Enquiry - Request to trace back order qty for indent inter in report | Ms Pamela request to trace back order qty for indent inter that CFLN not supply yet. She request if can include report under report/enquiry so that she able to generate the report by all item. This list is important for user due to she want to refer before make procurement in future.
11
12
13
14
15
16
17
18
19
20

## Sarawak
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18292258C | I-PhIS026255118S | 2018-03-01 | Hospital Serian | General Module | User profile : Password expired date default to 90 days | Miss Chai reported password expired date default to 90 days. User inform already change Password Expiry at facility information but still default to 90 days. No popup appear when save at facility information. Also query why system default to 90 days.
2 | 18337477C | I-PhIS029477118S | 2018-03-27 | Hospital Umum Sarawak | Manufacturing - Radiopharmaceutical | Kit Preparation - Volume not found | Miss Lucinda reported there is no value in Volume column for reported item. She inform there is no Worksheet ID as she has not save record yet. Kindly refer attachment provided. Item Code: RPH000041.02
3 | 18341860C | I-PhIS029845118S | 2018-03-29 | Hospital Umum Sarawak | Manufacturing - Radiopharmaceutical | Radiopharma kit Preparation - unable to allocate quantity to 0 | Radiopharma kit Preparation - unable to allocate quantity to 0 as error show only positive number is allowed as user inform some times user did not use the drug as preparation item code: RPH000041.01 RPH000041.02
4 | 18345713C | I-PhIS030129218S | 2018-03-30 | Hospital Miri | Order Management - Web | Transcribe order - unable to add item facility inactive | User Mr Ong request item status facility inactive to not appear when transcribe order
5 | 18315492C | I-PhIS027893118S | 2018-03-14 | Hospital Kapit | Outpatient Pharmacy | SPUB Patient List - Patient not appear - taper - RX partially dispensed, drug acknowledged | Pn Hamizah reported that patient not appear when she want to make new SPUB patient at screen SPUB Patient List. MRN No: HKPT00099862 Step by user: SPUB Patient List > Key in MRN No patient > click on search button > no record appear
6 | 18323593C | I-PhIS028479118S | 2018-03-19 | Hospital Umum Sarawak | Outpatient Pharmacy | Screening & Verification - Request to enable view Remarks | Miss Julie inform she key-in Remarks for one of drug in Screening and Verification screen. She already proceed until Dispense. Patient RX still active. By some reason, she want to view the information entered in Remarks but current system has no such function. Therefore, she request to enable user view Remarks for Full Supply patient. Both active and inactive medication.
7 | 18329652C | I-PhIS028919118S | 2018-03-22 | MUSN Kuching | Pharmacy Inventory | KEWPS10 - Request to remove name at column Dikeluarkan & Direkod Oleh . | User request to remove name at column Dikeluarkan & Direkod Oleh in KEWPS-10 for offline issue.
8 | 18293853C | I-PhIS026351118S | 2018-03-01 | Hospital Kapit | Report/Enquiry | Inpatient Prescription - Request include Discontinue prescription | Puan Hamizah request include Discontinue prescription in report. Current Situation Puan Hamizah informed data not tally when compare with manual prescription.
9 | 18306793C | I-PhIS027259118S | 2018-03-08 | Hospital Sibu | Report/Enquiry | Report - Inpatient Prescription: Request to insert Outpatient Dispensing Location | User request to insert Outpatient Dispensing Location into this report so user able to trace back any prescription that officer did.
10 | 18320854C | I-PhIS028271118S | 2018-03-16 | Klinik Kesihatan Bandar Miri | Report/Enquiry | KPI 2 (b) - 'Preskripsi Diterima' less than Prescription Dispense | Miss Kong reported No of 'Preskripsi Diterima' less than Prescription Dispensed. She inform she check No of 'Preskripsi Diterima' is 933 in KPI 2 (b). But when she check in Prescripsion Dispensed, total show as 1037. Kindly refer attachment provided.
11 | 18328573C | I-PhIS028841418S | 2018-03-21 | Hospital Kapit | Ward Pharmacy | request - allowed user to access CP2 detail even patient already discharge | user request system allowed user to access CP2 detail even patient already discharge. as per inform by user, user unable to view CP2 detail if patient already discharge.
12
13
14
15
16
17
18
19
20

## Selangor
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18335933C | I-PhIS029361118S | 2018-03-26 | Klinik Kesihatan Kalumpang | Adverse Drug Reaction (ADR) | ADR - Asterisks Sign | User informed that column that appear to be filled in strictly(asterisks sign ' * ') just 2 which is Product Generic Name & drug Type only . But for drug details to be appeared at ADR, he said user have to fill all column inside drug detail coulmn. User request asterisks (*) sign have to be present at all column inside screen add drug detail.
2 | 18313573C | I-PhIS027743118S | 2018-03-13 | Klinik Kesihatan Kalumpang | General Module | PhIS - System automatically login | Merujuk kepada perkara di atas, saya dapati Cubaan 1: 1. Buka PhIS, ' Log In ' 2. Buka 'Connect Manage' , CM, tanpa perlu 'Log In' 3. Tutup ( Bukan 'Log Out' ) PhIS. Jangan tutup CM 4. Buka semula PhIS. Sistem tidak memerlukan untuk 'Log In' lagi. Skrin akan terus masuk ke dalam PhIS Cubaan 2: 1. Buka 'Connect Manage' , CM, tanpa perlu 'Log In' 2. Buka PhIS, ' Log In ' 3. Tutup ( Bukan 'Log Out' ) PhIS. Jangan tutup CM 4. Buka semula PhIS. Sistem tidak memerlukan untuk 'Log In' lagi. Skrin akan terus masuk ke dalam PhIS Di dalam kedua - dua simulasi ini saya dapati apabila CM dibiarkan dibuka, PhIS hanya perlu sekali sahaja 'Log In', kerana selepas PhIS ditutup (Bukan 'Log Out') dan dibuka semula, PhiS akan terus terbuka tak perlu 'Log In' lagi kepada 'Log In' ID orang yang terakhir menggunakan PhIS. Saya berharap, saya tidak diminta meng 'upload' video simulasi ini, kerana pihak tuan boleh mencuba sendiri menggunakan komputer tuan.
3 | 18295392C | I-PhIS026457218S | 2018-03-02 | Klinik Kesihatan Serendah | Medication Counseling | Medication Counselling order - Unable to change status to cancelled. | User reported unable to cancel medication counselling order for patient due to edit button not appear. But confirmed by user she already proceed with counselling reporting. Counselling Order No: MC1800000404 MRN: KKE10006100090661
4 | 18312814C | I-PhIS027677218S | 2018-03-13 | Klinik Kesihatan Kalumpang | Order Management - Web | Record Prescription - Request cursor position at Original Prescriber Name field | En Omar request to default cursor position at Original Prescriber Name field. For current version, the default cursor position is at drug name field.
5 | 18323114C | I-PhIS028443318S | 2018-03-19 | Hospital Tanjung Karang | Order Management - Web | Record Prescription - Admission-Visit Type appear Outpatient | Puan Aishah reported Visit Type auto default to Outpatient at Admission even Dispensing Location : Farmasi Pesakit Dalam. Location Setup : Not tick to visit type : Outpatient
6 | 18323153C | I-PhIS028445118S | 2018-03-19 | Hospital Tanjung Karang | Order Management - Web | Record Prescription - Request wardstock not auto tick | Puan Aishah request wardstock drug not auto tick during order.
7 | 18332672C | I-PhIS029123118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Order Management - Web | Transcribe Order - Permohonan penambahbaikan untuk turutan cetakan pada label ubat | En Omar membuat permohonan penambahbaikan untuk turutan cetakan pada label printer. Menurut pengguna, jika pesakit pernah presribe ubat di fasiliti, dan datang lagi sekali untuk prescribe yang baru, pengguna harus mencetak label ubat. contoh: Transcribe order > medication profile > current medication menunjukkan ubat-ubat untuk pesakit. Jika di dalam current medication, senarai ubat yang pertama adalah ubat A, yg kedua adalah ubat B, dan ketiga adalah ubat C, akan tetapi di dalam surat ubat dari doktor menyatakan senarai ubat C adalah ubat yg pertama, ubat A yang kedua, dan ubat B adalah yang ketiga. Pengguna memohon supaya jika pengguna tanda senarai ubat di current medication mengikut senarai surat ubat doktor dan tekan butang 'Save', di cetakan label ubat yang keluar dari mesin cetakan ubat juga begitu.
8 | 18298693C | I-PhIS026707118S | 2018-03-05 | Pejabat Kesihatan Daerah Hulu Langat | Pharmacy Inventory | Request to enable for Update Batch Expiry Date | Cik Afiqah request to enable Edit/Update Batch Expiry when doing Second receiving Scenario : User had enter wrong expiry Date for the first Receiving. After proceed for second receiving with same Batch number it will follow 1st expiry date which is wrong. Therefore user request when proceed for another receiving the Expiry Date also updated.
9 | 18302474C | I-PhIS027013218S | 2018-03-07 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Slow Moving Item - Request to allow save without need to enter Offer Qty | Encik Omar request to allow save without need to enter Offer Qty. He inform sometimes he unable to complete key-in record due to busy with other things. His step as below:- 1. He go to Slow Moving Item 2. Click add button 3. Click List button 4. He select several items (eg: 20 items) 5. He only manage to enter offer qty for 5 items 6. System not allow to save
10 | 18315616C | I-PhIS027903118S | 2018-03-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request to allow level 3 access 'Disseminate' | En Omar request to allow user from level 3 access 'Disseminate' module. Email from user:- Merujuk kepada perkara di atas, saya ingin bertanya penggunaan modul ini di 'level 3'. Oleh kerana saya bertugas di Klinik Kesihatan, maka modul 'Disseminate' di level 3 TIDAK mendatangkan kebaikan dan kemudahan kepada unit saya kerana unit lain di fasiliti saya tidak menggunakan 'PhIS'.
11 | 18317272C | I-PhIS028011118S | 2018-03-14 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request allow to edit and resend transaction again | User want to continue using 1st disseminate transaction for 2nd disseminate. User request system allow to edit and resend the disseminate without generate list item again. Example: User informed in 1st disseminate still have balance item. So, he request system allow to edit on 1st disseminate transaction and allow to resend for 2nd disseminate. For, current situation user need to generate list item (for slow moving & Near expiration item) if he want to send 2nd disseminate.
12 | 18318933C | I-PhIS028129118S | 2018-03-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent (Inter Facility) - Request to edit at Indent details | Encik Omar request at screen indent details user able to edit and change qty before approve and go to next screen at RIQ (Inter).
13 | 18318972C | I-PhIS028131118S | 2018-03-15 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Disseminate - Request of update stock available | User request that if user sent disseminate to external facility, external facility able to view their stock available and keep update their stock available. So indenter able to indent based on stock that they have only.
14 | 18321413C | I-PhIS028317118S | 2018-03-16 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Inventory - Stock adjustment | User request to change add adjustment item screen different depends on UOM (SKU or PKU) select by user before click add item. User inform if user select PKU at UOM add adjustment item screen show same information as user select SKU at UOM. User request if user select PKU at UOM there no information in SKU show at add adjustment screen.
15 | 18331794C | I-PhIS029085118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | RIQ (Inter) - Request insert details user indenter | User request to insert details indenter before user approve the transaction (At screen Inter Facility Indent) and before issue. Details: Nama: Contact no: Email:
16 | 18331833C | I-PhIS029089118S | 2018-03-23 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Issue (Online) - Insert details indenter into Generate Issue Note | User request to insert details indenter into Generate Issue Note. As of now only appear name of indenter but user want add more details such as: 1) Contact no 2) Address Facility 3) Email
17 | 18333915C | I-PhIS029221318S | 2018-03-26 | Pejabat Kesihatan Daerah Hulu Selangor | Pharmacy Inventory | Issue (Offline) - Date not tally item been issue | User Mr Izzat reported order issue been approve on 26/3/2018 but date item been issue is 21/3/2018. Tarikh Pesanan: 21/3/2018 but date in Dilengkapkan Oleh Stor Pemesan appear as 26/3/2018. User also reported date Dikeluarkan dan Direkod oleh: appear as 21/3/2018 but order been approve on 26/3/2018 Issue note no : n02ps001-0000991 Manual issue no : M02PS001-0001172
18 | 18337234C | I-PhIS029457118S | 2018-03-27 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Request enhancement in RIQ(Inter/Intra) | Encik Omar request Stock Available appear as (PKU or SKU). If in PKU, user request able to issue out in quantity decimal point. Current Situation Encik Omar confuse the stock available in SKU or PKU, it takes time to make calculation to reconfirmed the value of PKU. User also request able to issue out using decimal point because user already save using UOM = PKU, but suddenly only 1 item not enough to issue out in PKU.
19 | 18339172C | I-PhIS029605118S | 2018-03-28 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent (Inter Facility) - Request notification for rejected indent | En Omar request notification for rejected indent. Details by user: - He make indent > issuer facility receive the indent but he reject to do issuing due to not enough stock > indenter facility can get notification once the indent was reject by issuer facility.
20 | 18340247C | I-PhIS029709618S | 2018-03-28 | Pejabat Kesihatan Daerah Hulu Selangor | Pharmacy Inventory | KEWPS10 - Tarikh bekalan dikehendaki not appear | User reported Tarikh bekalan dikehendaki not appear in KEWPS10. User query this column is capture from which transaction. User has check in issue report and receiving report but both transaction not appear. Kindly refer attachment for both transaction. Details as below: Issue No: M02PS001-0001165 E02PS001-0001947
21 | 18342480C | I-PhIS029897118S | 2018-03-29 | Klinik Kesihatan Gombak Setia | Pharmacy Inventory | Generate RCL - Request to enable generate item with HQ inactive | Pn Sabrina request to enable generate item with HQ inactive. She want to make condemn, she go to Generate RCL and click on RCL button, item not found. Check in Item Master, HQ status is Inactive. Inform her that item with HQ status Inactive will not display in RCL screen. She acknowledged and request to proceed with request - enhancement.
22 | 18345453C | I-PhIS030119118S | 2018-03-30 | Klinik Kesihatan Kalumpang | Pharmacy Inventory | Indent Interfacility (SPUB) -Request for notification | Encik Omar request got notification when user from other facility receive and open the indent SPUB and also got notification after 1 week if user from other facility still not receive and open the indent spub. Reason Since item urgent need to dispense to patient, user need to monitor the item status for further action
23 | 18331716C | I-PhIS029077118S | 2018-03-23 | Klinik Kesihatan Gombak Setia | Report/Enquiry | Report/Enquiry - SPUB Activities no record | Pn Liana reported when she generate SPUB Activites from 1/3/2018 until 23/3/2018 only 1 patient record appear. She dont have a manual record but she confirm have a patient SPUB for this month. She also inform today she has patient SPUB but not include in report SPUB Activites. Example patient SPUB for today. Name Patient:NOR KHAIRIAH IDRIS
24 | 18346455C | I-PhIS030191218S | 2018-03-31 | Hospital Kajang | Report/Enquiry | Stock Balance by Drug/Non Drug - Request to provide filter by date range | User request to provide filter by date range.

## Terengganu
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18323474C | I-PhIS028469318S | 2018-03-19 | Hospital Dungun | MTAC | MTAC Reporting(specific details) - Request trace back old record for follow up patient | Miss Adira request to trace back old record for follow up patient in specific details. Type of MTAC: Warfarin Problem: PhIS give option yes/no. If user click yes/no, still need to key in the information. This will duplicate user's work and take lot of time. Request: User request, if click yes, it will auto appear details previous record. It user select no then user have to key in.
2
3
4
5
6

## HKL
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18306774C | I-PhIS027261118S | 2018-03-08 | Hospital Kuala Lumpur | Pharmacy Inventory | Purchase Order (Appl) - Request to create one screen for manual purchase order | User request to create one screen for manual purchase order (Appl). User claimed she want insert manual order like Lp item & Contract. User consent regarding integration issue in eP. When order not enter to eP and user need receive manually.
2
3
4
5
6
7
8
9
10
11
12

## WLabuan
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6

## WP
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1 | 18324872C | I-PhIS028587118S | 2018-03-20 | Klinik Kesihatan Bandar Tun Razak | Patient Management | Patient Label - Request to increase font size | User request to increase font size for label especially address because it to small and have a more space. This is because user need print label for use for shipping (Poslaju) to patient. Kindly please refer attachment.
2 | 18323933C | I-PhIS028501318S | 2018-03-19 | Hospital Rehabilitasi Cheras | Pharmacy Inventory | Slow Moving Item - New item receive also generate | User reported new item received also on list of generate in slow moving item. User query on this item still new and no transaction make but appear on list of slow moving item. User just received item today. List item: 10.0800.01 12.3605.10 12.3605.11 12.3651.03 13.2600.01 17.3601.23 25.1001.04
3
4
5
6

## Institut
No | Report No | Ticket No | Reported Date | Facility | Module | Ticket Title | Ticket Description | Group | Detail Description of Request | Reason of Request | Support/ Reject | Remarks
1
2
3
4
5
6
7
8
9
10